## Read Me
Hawthorn Gardens — BuildLite UAT Master Pack
Purpose | Controlled fictional known-answer development for BuildLite commercial/CVR testing.
Version | v1 commercial design baseline — not yet imported into BuildLite.
Development | Hawthorn Gardens — 24 private homes.
Cost-code basis | BuildLite shipped 210-code master from server/data/cost_codes.json.
Principle | BuildLite should reproduce the Expected CVR; this workbook is the independent control answer.
Deliberate tests | Approved/pending CEs, credits, linked/direct recovery, material overspend, unbudgeted posting, forecast savings/overspends, actuals vs certificates.
Blue font | Hardcoded fictional UAT input.
Green font | Cross-sheet formula/link.
Black font | Calculation/formula.
Important | Fictional data for software testing only; not a market appraisal or investment case.

## Development Setup
Development Setup
Field | Value
Development | Hawthorn Gardens
Developer | BuildLite Homes Ltd
Location | Midlands (fictional)
Units | 24
Private Units | 24
Affordable Units | 0
Start Date | 2026-04-01
Target Completion | 2027-09-30
CVR Date | 2026-10-31
GDV | 8341500
Purpose | Permanent known-answer UAT development for BuildLite commercial/CVR testing
House Type | Beds | Approx ft² | Plots | No. Units
The Ash | 2 bed | 750 | 1-4 | 4
The Birch | 3 bed | 950 | 5-12 | 8
The Cedar | 3 bed | 1050 | 13-18 | 6
The Oak | 4 bed | 1350 | 19-24 | 6

## Cost Code Master
BuildLite Cost Code Master — 210 Codes
Cost Code | Sub-Heading | Trade | Element | Used in Hawthorn? | Original Budget (£) | Source
1100 | Land | Vendor | Land Cost | Yes | 1650000 | BuildLite repo master / fictional UAT assumption
1110 | Land | GOV | VAT on Land Purchase | No | 0 | BuildLite repo master / fictional UAT assumption
1120 | Land | GOV | Stamp Duty - Incl VAT if applicable | Yes | 85000 | BuildLite repo master / fictional UAT assumption
1130 | Land | Consultant | Legal Fees - Solicitor | Yes | 25000 | BuildLite repo master / fictional UAT assumption
1140 | Land | Consultant | Option Fees | No | 0 | BuildLite repo master / fictional UAT assumption
1150 | Land | Consultant | Selling Agent Fees - | No | 0 | BuildLite repo master / fictional UAT assumption
1160 | Land | Vendor | Sundy Land Costs - Overage Payments | No | 0 | BuildLite repo master / fictional UAT assumption
1170 | Fees | Consultant | Planning Application & Supporting Fees | Yes | 35000 | BuildLite repo master / fictional UAT assumption
1180 | Fees | Consultant | Site Investigation | Yes | 25000 | BuildLite repo master / fictional UAT assumption
1190 | Fees | Consultant | Archaeology | Yes | 15000 | BuildLite repo master / fictional UAT assumption
1200 | Fees | Consultant | Contamination | Yes | 20000 | BuildLite repo master / fictional UAT assumption
1210 | Fees | Consultant | Design Fees | Yes | 40000 | BuildLite repo master / fictional UAT assumption
1220 | Fees | Consultant | Architects - Post Planning | Yes | 55000 | BuildLite repo master / fictional UAT assumption
1230 | Fees | Consultant | Engineers | Yes | 75000 | BuildLite repo master / fictional UAT assumption
1240 | Fees | Consultant | Surveys | Yes | 20000 | BuildLite repo master / fictional UAT assumption
1250 | Fees | Consultant | NHBC Bond Fees | Yes | 25000 | BuildLite repo master / fictional UAT assumption
1260 | Fees | Consultant | Insurance | Yes | 15000 | BuildLite repo master / fictional UAT assumption
1270 | Fees | Consultant | Planning Consultants | No | 0 | BuildLite repo master / fictional UAT assumption
1280 | Fees | Consultant | Highways Consultants | Yes | 20000 | BuildLite repo master / fictional UAT assumption
1290 | Fees | Consultant | Environmental Consultants | Yes | 15000 | BuildLite repo master / fictional UAT assumption
1300 | Fees | Consultant | M&E Consultants | Yes | 10000 | BuildLite repo master / fictional UAT assumption
1310 | Fees | LA | Sewers Adoption (s104): | Yes | 18000 | BuildLite repo master / fictional UAT assumption
1320 | Fees | LA | Highways Adoption (s18/38): | Yes | 22000 | BuildLite repo master / fictional UAT assumption
1330 | Fees | LA | S278 Fees | Yes | 12000 | BuildLite repo master / fictional UAT assumption
1340 | Fees | LA | Building Regulation Fees | Yes | 22000 | BuildLite repo master / fictional UAT assumption
1350 | Fees | LA | Planning Fees | No | 0 | BuildLite repo master / fictional UAT assumption
1360 | Fees | Consultant | SAP Calculations | Yes | 10000 | BuildLite repo master / fictional UAT assumption
1370 | Fees | Consultant | Air Tests | Yes | 7500 | BuildLite repo master / fictional UAT assumption
1380 | Fees | Consultant | NHBC - Warranty & Build control | Yes | 48000 | BuildLite repo master / fictional UAT assumption
1400 | Fees | Lender | Finance lenders Fees | No | 0 | BuildLite repo master / fictional UAT assumption
1410 | Fees | Consultant | Other Fees | Yes | 12500 | BuildLite repo master / fictional UAT assumption
2100 | Prelims | Direct | Site Manager | Yes | 95000 | BuildLite repo master / fictional UAT assumption
2101 | Prelims | Direct | Assistant Site Manager | Yes | 55000 | BuildLite repo master / fictional UAT assumption
2110 | Prelims | Direct | Direct Staff Bonuses | Yes | 12000 | BuildLite repo master / fictional UAT assumption
2120 | Prelims | Direct | Direct Staff NIC on Bonuses | No | 0 | BuildLite repo master / fictional UAT assumption
2130 | Prelims | Direct | NIC on Salary | Yes | 18000 | BuildLite repo master / fictional UAT assumption
2140 | Prelims | Direct | Pension | Yes | 9000 | BuildLite repo master / fictional UAT assumption
2150 | Prelims | Direct | Forklift Driver - Direct | No | 0 | BuildLite repo master / fictional UAT assumption
2151 | Prelims | Agency | Forklift Driver - Agency | Yes | 36000 | BuildLite repo master / fictional UAT assumption
2160 | Prelims | Direct | Labourer - Direct | No | 0 | BuildLite repo master / fictional UAT assumption
2161 | Prelims | Agency | Labourer - Agency | Yes | 30000 | BuildLite repo master / fictional UAT assumption
2170 | Prelims | Agency | Site staff - Holiday Cover | No | 0 | BuildLite repo master / fictional UAT assumption
2180 | Prelims | Sub-Con | Principle Contractor Set-Up | Yes | 20000 | BuildLite repo master / fictional UAT assumption
2190 | Prelims | Plant Hire | Forklift Truck | Yes | 34000 | BuildLite repo master / fictional UAT assumption
2191 | Prelims | Plant Hire | Generator | No | 0 | BuildLite repo master / fictional UAT assumption
2200 | Prelims | Plant Hire | Site Office | Yes | 28000 | BuildLite repo master / fictional UAT assumption
2201 | Prelims | Plant Hire | Site Cabins | Yes | 18000 | BuildLite repo master / fictional UAT assumption
2202 | Prelims | Plant Hire | Containers | Yes | 10000 | BuildLite repo master / fictional UAT assumption
2210 | Prelims | Plant Hire | Oasis Unit | No | 0 | BuildLite repo master / fictional UAT assumption
2211 | Prelims | Material | Fuel | Yes | 22000 | BuildLite repo master / fictional UAT assumption
2220 | Prelims | Sub-Con | Compound - Groundworks | No | 0 | BuildLite repo master / fictional UAT assumption
2230 | Prelims | Utility | Site Electric Usage | Yes | 18000 | BuildLite repo master / fictional UAT assumption
2231 | Prelims | Utility | Site Water Usage | Yes | 7500 | BuildLite repo master / fictional UAT assumption
2232 | Prelims | Utility | TBS | No | 0 | BuildLite repo master / fictional UAT assumption
2240 | Prelims | Utility | Plot Utility Bills Pre-Handover | No | 0 | BuildLite repo master / fictional UAT assumption
2250 | Prelims | Plant Hire | Road Cleaning - F Lift Road brush | Yes | 8000 | BuildLite repo master / fictional UAT assumption
2260 | Prelims | Plant Hire | Road Cleaning - Road sweep | Yes | 15000 | BuildLite repo master / fictional UAT assumption
2270 | Prelims | Material | Tipping Skips | No | 0 | BuildLite repo master / fictional UAT assumption
2280 | Prelims | Plant Hire | Skips | Yes | 12000 | BuildLite repo master / fictional UAT assumption
2290 | Prelims | Material | Pallets | No | 0 | BuildLite repo master / fictional UAT assumption
2300 | Prelims | Material | Bulk Items | No | 0 | BuildLite repo master / fictional UAT assumption
2310 | Prelims | Material | PPE | No | 0 | BuildLite repo master / fictional UAT assumption
2311 | Prelims | Material | Site consumables | Yes | 10000 | BuildLite repo master / fictional UAT assumption
2320 | Prelims | Material | Pedestrian Barriers | No | 0 | BuildLite repo master / fictional UAT assumption
2321 | Prelims | Material | Heras Fencing | Yes | 14000 | BuildLite repo master / fictional UAT assumption
2330 | Prelims | Plant Hire | Security - Cameras | Yes | 15000 | BuildLite repo master / fictional UAT assumption
2340 | Prelims | Agency | Security - Static guards | No | 0 | BuildLite repo master / fictional UAT assumption
2350 | Prelims | Misc. | Contingency | Yes | 30000 | BuildLite repo master / fictional UAT assumption
3100 | R&S | Sub-Con | Groundworker Prelims | Yes | 120000 | BuildLite repo master / fictional UAT assumption
3110 | R&S | Sub-Con | Duct Crossings | Yes | 35000 | BuildLite repo master / fictional UAT assumption
3120 | R&S | Sub-Con | Footpaths to Base | Yes | 55000 | BuildLite repo master / fictional UAT assumption
3130 | R&S | Sub-Con | Saw cut & break out road for kerb install to channel / laybys | No | 0 | BuildLite repo master / fictional UAT assumption
3140 | R&S | Sub-Con | White Lining | No | 0 | BuildLite repo master / fictional UAT assumption
3150 | R&S | Sub-Con | Street Name Plates - Install | No | 0 | BuildLite repo master / fictional UAT assumption
3160 | R&S | Sub-Con | R&S - REMEDIALS: | Yes | 20000 | BuildLite repo master / fictional UAT assumption
3170 | R&S | Sub-Con | Electricity Mains - Mains & Connections | Yes | 55000 | BuildLite repo master / fictional UAT assumption
3180 | R&S | Sub-Con | Gas Mains | No | 0 | BuildLite repo master / fictional UAT assumption
3190 | R&S | Sub-Con | Water Mains - Laying & Connection | Yes | 35000 | BuildLite repo master / fictional UAT assumption
3200 | R&S | Sub-Con | Telephone Mains | Yes | 15000 | BuildLite repo master / fictional UAT assumption
3210 | R&S | Sub-Con | Fibre | Yes | 15000 | BuildLite repo master / fictional UAT assumption
3220 | R&S | Sub-Con | Street Lights - Supply & Install Columns | Yes | 36000 | BuildLite repo master / fictional UAT assumption
3230 | R&S | Sub-Con | Street Lighting Connections | Yes | 9000 | BuildLite repo master / fictional UAT assumption
3240 | R&S | Sub-Con | Public Open Space & Play Areas | Yes | 45000 | BuildLite repo master / fictional UAT assumption
3250 | R&S | Sub-Con | Play Equipment | No | 0 | BuildLite repo master / fictional UAT assumption
3260 | R&S | Sub-Con | Hard Landscaping | Yes | 35000 | BuildLite repo master / fictional UAT assumption
3270 | R&S | Sub-Con | Roads & Sewers Contingency | Yes | 25000 | BuildLite repo master / fictional UAT assumption
3500 | Plot | Sub-con | Service Trenches & Ducts | Yes | 95000 | BuildLite repo master / fictional UAT assumption
3510 | Plot | Sub-con | Muck Away | Yes | 65000 | BuildLite repo master / fictional UAT assumption
3520 | Plot | Sub-con | Plot Drainage incl Internal Drainage | Yes | 165000 | BuildLite repo master / fictional UAT assumption
3530 | Plot | Sub-con | Paths - Slabs | Yes | 42000 | BuildLite repo master / fictional UAT assumption
3540 | Plot | Sub-con | Private Drive Formation | Yes | 70000 | BuildLite repo master / fictional UAT assumption
3541 | Plot | Sub-con | Private Drives Complete | Yes | 62000 | BuildLite repo master / fictional UAT assumption
3550 | Plot | Sub-con | Shared Drive Formation | Yes | 25000 | BuildLite repo master / fictional UAT assumption
3551 | Plot | Sub-con | Shared Drive Complete | Yes | 22000 | BuildLite repo master / fictional UAT assumption
3570 | Plot | Sub-con | Screen Walls - Foundations | Yes | 28000 | BuildLite repo master / fictional UAT assumption
3580 | Plot | Sub-con | Screen Walls - Superstructure | Yes | 45000 | BuildLite repo master / fictional UAT assumption
3590 | Plot | Sub-con | Fencing | Yes | 62000 | BuildLite repo master / fictional UAT assumption
3600 | Plot | Sub-con | Plot Clearance | Yes | 24000 | BuildLite repo master / fictional UAT assumption
3610 | Plot | Sub-con | Plot Regrade | Yes | 30000 | BuildLite repo master / fictional UAT assumption
3620 | Plot | Sub-con | Topsoil placement | Yes | 32000 | BuildLite repo master / fictional UAT assumption
3630 | Plot | Sub-con | Turfing - Adoptable Verges to Roads | No | 0 | BuildLite repo master / fictional UAT assumption
3640 | Plot | Sub-con | Planting | Yes | 48000 | BuildLite repo master / fictional UAT assumption
3650 | Plot | Sub-con | Misc. Landscaping | Yes | 18000 | BuildLite repo master / fictional UAT assumption
3660 | Plot | Sub-con | Pre-Occupation Maintenance | No | 0 | BuildLite repo master / fictional UAT assumption
3670 | Plot | Sub-con | After Sales Maintenance | No | 0 | BuildLite repo master / fictional UAT assumption
3680 | Plot | Misc. | Contingency - Plot Groundworks | Yes | 22000 | BuildLite repo master / fictional UAT assumption
4100 | Super-Structure | Sub-Con | Pre-Cast Concrete | Yes | 35000 | BuildLite repo master / fictional UAT assumption
4110 | Super-Structure | Sub-Con | Scaffolding | Yes | 82000 | BuildLite repo master / fictional UAT assumption
4120 | Super-Structure | Sub-Con | Brickwork | Yes | 245000 | BuildLite repo master / fictional UAT assumption
4130 | Super-Structure | Sub-Con | Carpentry | Yes | 180000 | BuildLite repo master / fictional UAT assumption
4140 | Super-Structure | Sub-Con | Contract Crane Hire | Yes | 24000 | BuildLite repo master / fictional UAT assumption
4150 | Super-Structure | Sub-Con | Cladding | Yes | 48000 | BuildLite repo master / fictional UAT assumption
4160 | Super-Structure | Sub-Con | Render | Yes | 38000 | BuildLite repo master / fictional UAT assumption
4170 | Super-Structure | Sub-Con | Steelwork | Yes | 22000 | BuildLite repo master / fictional UAT assumption
4180 | Super-Structure | Sub-Con | Roofing | Yes | 115000 | BuildLite repo master / fictional UAT assumption
4190 | Super-Structure | Sub-Con | PV | Yes | 72000 | BuildLite repo master / fictional UAT assumption
4200 | Super-Structure | Sub-Con | Windows and Ext. Doors | Yes | 125000 | BuildLite repo master / fictional UAT assumption
4210 | Super-Structure | Sub-Con | Garage Doors | Yes | 18000 | BuildLite repo master / fictional UAT assumption
4220 | Super-Structure | Sub-Con | Insulation | Yes | 38000 | BuildLite repo master / fictional UAT assumption
4230 | Super-Structure | Sub-Con | Plastering & Drylining | Yes | 128000 | BuildLite repo master / fictional UAT assumption
4240 | Super-Structure | Sub-Con | Plumbing & Heating | Yes | 190000 | BuildLite repo master / fictional UAT assumption
4250 | Super-Structure | Sub-Con | Electrical | Yes | 145000 | BuildLite repo master / fictional UAT assumption
4260 | Super-Structure | Sub-Con | Kitchen Fitting | Yes | 118000 | BuildLite repo master / fictional UAT assumption
4270 | Super-Structure | Sub-Con | Appliances | Yes | 58000 | BuildLite repo master / fictional UAT assumption
4280 | Super-Structure | Sub-Con | Stone Worktops | Yes | 28000 | BuildLite repo master / fictional UAT assumption
4290 | Super-Structure | Sub-Con | Wardrobes | No | 0 | BuildLite repo master / fictional UAT assumption
4300 | Super-Structure | Sub-Con | Carpets | Yes | 62000 | BuildLite repo master / fictional UAT assumption
4310 | Super-Structure | Sub-Con | LVT | Yes | 38000 | BuildLite repo master / fictional UAT assumption
4320 | Super-Structure | Sub-Con | Vinyl | Yes | 20000 | BuildLite repo master / fictional UAT assumption
4330 | Super-Structure | Sub-Con | Mastic & Sealing | Yes | 18000 | BuildLite repo master / fictional UAT assumption
4340 | Super-Structure | Sub-Con | Painting & Decoration | Yes | 92000 | BuildLite repo master / fictional UAT assumption
4350 | Super-Structure | Sub-Con | Ceramic Tiling | Yes | 48000 | BuildLite repo master / fictional UAT assumption
4360 | Super-Structure | Sub-Con | Cleaning | Yes | 30000 | BuildLite repo master / fictional UAT assumption
4500 | Super-Structure | Material | Bricks | Yes | 165000 | BuildLite repo master / fictional UAT assumption
4510 | Super-Structure | Material | Brickwork Specials | Yes | 12000 | BuildLite repo master / fictional UAT assumption
4520 | Super-Structure | Material | External Cladding | No | 0 | BuildLite repo master / fictional UAT assumption
4530 | Super-Structure | Material | Batten | No | 0 | BuildLite repo master / fictional UAT assumption
4540 | Super-Structure | Material | Membrane | No | 0 | BuildLite repo master / fictional UAT assumption
4550 | Super-Structure | Material | Tenmat fire barrier | No | 0 | BuildLite repo master / fictional UAT assumption
4560 | Super-Structure | Material | Blocks - Aggrtegate | Yes | 54000 | BuildLite repo master / fictional UAT assumption
4570 | Super-Structure | Material | Blocks - Airated | Yes | 42000 | BuildLite repo master / fictional UAT assumption
4580 | Super-Structure | Material | Sand Cement & Mortar | Yes | 52000 | BuildLite repo master / fictional UAT assumption
4590 | Super-Structure | Material | Cast Stone Heads | Yes | 20000 | BuildLite repo master / fictional UAT assumption
4600 | Super-Structure | Material | Cast Stone Cills | Yes | 18000 | BuildLite repo master / fictional UAT assumption
4610 | Super-Structure | Material | Lintels | Yes | 45000 | BuildLite repo master / fictional UAT assumption
4620 | Super-Structure | Material | Steel | No | 0 | BuildLite repo master / fictional UAT assumption
4630 | Super-Structure | Material | Chimneys | No | 0 | BuildLite repo master / fictional UAT assumption
4640 | Super-Structure | Material | Joists | Yes | 78000 | BuildLite repo master / fictional UAT assumption
4650 | Super-Structure | Material | Floor deck | Yes | 30000 | BuildLite repo master / fictional UAT assumption
4660 | Super-Structure | Material | Roof Timbers | Yes | 85000 | BuildLite repo master / fictional UAT assumption
4670 | Super-Structure | Material | Soffit & Fascia | Yes | 35000 | BuildLite repo master / fictional UAT assumption
4680 | Super-Structure | Material | Staircases | Yes | 34000 | BuildLite repo master / fictional UAT assumption
4690 | Super-Structure | Material | Carcassing Timbers | Yes | 38000 | BuildLite repo master / fictional UAT assumption
4700 | Super-Structure | Material | Window Board | Yes | 10000 | BuildLite repo master / fictional UAT assumption
4710 | Super-Structure | Material | Door Linings | Yes | 18000 | BuildLite repo master / fictional UAT assumption
4720 | Super-Structure | Material | Skirting & Architrave | Yes | 28000 | BuildLite repo master / fictional UAT assumption
4730 | Super-Structure | Material | Internal Doors | Yes | 42000 | BuildLite repo master / fictional UAT assumption
4740 | Super-Structure | Material | Ironmongery | Yes | 18000 | BuildLite repo master / fictional UAT assumption
4750 | Super-Structure | Material | Porches | No | 0 | BuildLite repo master / fictional UAT assumption
4760 | Super-Structure | Material | Insulation Materials | Yes | 68000 | BuildLite repo master / fictional UAT assumption
4770 | Super-Structure | Material | Fixings | Yes | 12000 | BuildLite repo master / fictional UAT assumption
4780 | Super-Structure | Material | Loft Traps | No | 0 | BuildLite repo master / fictional UAT assumption
4790 | Super-Structure | Material | Meter Boxes | Yes | 9000 | BuildLite repo master / fictional UAT assumption
4800 | Super-Structure | Material | Rooflight | No | 0 | BuildLite repo master / fictional UAT assumption
4810 | Super-Structure | Material | GRP Products | No | 0 | BuildLite repo master / fictional UAT assumption
4820 | Super-Structure | Material | General Material Sundries | Yes | 18000 | BuildLite repo master / fictional UAT assumption
5100 | Abnormals | Sub-con | Demolition / Site Clearance / Remediation: | Yes | 80000 | BuildLite repo master / fictional UAT assumption
5110 | Abnormals | Sub-con | Archaeology: | No | 0 | BuildLite repo master / fictional UAT assumption
5120 | Abnormals | Sub-con | Ecology: | Yes | 18000 | BuildLite repo master / fictional UAT assumption
5130 | Abnormals | Sub-con | Piling - Specialist: | No | 0 | BuildLite repo master / fictional UAT assumption
5140 | Abnormals | Sub-con | Piling - Groundworks: | No | 0 | BuildLite repo master / fictional UAT assumption
5150 | Abnormals | Sub-con | Abnormal Foundations: | No | 0 | BuildLite repo master / fictional UAT assumption
5160 | Abnormals | Sub-con | Raft Foundation: | No | 0 | BuildLite repo master / fictional UAT assumption
5170 | Abnormals | Sub-con | Attenuation Pond / Swales / Culverts: | Yes | 95000 | BuildLite repo master / fictional UAT assumption
5180 | Abnormals | Utility | Electric Sub-Station: | No | 0 | BuildLite repo master / fictional UAT assumption
5190 | Abnormals | Sub-con | Pump Station & Rising Main: | No | 0 | BuildLite repo master / fictional UAT assumption
5200 | Abnormals | Sub-con | Retaining Features & Steps: | Yes | 65000 | BuildLite repo master / fictional UAT assumption
5210 | Abnormals | Sub-con | Abnormal / Non-Plot Fencing & Walls: | No | 0 | BuildLite repo master / fictional UAT assumption
5220 | Abnormals | LA | S278 Fees: | No | 0 | BuildLite repo master / fictional UAT assumption
5230 | Abnormals | LA | S184 Fees: | No | 0 | BuildLite repo master / fictional UAT assumption
5240 | Abnormals | Sub-con | Earthworks - Arisings | Yes | 55000 | BuildLite repo master / fictional UAT assumption
5250 | Abnormals | Sub-con | POS / Abnormal Landscaping: | Yes | 25000 | BuildLite repo master / fictional UAT assumption
5260 | Abnormals | Sub-con | S278 Works: | Yes | 75000 | BuildLite repo master / fictional UAT assumption
5270 | Abnormals | Utility | Offsite Utility Services Maintenance: | No | 0 | BuildLite repo master / fictional UAT assumption
5280 | Abnormals | Utility | Offsite Utility Service Diversions: | No | 0 | BuildLite repo master / fictional UAT assumption
5290 | Abnormals | Sub-con | Render: | No | 0 | BuildLite repo master / fictional UAT assumption
5300 | Abnormals | Material | Black Weatherboarding: | No | 0 | BuildLite repo master / fictional UAT assumption
5310 | Abnormals | Sub-con | Vertical Tile Hanging: | No | 0 | BuildLite repo master / fictional UAT assumption
5320 | Abnormals | Sub-con | Stone Walling (Reconstituted / Prepped): | No | 0 | BuildLite repo master / fictional UAT assumption
5340 | Contributions | LA | S106 | Yes | 160000 | BuildLite repo master / fictional UAT assumption
5350 | Contributions | LA | CIL | Yes | 115000 | BuildLite repo master / fictional UAT assumption
6100 | Sales | Revenue | Private Units | No | 0 | BuildLite repo master / fictional UAT assumption
6110 | Sales | Consultant | Sales Legal Fees | Yes | 25000 | BuildLite repo master / fictional UAT assumption
6120 | Sales | Consultant | Estate Agents | Yes | 95000 | BuildLite repo master / fictional UAT assumption
6130 | Sales | Revenue | P/X Assisted Move | No | 0 | BuildLite repo master / fictional UAT assumption
6140 | Sales | Consultant | Advertising | Yes | 42000 | BuildLite repo master / fictional UAT assumption
6150 | Sales | Material | Signs & Flags | Yes | 12000 | BuildLite repo master / fictional UAT assumption
6160 | Sales | Sub-contract | Showhouse Furnishing - Showhome 1 | Yes | 35000 | BuildLite repo master / fictional UAT assumption
6170 | Sales | Sub-contract | Sales Office Set-up | Yes | 18000 | BuildLite repo master / fictional UAT assumption
6180 | Sales | Material | Health and Safety Equipment - Sales | No | 0 | BuildLite repo master / fictional UAT assumption
6190 | Sales | LA | Sales Business Rates - Showhome 1 | No | 0 | BuildLite repo master / fictional UAT assumption
6200 | Sales | Material | Sales Consumables | Yes | 8000 | BuildLite repo master / fictional UAT assumption
6210 | Sales | Sub-contract | Sales Running Costs - Sales Office Cleaning | Yes | 10000 | BuildLite repo master / fictional UAT assumption
6220 | Sales | Sub-contract | Sales Landscaping - Showhome | Yes | 12000 | BuildLite repo master / fictional UAT assumption
6230 | Sales | Sub-contract | Sales Landscape Maintenance | Yes | 10000 | BuildLite repo master / fictional UAT assumption
6240 | Sales | Sub-contract | Sales Parking Areas - Installation | No | 0 | BuildLite repo master / fictional UAT assumption
6250 | Sales | Sub-contract | Sales Fencing - Railings | No | 0 | BuildLite repo master / fictional UAT assumption
6260 | Sales | Material | Home Information Packs | Yes | 4000 | BuildLite repo master / fictional UAT assumption
6270 | Sales | Material | Welcome Packs | Yes | 5000 | BuildLite repo master / fictional UAT assumption
6280 | Sales | Utility | Utility Bills Pre-Handover | No | 0 | BuildLite repo master / fictional UAT assumption

## Original Budget
Original Development Budget
Cost Code | Sub-Heading | Trade | Element | Original Budget (£) | £/Unit | Active? | Assumption / Test Purpose
1100 | Land | Vendor | Land Cost | 1650000 | 68750 | Yes | Fictional UAT budget assumption.
1110 | Land | GOV | VAT on Land Purchase | 0 | 0 | No
1120 | Land | GOV | Stamp Duty - Incl VAT if applicable | 85000 | 3541.6667 | Yes | Fictional UAT budget assumption.
1130 | Land | Consultant | Legal Fees - Solicitor | 25000 | 1041.6667 | Yes | Fictional UAT budget assumption.
1140 | Land | Consultant | Option Fees | 0 | 0 | No
1150 | Land | Consultant | Selling Agent Fees - | 0 | 0 | No
1160 | Land | Vendor | Sundy Land Costs - Overage Payments | 0 | 0 | No
1170 | Fees | Consultant | Planning Application & Supporting Fees | 35000 | 1458.3333 | Yes | Fictional UAT budget assumption.
1180 | Fees | Consultant | Site Investigation | 25000 | 1041.6667 | Yes | Fictional UAT budget assumption.
1190 | Fees | Consultant | Archaeology | 15000 | 625 | Yes | Fictional UAT budget assumption.
1200 | Fees | Consultant | Contamination | 20000 | 833.3333 | Yes | Fictional UAT budget assumption.
1210 | Fees | Consultant | Design Fees | 40000 | 1666.6667 | Yes | Fictional UAT budget assumption.
1220 | Fees | Consultant | Architects - Post Planning | 55000 | 2291.6667 | Yes | Fictional UAT budget assumption.
1230 | Fees | Consultant | Engineers | 75000 | 3125 | Yes | Fictional UAT budget assumption.
1240 | Fees | Consultant | Surveys | 20000 | 833.3333 | Yes | Fictional UAT budget assumption.
1250 | Fees | Consultant | NHBC Bond Fees | 25000 | 1041.6667 | Yes | Fictional UAT budget assumption.
1260 | Fees | Consultant | Insurance | 15000 | 625 | Yes | Fictional UAT budget assumption.
1270 | Fees | Consultant | Planning Consultants | 0 | 0 | No
1280 | Fees | Consultant | Highways Consultants | 20000 | 833.3333 | Yes | Fictional UAT budget assumption.
1290 | Fees | Consultant | Environmental Consultants | 15000 | 625 | Yes | Fictional UAT budget assumption.
1300 | Fees | Consultant | M&E Consultants | 10000 | 416.6667 | Yes | Fictional UAT budget assumption.
1310 | Fees | LA | Sewers Adoption (s104): | 18000 | 750 | Yes | Fictional UAT budget assumption.
1320 | Fees | LA | Highways Adoption (s18/38): | 22000 | 916.6667 | Yes | Fictional UAT budget assumption.
1330 | Fees | LA | S278 Fees | 12000 | 500 | Yes | Fictional UAT budget assumption.
1340 | Fees | LA | Building Regulation Fees | 22000 | 916.6667 | Yes | Fictional UAT budget assumption.
1350 | Fees | LA | Planning Fees | 0 | 0 | No
1360 | Fees | Consultant | SAP Calculations | 10000 | 416.6667 | Yes | Fictional UAT budget assumption.
1370 | Fees | Consultant | Air Tests | 7500 | 312.5 | Yes | Fictional UAT budget assumption.
1380 | Fees | Consultant | NHBC - Warranty & Build control | 48000 | 2000 | Yes | Fictional UAT budget assumption.
1400 | Fees | Lender | Finance lenders Fees | 0 | 0 | No
1410 | Fees | Consultant | Other Fees | 12500 | 520.8333 | Yes | Fictional UAT budget assumption.
2100 | Prelims | Direct | Site Manager | 95000 | 3958.3333 | Yes | Fictional UAT budget assumption.
2101 | Prelims | Direct | Assistant Site Manager | 55000 | 2291.6667 | Yes | Fictional UAT budget assumption.
2110 | Prelims | Direct | Direct Staff Bonuses | 12000 | 500 | Yes | Fictional UAT budget assumption.
2120 | Prelims | Direct | Direct Staff NIC on Bonuses | 0 | 0 | No
2130 | Prelims | Direct | NIC on Salary | 18000 | 750 | Yes | Fictional UAT budget assumption.
2140 | Prelims | Direct | Pension | 9000 | 375 | Yes | Fictional UAT budget assumption.
2150 | Prelims | Direct | Forklift Driver - Direct | 0 | 0 | No
2151 | Prelims | Agency | Forklift Driver - Agency | 36000 | 1500 | Yes | Fictional UAT budget assumption.
2160 | Prelims | Direct | Labourer - Direct | 0 | 0 | No
2161 | Prelims | Agency | Labourer - Agency | 30000 | 1250 | Yes | Fictional UAT budget assumption.
2170 | Prelims | Agency | Site staff - Holiday Cover | 0 | 0 | No
2180 | Prelims | Sub-Con | Principle Contractor Set-Up | 20000 | 833.3333 | Yes | Fictional UAT budget assumption.
2190 | Prelims | Plant Hire | Forklift Truck | 34000 | 1416.6667 | Yes | Fictional UAT budget assumption.
2191 | Prelims | Plant Hire | Generator | 0 | 0 | No
2200 | Prelims | Plant Hire | Site Office | 28000 | 1166.6667 | Yes | Fictional UAT budget assumption.
2201 | Prelims | Plant Hire | Site Cabins | 18000 | 750 | Yes | Fictional UAT budget assumption.
2202 | Prelims | Plant Hire | Containers | 10000 | 416.6667 | Yes | Fictional UAT budget assumption.
2210 | Prelims | Plant Hire | Oasis Unit | 0 | 0 | No
2211 | Prelims | Material | Fuel | 22000 | 916.6667 | Yes | Fictional UAT budget assumption.
2220 | Prelims | Sub-Con | Compound - Groundworks | 0 | 0 | No
2230 | Prelims | Utility | Site Electric Usage | 18000 | 750 | Yes | Fictional UAT budget assumption.
2231 | Prelims | Utility | Site Water Usage | 7500 | 312.5 | Yes | Fictional UAT budget assumption.
2232 | Prelims | Utility | TBS | 0 | 0 | No
2240 | Prelims | Utility | Plot Utility Bills Pre-Handover | 0 | 0 | No
2250 | Prelims | Plant Hire | Road Cleaning - F Lift Road brush | 8000 | 333.3333 | Yes | Fictional UAT budget assumption.
2260 | Prelims | Plant Hire | Road Cleaning - Road sweep | 15000 | 625 | Yes | Fictional UAT budget assumption.
2270 | Prelims | Material | Tipping Skips | 0 | 0 | No
2280 | Prelims | Plant Hire | Skips | 12000 | 500 | Yes | Fictional UAT budget assumption.
2290 | Prelims | Material | Pallets | 0 | 0 | No
2300 | Prelims | Material | Bulk Items | 0 | 0 | No
2310 | Prelims | Material | PPE | 0 | 0 | No
2311 | Prelims | Material | Site consumables | 10000 | 416.6667 | Yes | Fictional UAT budget assumption.
2320 | Prelims | Material | Pedestrian Barriers | 0 | 0 | No
2321 | Prelims | Material | Heras Fencing | 14000 | 583.3333 | Yes | Fictional UAT budget assumption.
2330 | Prelims | Plant Hire | Security - Cameras | 15000 | 625 | Yes | Fictional UAT budget assumption.
2340 | Prelims | Agency | Security - Static guards | 0 | 0 | No
2350 | Prelims | Misc. | Contingency | 30000 | 1250 | Yes | Only £20k of £30k contingency expected to be used.
3100 | R&S | Sub-Con | Groundworker Prelims | 120000 | 5000 | Yes | Soft-ground approved CE plus unresolved muck-away risk.
3110 | R&S | Sub-Con | Duct Crossings | 35000 | 1458.3333 | Yes | Fictional UAT budget assumption.
3120 | R&S | Sub-Con | Footpaths to Base | 55000 | 2291.6667 | Yes | Fictional UAT budget assumption.
3130 | R&S | Sub-Con | Saw cut & break out road for kerb install to channel / laybys | 0 | 0 | No
3140 | R&S | Sub-Con | White Lining | 0 | 0 | No
3150 | R&S | Sub-Con | Street Name Plates - Install | 0 | 0 | No
3160 | R&S | Sub-Con | R&S - REMEDIALS: | 20000 | 833.3333 | Yes | Fictional UAT budget assumption.
3170 | R&S | Sub-Con | Electricity Mains - Mains & Connections | 55000 | 2291.6667 | Yes | Fictional UAT budget assumption.
3180 | R&S | Sub-Con | Gas Mains | 0 | 0 | No
3190 | R&S | Sub-Con | Water Mains - Laying & Connection | 35000 | 1458.3333 | Yes | Fictional UAT budget assumption.
3200 | R&S | Sub-Con | Telephone Mains | 15000 | 625 | Yes | Fictional UAT budget assumption.
3210 | R&S | Sub-Con | Fibre | 15000 | 625 | Yes | Fictional UAT budget assumption.
3220 | R&S | Sub-Con | Street Lights - Supply & Install Columns | 36000 | 1500 | Yes | Fictional UAT budget assumption.
3230 | R&S | Sub-Con | Street Lighting Connections | 9000 | 375 | Yes | Fictional UAT budget assumption.
3240 | R&S | Sub-Con | Public Open Space & Play Areas | 45000 | 1875 | Yes | Fictional UAT budget assumption.
3250 | R&S | Sub-Con | Play Equipment | 0 | 0 | No
3260 | R&S | Sub-Con | Hard Landscaping | 35000 | 1458.3333 | Yes | Fictional UAT budget assumption.
3270 | R&S | Sub-Con | Roads & Sewers Contingency | 25000 | 1041.6667 | Yes | Fictional UAT budget assumption.
3500 | Plot | Sub-con | Service Trenches & Ducts | 95000 | 3958.3333 | Yes | Fictional UAT budget assumption.
3510 | Plot | Sub-con | Muck Away | 65000 | 2708.3333 | Yes | Fictional UAT budget assumption.
3520 | Plot | Sub-con | Plot Drainage incl Internal Drainage | 165000 | 6875 | Yes | Fictional UAT budget assumption.
3530 | Plot | Sub-con | Paths - Slabs | 42000 | 1750 | Yes | Fictional UAT budget assumption.
3540 | Plot | Sub-con | Private Drive Formation | 70000 | 2916.6667 | Yes | Fictional UAT budget assumption.
3541 | Plot | Sub-con | Private Drives Complete | 62000 | 2583.3333 | Yes | Fictional UAT budget assumption.
3550 | Plot | Sub-con | Shared Drive Formation | 25000 | 1041.6667 | Yes | Fictional UAT budget assumption.
3551 | Plot | Sub-con | Shared Drive Complete | 22000 | 916.6667 | Yes | Fictional UAT budget assumption.
3570 | Plot | Sub-con | Screen Walls - Foundations | 28000 | 1166.6667 | Yes | Fictional UAT budget assumption.
3580 | Plot | Sub-con | Screen Walls - Superstructure | 45000 | 1875 | Yes | Fictional UAT budget assumption.
3590 | Plot | Sub-con | Fencing | 62000 | 2583.3333 | Yes | Fictional UAT budget assumption.
3600 | Plot | Sub-con | Plot Clearance | 24000 | 1000 | Yes | Fictional UAT budget assumption.
3610 | Plot | Sub-con | Plot Regrade | 30000 | 1250 | Yes | Fictional UAT budget assumption.
3620 | Plot | Sub-con | Topsoil placement | 32000 | 1333.3333 | Yes | Fictional UAT budget assumption.
3630 | Plot | Sub-con | Turfing - Adoptable Verges to Roads | 0 | 0 | No
3640 | Plot | Sub-con | Planting | 48000 | 2000 | Yes | Fictional UAT budget assumption.
3650 | Plot | Sub-con | Misc. Landscaping | 18000 | 750 | Yes | Fictional UAT budget assumption.
3660 | Plot | Sub-con | Pre-Occupation Maintenance | 0 | 0 | No
3670 | Plot | Sub-con | After Sales Maintenance | 0 | 0 | No
3680 | Plot | Misc. | Contingency - Plot Groundworks | 22000 | 916.6667 | Yes | Fictional UAT budget assumption.
4100 | Super-Structure | Sub-Con | Pre-Cast Concrete | 35000 | 1458.3333 | Yes | Fictional UAT budget assumption.
4110 | Super-Structure | Sub-Con | Scaffolding | 82000 | 3416.6667 | Yes | Fictional UAT budget assumption.
4120 | Super-Structure | Sub-Con | Brickwork | 245000 | 10208.3333 | Yes | Productivity loss pushes final cost above budget/commitment.
4130 | Super-Structure | Sub-Con | Carpentry | 180000 | 7500 | Yes | Control package: forecast at current PO, delivering £5k saving.
4140 | Super-Structure | Sub-Con | Contract Crane Hire | 24000 | 1000 | Yes | Fictional UAT budget assumption.
4150 | Super-Structure | Sub-Con | Cladding | 48000 | 2000 | Yes | Fictional UAT budget assumption.
4160 | Super-Structure | Sub-Con | Render | 38000 | 1583.3333 | Yes | Fictional UAT budget assumption.
4170 | Super-Structure | Sub-Con | Steelwork | 22000 | 916.6667 | Yes | Fictional UAT budget assumption.
4180 | Super-Structure | Sub-Con | Roofing | 115000 | 4791.6667 | Yes | Pending valley detail expected in full.
4190 | Super-Structure | Sub-Con | PV | 72000 | 3000 | Yes | Fictional UAT budget assumption.
4200 | Super-Structure | Sub-Con | Windows and Ext. Doors | 125000 | 5208.3333 | Yes | Approved credit expected to flow through to final cost.
4210 | Super-Structure | Sub-Con | Garage Doors | 18000 | 750 | Yes | Fictional UAT budget assumption.
4220 | Super-Structure | Sub-Con | Insulation | 38000 | 1583.3333 | Yes | Fictional UAT budget assumption.
4230 | Super-Structure | Sub-Con | Plastering & Drylining | 128000 | 5333.3333 | Yes | Current order forecast; £4k linked recovery is payment-only.
4240 | Super-Structure | Sub-Con | Plumbing & Heating | 190000 | 7916.6667 | Yes | Approved omission/credit expected to crystallise as saving.
4250 | Super-Structure | Sub-Con | Electrical | 145000 | 6041.6667 | Yes | Includes £12k customer extras + £4k payable repair origin.
4260 | Super-Structure | Sub-Con | Kitchen Fitting | 118000 | 4916.6667 | Yes | Fictional UAT budget assumption.
4270 | Super-Structure | Sub-Con | Appliances | 58000 | 2416.6667 | Yes | Fictional UAT budget assumption.
4280 | Super-Structure | Sub-Con | Stone Worktops | 28000 | 1166.6667 | Yes | Fictional UAT budget assumption.
4290 | Super-Structure | Sub-Con | Wardrobes | 0 | 0 | No | Deliberate future mispost test.
4300 | Super-Structure | Sub-Con | Carpets | 62000 | 2583.3333 | Yes | Fictional UAT budget assumption.
4310 | Super-Structure | Sub-Con | LVT | 38000 | 1583.3333 | Yes | Fictional UAT budget assumption.
4320 | Super-Structure | Sub-Con | Vinyl | 20000 | 833.3333 | Yes | Fictional UAT budget assumption.
4330 | Super-Structure | Sub-Con | Mastic & Sealing | 18000 | 750 | Yes | Fictional UAT budget assumption.
4340 | Super-Structure | Sub-Con | Painting & Decoration | 92000 | 3833.3333 | Yes | QS forecasts £7k above PO despite normal ledger/cert progress.
4350 | Super-Structure | Sub-Con | Ceramic Tiling | 48000 | 2000 | Yes | Fictional UAT budget assumption.
4360 | Super-Structure | Sub-Con | Cleaning | 30000 | 1250 | Yes | Order expected at £28k; direct recovery affects payment only.
4500 | Super-Structure | Material | Bricks | 165000 | 6875 | Yes | Brick material price/quantity overspend.
4510 | Super-Structure | Material | Brickwork Specials | 12000 | 500 | Yes | Fictional UAT budget assumption.
4520 | Super-Structure | Material | External Cladding | 0 | 0 | No
4530 | Super-Structure | Material | Batten | 0 | 0 | No
4540 | Super-Structure | Material | Membrane | 0 | 0 | No
4550 | Super-Structure | Material | Tenmat fire barrier | 0 | 0 | No
4560 | Super-Structure | Material | Blocks - Aggrtegate | 54000 | 2250 | Yes | Fictional UAT budget assumption.
4570 | Super-Structure | Material | Blocks - Airated | 42000 | 1750 | Yes | Fictional UAT budget assumption.
4580 | Super-Structure | Material | Sand Cement & Mortar | 52000 | 2166.6667 | Yes | Mortar usage running above budget.
4590 | Super-Structure | Material | Cast Stone Heads | 20000 | 833.3333 | Yes | Fictional UAT budget assumption.
4600 | Super-Structure | Material | Cast Stone Cills | 18000 | 750 | Yes | Fictional UAT budget assumption.
4610 | Super-Structure | Material | Lintels | 45000 | 1875 | Yes | Fictional UAT budget assumption.
4620 | Super-Structure | Material | Steel | 0 | 0 | No
4630 | Super-Structure | Material | Chimneys | 0 | 0 | No
4640 | Super-Structure | Material | Joists | 78000 | 3250 | Yes | Fictional UAT budget assumption.
4650 | Super-Structure | Material | Floor deck | 30000 | 1250 | Yes | Fictional UAT budget assumption.
4660 | Super-Structure | Material | Roof Timbers | 85000 | 3541.6667 | Yes | Fictional UAT budget assumption.
4670 | Super-Structure | Material | Soffit & Fascia | 35000 | 1458.3333 | Yes | Fictional UAT budget assumption.
4680 | Super-Structure | Material | Staircases | 34000 | 1416.6667 | Yes | Fictional UAT budget assumption.
4690 | Super-Structure | Material | Carcassing Timbers | 38000 | 1583.3333 | Yes | Fictional UAT budget assumption.
4700 | Super-Structure | Material | Window Board | 10000 | 416.6667 | Yes | Fictional UAT budget assumption.
4710 | Super-Structure | Material | Door Linings | 18000 | 750 | Yes | Fictional UAT budget assumption.
4720 | Super-Structure | Material | Skirting & Architrave | 28000 | 1166.6667 | Yes | Fictional UAT budget assumption.
4730 | Super-Structure | Material | Internal Doors | 42000 | 1750 | Yes | Fictional UAT budget assumption.
4740 | Super-Structure | Material | Ironmongery | 18000 | 750 | Yes | Fictional UAT budget assumption.
4750 | Super-Structure | Material | Porches | 0 | 0 | No
4760 | Super-Structure | Material | Insulation Materials | 68000 | 2833.3333 | Yes | Fictional UAT budget assumption.
4770 | Super-Structure | Material | Fixings | 12000 | 500 | Yes | Fictional UAT budget assumption.
4780 | Super-Structure | Material | Loft Traps | 0 | 0 | No
4790 | Super-Structure | Material | Meter Boxes | 9000 | 375 | Yes | Fictional UAT budget assumption.
4800 | Super-Structure | Material | Rooflight | 0 | 0 | No
4810 | Super-Structure | Material | GRP Products | 0 | 0 | No
4820 | Super-Structure | Material | General Material Sundries | 18000 | 750 | Yes | Fictional UAT budget assumption.
5100 | Abnormals | Sub-con | Demolition / Site Clearance / Remediation: | 80000 | 3333.3333 | Yes | Fictional UAT budget assumption.
5110 | Abnormals | Sub-con | Archaeology: | 0 | 0 | No
5120 | Abnormals | Sub-con | Ecology: | 18000 | 750 | Yes | Fictional UAT budget assumption.
5130 | Abnormals | Sub-con | Piling - Specialist: | 0 | 0 | No
5140 | Abnormals | Sub-con | Piling - Groundworks: | 0 | 0 | No
5150 | Abnormals | Sub-con | Abnormal Foundations: | 0 | 0 | No
5160 | Abnormals | Sub-con | Raft Foundation: | 0 | 0 | No
5170 | Abnormals | Sub-con | Attenuation Pond / Swales / Culverts: | 95000 | 3958.3333 | Yes | Fictional UAT budget assumption.
5180 | Abnormals | Utility | Electric Sub-Station: | 0 | 0 | No
5190 | Abnormals | Sub-con | Pump Station & Rising Main: | 0 | 0 | No
5200 | Abnormals | Sub-con | Retaining Features & Steps: | 65000 | 2708.3333 | Yes | Fictional UAT budget assumption.
5210 | Abnormals | Sub-con | Abnormal / Non-Plot Fencing & Walls: | 0 | 0 | No
5220 | Abnormals | LA | S278 Fees: | 0 | 0 | No
5230 | Abnormals | LA | S184 Fees: | 0 | 0 | No
5240 | Abnormals | Sub-con | Earthworks - Arisings | 55000 | 2291.6667 | Yes | Fictional UAT budget assumption.
5250 | Abnormals | Sub-con | POS / Abnormal Landscaping: | 25000 | 1041.6667 | Yes | Fictional UAT budget assumption.
5260 | Abnormals | Sub-con | S278 Works: | 75000 | 3125 | Yes | Approved £6.5k CE plus minor traffic-management allowance.
5270 | Abnormals | Utility | Offsite Utility Services Maintenance: | 0 | 0 | No
5280 | Abnormals | Utility | Offsite Utility Service Diversions: | 0 | 0 | No
5290 | Abnormals | Sub-con | Render: | 0 | 0 | No
5300 | Abnormals | Material | Black Weatherboarding: | 0 | 0 | No
5310 | Abnormals | Sub-con | Vertical Tile Hanging: | 0 | 0 | No
5320 | Abnormals | Sub-con | Stone Walling (Reconstituted / Prepped): | 0 | 0 | No
5340 | Contributions | LA | S106 | 160000 | 6666.6667 | Yes | Fictional UAT budget assumption.
5350 | Contributions | LA | CIL | 115000 | 4791.6667 | Yes | Fictional UAT budget assumption.
6100 | Sales | Revenue | Private Units | 0 | 0 | No
6110 | Sales | Consultant | Sales Legal Fees | 25000 | 1041.6667 | Yes | Fictional UAT budget assumption.
6120 | Sales | Consultant | Estate Agents | 95000 | 3958.3333 | Yes | Fictional UAT budget assumption.
6130 | Sales | Revenue | P/X Assisted Move | 0 | 0 | No
6140 | Sales | Consultant | Advertising | 42000 | 1750 | Yes | Fictional UAT budget assumption.
6150 | Sales | Material | Signs & Flags | 12000 | 500 | Yes | Fictional UAT budget assumption.
6160 | Sales | Sub-contract | Showhouse Furnishing - Showhome 1 | 35000 | 1458.3333 | Yes | Fictional UAT budget assumption.
6170 | Sales | Sub-contract | Sales Office Set-up | 18000 | 750 | Yes | Fictional UAT budget assumption.
6180 | Sales | Material | Health and Safety Equipment - Sales | 0 | 0 | No
6190 | Sales | LA | Sales Business Rates - Showhome 1 | 0 | 0 | No
6200 | Sales | Material | Sales Consumables | 8000 | 333.3333 | Yes | Fictional UAT budget assumption.
6210 | Sales | Sub-contract | Sales Running Costs - Sales Office Cleaning | 10000 | 416.6667 | Yes | Fictional UAT budget assumption.
6220 | Sales | Sub-contract | Sales Landscaping - Showhome | 12000 | 500 | Yes | Fictional UAT budget assumption.
6230 | Sales | Sub-contract | Sales Landscape Maintenance | 10000 | 416.6667 | Yes | Fictional UAT budget assumption.
6240 | Sales | Sub-contract | Sales Parking Areas - Installation | 0 | 0 | No
6250 | Sales | Sub-contract | Sales Fencing - Railings | 0 | 0 | No
6260 | Sales | Material | Home Information Packs | 4000 | 166.6667 | Yes | Fictional UAT budget assumption.
6270 | Sales | Material | Welcome Packs | 5000 | 208.3333 | Yes | Fictional UAT budget assumption.
6280 | Sales | Utility | Utility Bills Pre-Handover | 0 | 0 | No
TOTAL ORIGINAL BUDGET |  |  |  | 8065500 | 336062.5

## Package PO Plan
Package / Purchase Order Plan
PO Number | Cost Code | Trade / Element | Supplier | Order Type | Original PO (£) | Status | Budget (£) | Headroom/(Overbuy) (£) | Purpose
S-HG001 | 3100 | Sub-Con — Groundworker Prelims | J&M Civils Ltd | S | 115000 | Approved | 120000 | 5000 | Infrastructure
S-HG002 | 3500 | Sub-con — Service Trenches & Ducts | J&M Civils Ltd | S | 90000 | Approved | 95000 | 5000 | Plot services
S-HG003 | 3520 | Sub-con — Plot Drainage incl Internal Drainage | J&M Civils Ltd | S | 155000 | Approved | 165000 | 10000 | Plot drainage
S-HG004 | 4110 | Sub-Con — Scaffolding | HighReach Scaffolding Ltd | S | 78000 | Approved | 82000 | 4000 | Scaffolding
S-HG005 | 4120 | Sub-Con — Brickwork | Midlands Brickwork Ltd | S | 235000 | Approved | 245000 | 10000 | Brickwork labour
S-HG006 | 4130 | Sub-Con — Carpentry | Oakline Carpentry Ltd | S | 175000 | Approved | 180000 | 5000 | Carpentry labour
S-HG007 | 4180 | Sub-Con — Roofing | Peak Roofing Ltd | S | 110000 | Approved | 115000 | 5000 | Roofing
S-HG008 | 4200 | Sub-Con — Windows and Ext. Doors | Clearview Windows Ltd | S | 122000 | Approved | 125000 | 3000 | Windows & external doors
S-HG009 | 4230 | Sub-Con — Plastering & Drylining | SmoothFinish Drylining Ltd | S | 125000 | Approved | 128000 | 3000 | Drylining
S-HG010 | 4240 | Sub-Con — Plumbing & Heating | FlowRight Plumbing Ltd | S | 185000 | Approved | 190000 | 5000 | Plumbing & heating
S-HG011 | 4250 | Sub-Con — Electrical | Voltwise Electrical Ltd | S | 140000 | Approved | 145000 | 5000 | Electrical
S-HG012 | 4260 | Sub-Con — Kitchen Fitting | KitchenCraft Installations Ltd | S | 112000 | Approved | 118000 | 6000 | Kitchen fitting
S-HG013 | 4340 | Sub-Con — Painting & Decoration | PerfectFinish Decorating Ltd | S | 88000 | Approved | 92000 | 4000 | Painting & decorating
S-HG014 | 4350 | Sub-Con — Ceramic Tiling | TileWorks Midlands Ltd | S | 46000 | Approved | 48000 | 2000 | Ceramic tiling
S-HG015 | 4360 | Sub-Con — Cleaning | WipeRight Cleaning Ltd | S | 28000 | Approved | 30000 | 2000 | Cleaning
S-HG016 | 3590 | Sub-con — Fencing | Boundary Fencing Ltd | S | 58000 | Approved | 62000 | 4000 | Plot fencing
S-HG017 | 3640 | Sub-con — Planting | Greenleaf Landscapes Ltd | S | 40000 | Approved | 48000 | 8000 | Planting
S-HG018 | 5100 | Sub-con — Demolition / Site Clearance / Remediation: | CleanEarth Remediation Ltd | S | 76000 | Approved | 80000 | 4000 | Remediation
S-HG019 | 5260 | Sub-con — S278 Works: | J&M Civils Ltd | S | 70000 | Approved | 75000 | 5000 | S278 works
M-HG001 | 4500 | Material — Bricks | Midlands Brick Supplies | M | 158000 | Approved | 165000 | 7000 | Bricks
M-HG002 | 4560 | Material — Blocks - Aggrtegate | BlockCo Ltd | M | 52000 | Approved | 54000 | 2000 | Aggregate blocks
M-HG003 | 4570 | Material — Blocks - Airated | AirBlock Ltd | M | 40000 | Approved | 42000 | 2000 | Aerated blocks
M-HG004 | 4580 | Material — Sand Cement & Mortar | MortarMix Ltd | M | 50000 | Approved | 52000 | 2000 | Mortar
M-HG005 | 4660 | Material — Roof Timbers | TimberFrame Merchants | M | 82000 | Approved | 85000 | 3000 | Roof timbers
M-HG006 | 4730 | Material — Internal Doors | DoorSet UK | M | 40000 | Approved | 42000 | 2000 | Internal doors
M-HG007 | 4270 | Sub-Con — Appliances | Home Appliance Supply | M | 55000 | Approved | 58000 | 3000 | Appliances

## Commercial Events
Commercial Events — Designed UAT Scenarios
Event No. | Cost Code | Supplier | Event Type | Description | Value (£) | Status | Financial Treatment | Relationship Type | Linked Event | CCV Impact (£) | UAT Purpose
CE-HG001 | 3100 | J&M Civils Ltd | variation | Unexpected soft spots and stone replacement | 35000 | approved | contractAmendment |  |  | 35000 | Groundworks approved overspend
CE-HG002 | 3100 | J&M Civils Ltd | variation | Additional muck-away risk | 20000 | submitted | contractAmendment |  |  | 0 | Pending risk
CE-HG003 | 4120 | Midlands Brickwork Ltd | variation | Additional masonry detailing | 5000 | approved | contractAmendment |  |  | 5000 | Small approved uplift
CE-HG004 | 4250 | Voltwise Electrical Ltd | salesUpgrade | Customer electrical upgrades | 12000 | approved | contractAmendment |  |  | 12000 | Payable customer extras
CE-HG005 | 4250 | Voltwise Electrical Ltd | variation | Repair dryliner damage | 4000 | approved | contractAmendment | origin | CE-HG006 | 4000 | Payable origin
CE-HG006 | 4230 | SmoothFinish Drylining Ltd | contraCharge | Repair dryliner damage | -4000 | approved | recoverableDeduction | recovery | CE-HG005 | 0 | Linked recovery; payment-only
CE-HG007 | 4240 | FlowRight Plumbing Ltd | credit | Omitted secondary towel radiators | -6000 | approved | contractAmendment |  |  | -6000 | Approved credit
CE-HG008 | 4200 | Clearview Windows Ltd | credit | Revised patio-door specification | -3000 | approved | contractAmendment |  |  | -3000 | Approved credit
CE-HG009 | 4180 | Peak Roofing Ltd | variation | Revised valley detail | 8000 | submitted | contractAmendment |  |  | 0 | Pending variation
CE-HG010 | 4360 | WipeRight Cleaning Ltd | contraCharge | Damage to finished flooring | -1500 | approved | recoverableDeduction | recovery |  | 0 | Direct recovery
CE-HG011 | 4340 | PerfectFinish Decorating Ltd | variation | Additional colour changes | 2000 | draft | contractAmendment |  |  | 0 | Draft variation
CE-HG012 | 5260 | J&M Civils Ltd | variation | Additional traffic-management phase | 6500 | approved | contractAmendment |  |  | 6500 | Approved S278 uplift

## Certificates
Payment Certificate History
PO Number | Certificate No. | Status | Gross Works (£) | Retention (£) | Recovery Deduction (£) | Net Payment (£) | Certificate Date | Notes | Source
S-HG001 | 1 | Locked | 45000 | 2250 | 0 | 42750 | 2026-06-30 |  | Fictional UAT certificate history
S-HG001 | 2 | Locked | 52000 | 2600 | 0 | 49400 | 2026-08-31 |  | Fictional UAT certificate history
S-HG004 | 1 | Locked | 24000 | 1200 | 0 | 22800 | 2026-07-31 |  | Fictional UAT certificate history
S-HG005 | 1 | Locked | 28500 | 1425 | 0 | 27075 | 2026-04-30 |  | Fictional UAT certificate history
S-HG005 | 2 | Locked | 34000 | 1700 | 0 | 32300 | 2026-05-31 |  | Fictional UAT certificate history
S-HG005 | 3 | Locked | 31500 | 1575 | 0 | 29925 | 2026-06-30 |  | Fictional UAT certificate history
S-HG005 | 4 | Locked | 18000 | 900 | 0 | 17100 | 2026-07-31 |  | Fictional UAT certificate history
S-HG006 | 1 | Locked | 42000 | 2100 | 0 | 39900 | 2026-07-31 |  | Fictional UAT certificate history
S-HG006 | 2 | Locked | 35000 | 1750 | 0 | 33250 | 2026-09-30 |  | Fictional UAT certificate history
S-HG007 | 1 | Locked | 30000 | 1500 | 0 | 28500 | 2026-09-30 |  | Fictional UAT certificate history
S-HG008 | 1 | Locked | 36000 | 1800 | 0 | 34200 | 2026-09-30 |  | Fictional UAT certificate history
S-HG009 | 1 | Locked | 32000 | 1600 | 0 | 30400 | 2026-08-31 |  | Fictional UAT certificate history
S-HG009 | 2 | Locked | 28000 | 1400 | -1500 | 25100 | 2026-10-31 | Partial linked recovery deduction — payment-only. | Fictional UAT certificate history
S-HG010 | 1 | Locked | 48000 | 2400 | 0 | 45600 | 2026-08-31 |  | Fictional UAT certificate history
S-HG010 | 2 | Locked | 39000 | 1950 | 0 | 37050 | 2026-10-31 |  | Fictional UAT certificate history
S-HG011 | 1 | Locked | 34000 | 1700 | 0 | 32300 | 2026-07-31 |  | Fictional UAT certificate history
S-HG011 | 2 | Locked | 26000 | 1300 | 0 | 24700 | 2026-09-30 |  | Fictional UAT certificate history
S-HG012 | 1 | Locked | 30000 | 1500 | 0 | 28500 | 2026-09-30 |  | Fictional UAT certificate history
S-HG013 | 1 | Locked | 28000 | 1400 | 0 | 26600 | 2026-08-31 |  | Fictional UAT certificate history
S-HG014 | 1 | Locked | 18000 | 900 | 0 | 17100 | 2026-09-30 |  | Fictional UAT certificate history
S-HG018 | 1 | Locked | 56000 | 2800 | 0 | 53200 | 2026-06-30 |  | Fictional UAT certificate history

## Ledger
Cost Ledger — Fictional Accounting Transactions
Posting Date | Cost Code | Sub-Heading | Element | Supplier | Reference | Description | Debit (£) | UAT Flag
2026-04-30 | 1100 | Land | Land Cost | Vendor | HG-1100-01 | Land Cost - ledger posting 1 | 371250
2026-05-31 | 1100 | Land | Land Cost | Vendor | HG-1100-02 | Land Cost - ledger posting 2 | 396000
2026-07-01 | 1100 | Land | Land Cost | Vendor | HG-1100-03 | Land Cost - ledger posting 3 | 420750
2026-08-01 | 1100 | Land | Land Cost | Vendor | HG-1100-04 | Land Cost - ledger posting 4 | 462000
2026-04-30 | 1120 | Land | Stamp Duty - Incl VAT if applicable | GOV | HG-1120-01 | Stamp Duty - Incl VAT if applicable - ledger posting 1 | 25500
2026-05-31 | 1120 | Land | Stamp Duty - Incl VAT if applicable | GOV | HG-1120-02 | Stamp Duty - Incl VAT if applicable - ledger posting 2 | 27200
2026-07-01 | 1120 | Land | Stamp Duty - Incl VAT if applicable | GOV | HG-1120-03 | Stamp Duty - Incl VAT if applicable - ledger posting 3 | 32300
2026-04-30 | 1130 | Land | Legal Fees - Solicitor | Consultant | HG-1130-01 | Legal Fees - Solicitor - ledger posting 1 | 9900
2026-05-31 | 1130 | Land | Legal Fees - Solicitor | Consultant | HG-1130-02 | Legal Fees - Solicitor - ledger posting 2 | 12100
2026-04-30 | 1170 | Fees | Planning Application & Supporting Fees | Consultant | HG-1170-01 | Planning Application & Supporting Fees - ledger posting 1 | 15750
2026-05-31 | 1170 | Fees | Planning Application & Supporting Fees | Consultant | HG-1170-02 | Planning Application & Supporting Fees - ledger posting 2 | 19250
2026-04-30 | 1180 | Fees | Site Investigation | Consultant | HG-1180-01 | Site Investigation - ledger posting 1 | 11250
2026-05-31 | 1180 | Fees | Site Investigation | Consultant | HG-1180-02 | Site Investigation - ledger posting 2 | 13750
2026-04-30 | 1190 | Fees | Archaeology | Consultant | HG-1190-01 | Archaeology - ledger posting 1 | 6750
2026-05-31 | 1190 | Fees | Archaeology | Consultant | HG-1190-02 | Archaeology - ledger posting 2 | 8250
2026-04-30 | 1210 | Fees | Design Fees | Consultant | HG-1210-01 | Design Fees - ledger posting 1 | 12600
2026-05-31 | 1210 | Fees | Design Fees | Consultant | HG-1210-02 | Design Fees - ledger posting 2 | 15400
2026-04-30 | 1220 | Fees | Architects - Post Planning | Consultant | HG-1220-01 | Architects - Post Planning - ledger posting 1 | 11250
2026-05-31 | 1220 | Fees | Architects - Post Planning | Consultant | HG-1220-02 | Architects - Post Planning - ledger posting 2 | 13750
2026-04-30 | 1230 | Fees | Engineers | Consultant | HG-1230-01 | Engineers - ledger posting 1 | 18900
2026-05-31 | 1230 | Fees | Engineers | Consultant | HG-1230-02 | Engineers - ledger posting 2 | 23100
2026-04-30 | 1280 | Fees | Highways Consultants | Consultant | HG-1280-01 | Highways Consultants - ledger posting 1 | 8000
2026-04-30 | 1290 | Fees | Environmental Consultants | Consultant | HG-1290-01 | Environmental Consultants - ledger posting 1 | 6000
2026-04-30 | 1380 | Fees | NHBC - Warranty & Build control | Consultant | HG-1380-01 | NHBC - Warranty & Build control - ledger posting 1 | 11700
2026-05-31 | 1380 | Fees | NHBC - Warranty & Build control | Consultant | HG-1380-02 | NHBC - Warranty & Build control - ledger posting 2 | 14300
2026-04-30 | 2100 | Prelims | Site Manager | Direct | HG-2100-01 | Site Manager - ledger posting 1 | 18900
2026-05-31 | 2100 | Prelims | Site Manager | Direct | HG-2100-02 | Site Manager - ledger posting 2 | 23100
2026-04-30 | 2101 | Prelims | Assistant Site Manager | Direct | HG-2101-01 | Assistant Site Manager - ledger posting 1 | 10800
2026-05-31 | 2101 | Prelims | Assistant Site Manager | Direct | HG-2101-02 | Assistant Site Manager - ledger posting 2 | 13200
2026-04-30 | 2151 | Prelims | Forklift Driver - Agency | Agency | HG-2151-01 | Forklift Driver - Agency - ledger posting 1 | 12000
2026-04-30 | 2161 | Prelims | Labourer - Agency | Agency | HG-2161-01 | Labourer - Agency - ledger posting 1 | 10000
2026-04-30 | 2190 | Prelims | Forklift Truck | Plant Hire | HG-2190-01 | Forklift Truck - ledger posting 1 | 14000
2026-04-30 | 2200 | Prelims | Site Office | Plant Hire | HG-2200-01 | Site Office - ledger posting 1 | 10000
2026-04-30 | 2211 | Prelims | Fuel | Material | HG-2211-01 | Fuel - ledger posting 1 | 9000
2026-04-30 | 2230 | Prelims | Site Electric Usage | Utility | HG-2230-01 | Site Electric Usage - ledger posting 1 | 7000
2026-04-30 | 2231 | Prelims | Site Water Usage | Utility | HG-2231-01 | Site Water Usage - ledger posting 1 | 2500
2026-04-30 | 2280 | Prelims | Skips | Plant Hire | HG-2280-01 | Skips - ledger posting 1 | 4000
2026-04-30 | 2330 | Prelims | Security - Cameras | Plant Hire | HG-2330-01 | Security - Cameras - ledger posting 1 | 5000
2026-04-30 | 3100 | R&S | Groundworker Prelims | Sub-Con | HG-3100-01 | Groundworker Prelims - ledger posting 1 | 25200
2026-05-31 | 3100 | R&S | Groundworker Prelims | Sub-Con | HG-3100-02 | Groundworker Prelims - ledger posting 2 | 26880
2026-07-01 | 3100 | R&S | Groundworker Prelims | Sub-Con | HG-3100-03 | Groundworker Prelims - ledger posting 3 | 28560
2026-08-01 | 3100 | R&S | Groundworker Prelims | Sub-Con | HG-3100-04 | Groundworker Prelims - ledger posting 4 | 31360
2026-04-30 | 3110 | R&S | Duct Crossings | Sub-Con | HG-3110-01 | Duct Crossings - ledger posting 1 | 8100
2026-05-31 | 3110 | R&S | Duct Crossings | Sub-Con | HG-3110-02 | Duct Crossings - ledger posting 2 | 9900
2026-04-30 | 3120 | R&S | Footpaths to Base | Sub-Con | HG-3120-01 | Footpaths to Base - ledger posting 1 | 8100
2026-05-31 | 3120 | R&S | Footpaths to Base | Sub-Con | HG-3120-02 | Footpaths to Base - ledger posting 2 | 9900
2026-04-30 | 3170 | R&S | Electricity Mains - Mains & Connections | Sub-Con | HG-3170-01 | Electricity Mains - Mains & Connections - ledger posting 1 | 9900
2026-05-31 | 3170 | R&S | Electricity Mains - Mains & Connections | Sub-Con | HG-3170-02 | Electricity Mains - Mains & Connections - ledger posting 2 | 12100
2026-04-30 | 3190 | R&S | Water Mains - Laying & Connection | Sub-Con | HG-3190-01 | Water Mains - Laying & Connection - ledger posting 1 | 14000
2026-04-30 | 3500 | Plot | Service Trenches & Ducts | Sub-con | HG-3500-01 | Service Trenches & Ducts - ledger posting 1 | 15600
2026-05-31 | 3500 | Plot | Service Trenches & Ducts | Sub-con | HG-3500-02 | Service Trenches & Ducts - ledger posting 2 | 16640
2026-07-01 | 3500 | Plot | Service Trenches & Ducts | Sub-con | HG-3500-03 | Service Trenches & Ducts - ledger posting 3 | 19760
2026-04-30 | 3510 | Plot | Muck Away | Sub-con | HG-3510-01 | Muck Away - ledger posting 1 | 19800
2026-05-31 | 3510 | Plot | Muck Away | Sub-con | HG-3510-02 | Muck Away - ledger posting 2 | 24200
2026-04-30 | 3520 | Plot | Plot Drainage incl Internal Drainage | Sub-con | HG-3520-01 | Plot Drainage incl Internal Drainage - ledger posting 1 | 28800
2026-05-31 | 3520 | Plot | Plot Drainage incl Internal Drainage | Sub-con | HG-3520-02 | Plot Drainage incl Internal Drainage - ledger posting 2 | 30720
2026-07-01 | 3520 | Plot | Plot Drainage incl Internal Drainage | Sub-con | HG-3520-03 | Plot Drainage incl Internal Drainage - ledger posting 3 | 36480
2026-04-30 | 3540 | Plot | Private Drive Formation | Sub-con | HG-3540-01 | Private Drive Formation - ledger posting 1 | 10800
2026-05-31 | 3540 | Plot | Private Drive Formation | Sub-con | HG-3540-02 | Private Drive Formation - ledger posting 2 | 13200
2026-04-30 | 3590 | Plot | Fencing | Sub-con | HG-3590-01 | Fencing - ledger posting 1 | 6750
2026-05-31 | 3590 | Plot | Fencing | Sub-con | HG-3590-02 | Fencing - ledger posting 2 | 8250
2026-04-30 | 4110 | Super-Structure | Scaffolding | Sub-Con | HG-4110-01 | Scaffolding - ledger posting 1 | 13500
2026-05-31 | 4110 | Super-Structure | Scaffolding | Sub-Con | HG-4110-02 | Scaffolding - ledger posting 2 | 16500
2026-04-30 | 4120 | Super-Structure | Brickwork | Midlands Brickwork Ltd | HG-4120-01 | Brickwork - ledger posting 1 | 26550
2026-05-31 | 4120 | Super-Structure | Brickwork | Midlands Brickwork Ltd | HG-4120-02 | Brickwork - ledger posting 2 | 28320
2026-07-01 | 4120 | Super-Structure | Brickwork | Midlands Brickwork Ltd | HG-4120-03 | Brickwork - ledger posting 3 | 30090
2026-08-01 | 4120 | Super-Structure | Brickwork | Midlands Brickwork Ltd | HG-4120-04 | Brickwork - ledger posting 4 | 33040
2026-04-30 | 4130 | Super-Structure | Carpentry | Oakline Carpentry Ltd | HG-4130-01 | Carpentry - ledger posting 1 | 24600
2026-05-31 | 4130 | Super-Structure | Carpentry | Oakline Carpentry Ltd | HG-4130-02 | Carpentry - ledger posting 2 | 26240
2026-07-01 | 4130 | Super-Structure | Carpentry | Oakline Carpentry Ltd | HG-4130-03 | Carpentry - ledger posting 3 | 31160
2026-04-30 | 4180 | Super-Structure | Roofing | Sub-Con | HG-4180-01 | Roofing - ledger posting 1 | 18900
2026-05-31 | 4180 | Super-Structure | Roofing | Sub-Con | HG-4180-02 | Roofing - ledger posting 2 | 23100
2026-04-30 | 4200 | Super-Structure | Windows and Ext. Doors | Sub-Con | HG-4200-01 | Windows and Ext. Doors - ledger posting 1 | 20700
2026-05-31 | 4200 | Super-Structure | Windows and Ext. Doors | Sub-Con | HG-4200-02 | Windows and Ext. Doors - ledger posting 2 | 25300
2026-04-30 | 4230 | Super-Structure | Plastering & Drylining | SmoothFinish Drylining Ltd | HG-4230-01 | Plastering & Drylining - ledger posting 1 | 20400
2026-05-31 | 4230 | Super-Structure | Plastering & Drylining | SmoothFinish Drylining Ltd | HG-4230-02 | Plastering & Drylining - ledger posting 2 | 21760
2026-07-01 | 4230 | Super-Structure | Plastering & Drylining | SmoothFinish Drylining Ltd | HG-4230-03 | Plastering & Drylining - ledger posting 3 | 25840
2026-04-30 | 4240 | Super-Structure | Plumbing & Heating | FlowRight Plumbing Ltd | HG-4240-01 | Plumbing & Heating - ledger posting 1 | 27600
2026-05-31 | 4240 | Super-Structure | Plumbing & Heating | FlowRight Plumbing Ltd | HG-4240-02 | Plumbing & Heating - ledger posting 2 | 29440
2026-07-01 | 4240 | Super-Structure | Plumbing & Heating | FlowRight Plumbing Ltd | HG-4240-03 | Plumbing & Heating - ledger posting 3 | 34960
2026-04-30 | 4250 | Super-Structure | Electrical | Voltwise Electrical Ltd | HG-4250-01 | Electrical - ledger posting 1 | 21600
2026-05-31 | 4250 | Super-Structure | Electrical | Voltwise Electrical Ltd | HG-4250-02 | Electrical - ledger posting 2 | 23040
2026-07-01 | 4250 | Super-Structure | Electrical | Voltwise Electrical Ltd | HG-4250-03 | Electrical - ledger posting 3 | 27360
2026-04-30 | 4260 | Super-Structure | Kitchen Fitting | Sub-Con | HG-4260-01 | Kitchen Fitting - ledger posting 1 | 13500
2026-05-31 | 4260 | Super-Structure | Kitchen Fitting | Sub-Con | HG-4260-02 | Kitchen Fitting - ledger posting 2 | 16500
2026-04-30 | 4340 | Super-Structure | Painting & Decoration | PerfectFinish Decorating Ltd | HG-4340-01 | Painting & Decoration - ledger posting 1 | 17100
2026-05-31 | 4340 | Super-Structure | Painting & Decoration | PerfectFinish Decorating Ltd | HG-4340-02 | Painting & Decoration - ledger posting 2 | 20900
2026-04-30 | 4350 | Super-Structure | Ceramic Tiling | Sub-Con | HG-4350-01 | Ceramic Tiling - ledger posting 1 | 8100
2026-05-31 | 4350 | Super-Structure | Ceramic Tiling | Sub-Con | HG-4350-02 | Ceramic Tiling - ledger posting 2 | 9900
2026-04-30 | 4360 | Super-Structure | Cleaning | Sub-Con | HG-4360-01 | Cleaning - ledger posting 1 | 0
2026-04-30 | 4500 | Super-Structure | Bricks | Midlands Brick Supplies | HG-4500-01 | Bricks - ledger posting 1 | 23625
2026-05-31 | 4500 | Super-Structure | Bricks | Midlands Brick Supplies | HG-4500-02 | Bricks - ledger posting 2 | 25200
2026-07-01 | 4500 | Super-Structure | Bricks | Midlands Brick Supplies | HG-4500-03 | Bricks - ledger posting 3 | 26775
2026-08-01 | 4500 | Super-Structure | Bricks | Midlands Brick Supplies | HG-4500-04 | Bricks - ledger posting 4 | 29400
2026-04-30 | 4560 | Super-Structure | Blocks - Aggrtegate | Material | HG-4560-01 | Blocks - Aggrtegate - ledger posting 1 | 14850
2026-05-31 | 4560 | Super-Structure | Blocks - Aggrtegate | Material | HG-4560-02 | Blocks - Aggrtegate - ledger posting 2 | 18150
2026-04-30 | 4570 | Super-Structure | Blocks - Airated | Material | HG-4570-01 | Blocks - Airated - ledger posting 1 | 12600
2026-05-31 | 4570 | Super-Structure | Blocks - Airated | Material | HG-4570-02 | Blocks - Airated - ledger posting 2 | 15400
2026-04-30 | 4580 | Super-Structure | Sand Cement & Mortar | Material | HG-4580-01 | Sand Cement & Mortar - ledger posting 1 | 13950
2026-05-31 | 4580 | Super-Structure | Sand Cement & Mortar | Material | HG-4580-02 | Sand Cement & Mortar - ledger posting 2 | 17050
2026-04-30 | 4610 | Super-Structure | Lintels | Material | HG-4610-01 | Lintels - ledger posting 1 | 10350
2026-05-31 | 4610 | Super-Structure | Lintels | Material | HG-4610-02 | Lintels - ledger posting 2 | 12650
2026-04-30 | 4640 | Super-Structure | Joists | Material | HG-4640-01 | Joists - ledger posting 1 | 17100
2026-05-31 | 4640 | Super-Structure | Joists | Material | HG-4640-02 | Joists - ledger posting 2 | 20900
2026-04-30 | 4660 | Super-Structure | Roof Timbers | Material | HG-4660-01 | Roof Timbers - ledger posting 1 | 20700
2026-05-31 | 4660 | Super-Structure | Roof Timbers | Material | HG-4660-02 | Roof Timbers - ledger posting 2 | 25300
2026-04-30 | 4730 | Super-Structure | Internal Doors | Material | HG-4730-01 | Internal Doors - ledger posting 1 | 6750
2026-05-31 | 4730 | Super-Structure | Internal Doors | Material | HG-4730-02 | Internal Doors - ledger posting 2 | 8250
2026-04-30 | 4760 | Super-Structure | Insulation Materials | Material | HG-4760-01 | Insulation Materials - ledger posting 1 | 13050
2026-05-31 | 4760 | Super-Structure | Insulation Materials | Material | HG-4760-02 | Insulation Materials - ledger posting 2 | 15950
2026-04-30 | 5100 | Abnormals | Demolition / Site Clearance / Remediation: | CleanEarth Remediation Ltd | HG-5100-01 | Demolition / Site Clearance / Remediation: - ledger posting 1 | 22800
2026-05-31 | 5100 | Abnormals | Demolition / Site Clearance / Remediation: | CleanEarth Remediation Ltd | HG-5100-02 | Demolition / Site Clearance / Remediation: - ledger posting 2 | 24320
2026-07-01 | 5100 | Abnormals | Demolition / Site Clearance / Remediation: | CleanEarth Remediation Ltd | HG-5100-03 | Demolition / Site Clearance / Remediation: - ledger posting 3 | 28880
2026-04-30 | 5170 | Abnormals | Attenuation Pond / Swales / Culverts: | Sub-con | HG-5170-01 | Attenuation Pond / Swales / Culverts: - ledger posting 1 | 15750
2026-05-31 | 5170 | Abnormals | Attenuation Pond / Swales / Culverts: | Sub-con | HG-5170-02 | Attenuation Pond / Swales / Culverts: - ledger posting 2 | 19250
2026-04-30 | 5200 | Abnormals | Retaining Features & Steps: | Sub-con | HG-5200-01 | Retaining Features & Steps: - ledger posting 1 | 8100
2026-05-31 | 5200 | Abnormals | Retaining Features & Steps: | Sub-con | HG-5200-02 | Retaining Features & Steps: - ledger posting 2 | 9900
2026-04-30 | 5240 | Abnormals | Earthworks - Arisings | Sub-con | HG-5240-01 | Earthworks - Arisings - ledger posting 1 | 15300
2026-05-31 | 5240 | Abnormals | Earthworks - Arisings | Sub-con | HG-5240-02 | Earthworks - Arisings - ledger posting 2 | 18700
2026-04-30 | 5260 | Abnormals | S278 Works: | Sub-con | HG-5260-01 | S278 Works: - ledger posting 1 | 11250
2026-05-31 | 5260 | Abnormals | S278 Works: | Sub-con | HG-5260-02 | S278 Works: - ledger posting 2 | 13750
2026-04-30 | 5340 | Contributions | S106 | LA | HG-5340-01 | S106 - ledger posting 1 | 24000
2026-05-31 | 5340 | Contributions | S106 | LA | HG-5340-02 | S106 - ledger posting 2 | 25600
2026-07-01 | 5340 | Contributions | S106 | LA | HG-5340-03 | S106 - ledger posting 3 | 30400
2026-04-30 | 5350 | Contributions | CIL | LA | HG-5350-01 | CIL - ledger posting 1 | 17250
2026-05-31 | 5350 | Contributions | CIL | LA | HG-5350-02 | CIL - ledger posting 2 | 18400
2026-07-01 | 5350 | Contributions | CIL | LA | HG-5350-03 | CIL - ledger posting 3 | 21850
2026-04-30 | 4290 | Super-Structure | Wardrobes | Furniture supplier (mispost) | HG-4290-01 | Wardrobes - ledger posting 1 | 8500 | DELIBERATE WRONG-CODE POSTING
2026-04-30 | 6140 | Sales | Advertising | Consultant | HG-6140-01 | Advertising - ledger posting 1 | 10000
2026-04-30 | 6160 | Sales | Showhouse Furnishing - Showhome 1 | Sub-contract | HG-6160-01 | Showhouse Furnishing - Showhome 1 - ledger posting 1 | 8100
2026-05-31 | 6160 | Sales | Showhouse Furnishing - Showhome 1 | Sub-contract | HG-6160-02 | Showhouse Furnishing - Showhome 1 - ledger posting 2 | 9900

## Forecast Adjustments
QS Forecast — Known-Answer Inputs
Cost Code | Element | Original Budget (£) | Current Commitment (£) | Ledger Actual (£) | Expected FFC (£) | Variance to Budget (£) | QS Rationale
1100 | Land Cost | 1650000 | 0 | 1650000 | 1650000 | 0 | Forecast at strongest current commercial baseline unless noted.
1120 | Stamp Duty - Incl VAT if applicable | 85000 | 0 | 85000 | 85000 | 0 | Forecast at strongest current commercial baseline unless noted.
1130 | Legal Fees - Solicitor | 25000 | 0 | 22000 | 25000 | 0 | Forecast at strongest current commercial baseline unless noted.
1170 | Planning Application & Supporting Fees | 35000 | 0 | 35000 | 35000 | 0 | Forecast at strongest current commercial baseline unless noted.
1180 | Site Investigation | 25000 | 0 | 25000 | 25000 | 0 | Forecast at strongest current commercial baseline unless noted.
1190 | Archaeology | 15000 | 0 | 15000 | 15000 | 0 | Forecast at strongest current commercial baseline unless noted.
1200 | Contamination | 20000 | 0 | 0 | 20000 | 0 | Forecast at strongest current commercial baseline unless noted.
1210 | Design Fees | 40000 | 0 | 28000 | 40000 | 0 | Forecast at strongest current commercial baseline unless noted.
1220 | Architects - Post Planning | 55000 | 0 | 25000 | 55000 | 0 | Forecast at strongest current commercial baseline unless noted.
1230 | Engineers | 75000 | 0 | 42000 | 75000 | 0 | Forecast at strongest current commercial baseline unless noted.
1240 | Surveys | 20000 | 0 | 0 | 20000 | 0 | Forecast at strongest current commercial baseline unless noted.
1250 | NHBC Bond Fees | 25000 | 0 | 0 | 25000 | 0 | Forecast at strongest current commercial baseline unless noted.
1260 | Insurance | 15000 | 0 | 0 | 15000 | 0 | Forecast at strongest current commercial baseline unless noted.
1280 | Highways Consultants | 20000 | 0 | 8000 | 20000 | 0 | Forecast at strongest current commercial baseline unless noted.
1290 | Environmental Consultants | 15000 | 0 | 6000 | 15000 | 0 | Forecast at strongest current commercial baseline unless noted.
1300 | M&E Consultants | 10000 | 0 | 0 | 10000 | 0 | Forecast at strongest current commercial baseline unless noted.
1310 | Sewers Adoption (s104): | 18000 | 0 | 0 | 18000 | 0 | Forecast at strongest current commercial baseline unless noted.
1320 | Highways Adoption (s18/38): | 22000 | 0 | 0 | 22000 | 0 | Forecast at strongest current commercial baseline unless noted.
1330 | S278 Fees | 12000 | 0 | 0 | 12000 | 0 | Forecast at strongest current commercial baseline unless noted.
1340 | Building Regulation Fees | 22000 | 0 | 0 | 22000 | 0 | Forecast at strongest current commercial baseline unless noted.
1360 | SAP Calculations | 10000 | 0 | 0 | 10000 | 0 | Forecast at strongest current commercial baseline unless noted.
1370 | Air Tests | 7500 | 0 | 0 | 7500 | 0 | Forecast at strongest current commercial baseline unless noted.
1380 | NHBC - Warranty & Build control | 48000 | 0 | 26000 | 48000 | 0 | Forecast at strongest current commercial baseline unless noted.
1410 | Other Fees | 12500 | 0 | 0 | 12500 | 0 | Forecast at strongest current commercial baseline unless noted.
2100 | Site Manager | 95000 | 0 | 42000 | 95000 | 0 | Forecast at strongest current commercial baseline unless noted.
2101 | Assistant Site Manager | 55000 | 0 | 24000 | 55000 | 0 | Forecast at strongest current commercial baseline unless noted.
2110 | Direct Staff Bonuses | 12000 | 0 | 0 | 12000 | 0 | Forecast at strongest current commercial baseline unless noted.
2130 | NIC on Salary | 18000 | 0 | 0 | 18000 | 0 | Forecast at strongest current commercial baseline unless noted.
2140 | Pension | 9000 | 0 | 0 | 9000 | 0 | Forecast at strongest current commercial baseline unless noted.
2151 | Forklift Driver - Agency | 36000 | 0 | 12000 | 36000 | 0 | Forecast at strongest current commercial baseline unless noted.
2161 | Labourer - Agency | 30000 | 0 | 10000 | 30000 | 0 | Forecast at strongest current commercial baseline unless noted.
2180 | Principle Contractor Set-Up | 20000 | 0 | 0 | 20000 | 0 | Forecast at strongest current commercial baseline unless noted.
2190 | Forklift Truck | 34000 | 0 | 14000 | 34000 | 0 | Forecast at strongest current commercial baseline unless noted.
2200 | Site Office | 28000 | 0 | 10000 | 28000 | 0 | Forecast at strongest current commercial baseline unless noted.
2201 | Site Cabins | 18000 | 0 | 0 | 18000 | 0 | Forecast at strongest current commercial baseline unless noted.
2202 | Containers | 10000 | 0 | 0 | 10000 | 0 | Forecast at strongest current commercial baseline unless noted.
2211 | Fuel | 22000 | 0 | 9000 | 22000 | 0 | Forecast at strongest current commercial baseline unless noted.
2230 | Site Electric Usage | 18000 | 0 | 7000 | 18000 | 0 | Forecast at strongest current commercial baseline unless noted.
2231 | Site Water Usage | 7500 | 0 | 2500 | 7500 | 0 | Forecast at strongest current commercial baseline unless noted.
2250 | Road Cleaning - F Lift Road brush | 8000 | 0 | 0 | 8000 | 0 | Forecast at strongest current commercial baseline unless noted.
2260 | Road Cleaning - Road sweep | 15000 | 0 | 0 | 15000 | 0 | Forecast at strongest current commercial baseline unless noted.
2280 | Skips | 12000 | 0 | 4000 | 12000 | 0 | Forecast at strongest current commercial baseline unless noted.
2311 | Site consumables | 10000 | 0 | 0 | 10000 | 0 | Forecast at strongest current commercial baseline unless noted.
2321 | Heras Fencing | 14000 | 0 | 0 | 14000 | 0 | Forecast at strongest current commercial baseline unless noted.
2330 | Security - Cameras | 15000 | 0 | 5000 | 15000 | 0 | Forecast at strongest current commercial baseline unless noted.
2350 | Contingency | 30000 | 0 | 0 | 20000 | 10000 | Only £20k of £30k contingency expected to be used.
3100 | Groundworker Prelims | 120000 | 150000 | 112000 | 155000 | -35000 | Soft-ground approved CE plus unresolved muck-away risk.
3110 | Duct Crossings | 35000 | 0 | 18000 | 35000 | 0 | Forecast at strongest current commercial baseline unless noted.
3120 | Footpaths to Base | 55000 | 0 | 18000 | 55000 | 0 | Forecast at strongest current commercial baseline unless noted.
3160 | R&S - REMEDIALS: | 20000 | 0 | 0 | 20000 | 0 | Forecast at strongest current commercial baseline unless noted.
3170 | Electricity Mains - Mains & Connections | 55000 | 0 | 22000 | 55000 | 0 | Forecast at strongest current commercial baseline unless noted.
3190 | Water Mains - Laying & Connection | 35000 | 0 | 14000 | 35000 | 0 | Forecast at strongest current commercial baseline unless noted.
3200 | Telephone Mains | 15000 | 0 | 0 | 15000 | 0 | Forecast at strongest current commercial baseline unless noted.
3210 | Fibre | 15000 | 0 | 0 | 15000 | 0 | Forecast at strongest current commercial baseline unless noted.
3220 | Street Lights - Supply & Install Columns | 36000 | 0 | 0 | 36000 | 0 | Forecast at strongest current commercial baseline unless noted.
3230 | Street Lighting Connections | 9000 | 0 | 0 | 9000 | 0 | Forecast at strongest current commercial baseline unless noted.
3240 | Public Open Space & Play Areas | 45000 | 0 | 0 | 45000 | 0 | Forecast at strongest current commercial baseline unless noted.
3260 | Hard Landscaping | 35000 | 0 | 0 | 35000 | 0 | Forecast at strongest current commercial baseline unless noted.
3270 | Roads & Sewers Contingency | 25000 | 0 | 0 | 25000 | 0 | Forecast at strongest current commercial baseline unless noted.
3500 | Service Trenches & Ducts | 95000 | 90000 | 52000 | 95000 | 0 | Forecast at strongest current commercial baseline unless noted.
3510 | Muck Away | 65000 | 0 | 44000 | 65000 | 0 | Forecast at strongest current commercial baseline unless noted.
3520 | Plot Drainage incl Internal Drainage | 165000 | 155000 | 96000 | 165000 | 0 | Forecast at strongest current commercial baseline unless noted.
3530 | Paths - Slabs | 42000 | 0 | 0 | 42000 | 0 | Forecast at strongest current commercial baseline unless noted.
3540 | Private Drive Formation | 70000 | 0 | 24000 | 70000 | 0 | Forecast at strongest current commercial baseline unless noted.
3541 | Private Drives Complete | 62000 | 0 | 0 | 62000 | 0 | Forecast at strongest current commercial baseline unless noted.
3550 | Shared Drive Formation | 25000 | 0 | 0 | 25000 | 0 | Forecast at strongest current commercial baseline unless noted.
3551 | Shared Drive Complete | 22000 | 0 | 0 | 22000 | 0 | Forecast at strongest current commercial baseline unless noted.
3570 | Screen Walls - Foundations | 28000 | 0 | 0 | 28000 | 0 | Forecast at strongest current commercial baseline unless noted.
3580 | Screen Walls - Superstructure | 45000 | 0 | 0 | 45000 | 0 | Forecast at strongest current commercial baseline unless noted.
3590 | Fencing | 62000 | 58000 | 15000 | 62000 | 0 | Forecast at strongest current commercial baseline unless noted.
3600 | Plot Clearance | 24000 | 0 | 0 | 24000 | 0 | Forecast at strongest current commercial baseline unless noted.
3610 | Plot Regrade | 30000 | 0 | 0 | 30000 | 0 | Forecast at strongest current commercial baseline unless noted.
3620 | Topsoil placement | 32000 | 0 | 0 | 32000 | 0 | Forecast at strongest current commercial baseline unless noted.
3640 | Planting | 48000 | 40000 | 0 | 48000 | 0 | Forecast at strongest current commercial baseline unless noted.
3650 | Misc. Landscaping | 18000 | 0 | 0 | 18000 | 0 | Forecast at strongest current commercial baseline unless noted.
3680 | Contingency - Plot Groundworks | 22000 | 0 | 0 | 22000 | 0 | Forecast at strongest current commercial baseline unless noted.
4100 | Pre-Cast Concrete | 35000 | 0 | 0 | 35000 | 0 | Forecast at strongest current commercial baseline unless noted.
4110 | Scaffolding | 82000 | 78000 | 30000 | 82000 | 0 | Forecast at strongest current commercial baseline unless noted.
4120 | Brickwork | 245000 | 240000 | 118000 | 255000 | -10000 | Productivity loss pushes final cost above budget/commitment.
4130 | Carpentry | 180000 | 175000 | 82000 | 175000 | 5000 | Control package: forecast at current PO, delivering £5k saving.
4140 | Contract Crane Hire | 24000 | 0 | 0 | 24000 | 0 | Forecast at strongest current commercial baseline unless noted.
4150 | Cladding | 48000 | 0 | 0 | 48000 | 0 | Forecast at strongest current commercial baseline unless noted.
4160 | Render | 38000 | 0 | 0 | 38000 | 0 | Forecast at strongest current commercial baseline unless noted.
4170 | Steelwork | 22000 | 0 | 0 | 22000 | 0 | Forecast at strongest current commercial baseline unless noted.
4180 | Roofing | 115000 | 110000 | 42000 | 118000 | -3000 | Pending valley detail expected in full.
4190 | PV | 72000 | 0 | 0 | 72000 | 0 | Forecast at strongest current commercial baseline unless noted.
4200 | Windows and Ext. Doors | 125000 | 119000 | 46000 | 119000 | 6000 | Approved credit expected to flow through to final cost.
4210 | Garage Doors | 18000 | 0 | 0 | 18000 | 0 | Forecast at strongest current commercial baseline unless noted.
4220 | Insulation | 38000 | 0 | 0 | 38000 | 0 | Forecast at strongest current commercial baseline unless noted.
4230 | Plastering & Drylining | 128000 | 125000 | 68000 | 125000 | 3000 | Current order forecast; £4k linked recovery is payment-only.
4240 | Plumbing & Heating | 190000 | 179000 | 92000 | 179000 | 11000 | Approved omission/credit expected to crystallise as saving.
4250 | Electrical | 145000 | 156000 | 72000 | 156000 | -11000 | Includes £12k customer extras + £4k payable repair origin.
4260 | Kitchen Fitting | 118000 | 112000 | 30000 | 118000 | 0 | Forecast at strongest current commercial baseline unless noted.
4270 | Appliances | 58000 | 55000 | 0 | 58000 | 0 | Forecast at strongest current commercial baseline unless noted.
4280 | Stone Worktops | 28000 | 0 | 0 | 28000 | 0 | Forecast at strongest current commercial baseline unless noted.
4290 | Wardrobes | 0 | 0 | 8500 | 8500 | -8500 | Deliberate wrong-code ledger posting with no budget.
4300 | Carpets | 62000 | 0 | 0 | 62000 | 0 | Forecast at strongest current commercial baseline unless noted.
4310 | LVT | 38000 | 0 | 0 | 38000 | 0 | Forecast at strongest current commercial baseline unless noted.
4320 | Vinyl | 20000 | 0 | 0 | 20000 | 0 | Forecast at strongest current commercial baseline unless noted.
4330 | Mastic & Sealing | 18000 | 0 | 0 | 18000 | 0 | Forecast at strongest current commercial baseline unless noted.
4340 | Painting & Decoration | 92000 | 88000 | 38000 | 95000 | -3000 | QS forecasts £7k above PO despite normal ledger/cert progress.
4350 | Ceramic Tiling | 48000 | 46000 | 18000 | 48000 | 0 | Forecast at strongest current commercial baseline unless noted.
4360 | Cleaning | 30000 | 28000 | 0 | 28000 | 2000 | Order expected at £28k; direct recovery affects payment only.
4500 | Bricks | 165000 | 158000 | 105000 | 172000 | -7000 | Brick material price/quantity overspend.
4510 | Brickwork Specials | 12000 | 0 | 0 | 12000 | 0 | Forecast at strongest current commercial baseline unless noted.
4560 | Blocks - Aggrtegate | 54000 | 52000 | 33000 | 54000 | 0 | Forecast at strongest current commercial baseline unless noted.
4570 | Blocks - Airated | 42000 | 40000 | 28000 | 42000 | 0 | Forecast at strongest current commercial baseline unless noted.
4580 | Sand Cement & Mortar | 52000 | 50000 | 31000 | 56000 | -4000 | Mortar usage running above budget.
4590 | Cast Stone Heads | 20000 | 0 | 0 | 20000 | 0 | Forecast at strongest current commercial baseline unless noted.
4600 | Cast Stone Cills | 18000 | 0 | 0 | 18000 | 0 | Forecast at strongest current commercial baseline unless noted.
4610 | Lintels | 45000 | 0 | 23000 | 45000 | 0 | Forecast at strongest current commercial baseline unless noted.
4640 | Joists | 78000 | 0 | 38000 | 78000 | 0 | Forecast at strongest current commercial baseline unless noted.
4650 | Floor deck | 30000 | 0 | 0 | 30000 | 0 | Forecast at strongest current commercial baseline unless noted.
4660 | Roof Timbers | 85000 | 82000 | 46000 | 85000 | 0 | Forecast at strongest current commercial baseline unless noted.
4670 | Soffit & Fascia | 35000 | 0 | 0 | 35000 | 0 | Forecast at strongest current commercial baseline unless noted.
4680 | Staircases | 34000 | 0 | 0 | 34000 | 0 | Forecast at strongest current commercial baseline unless noted.
4690 | Carcassing Timbers | 38000 | 0 | 0 | 38000 | 0 | Forecast at strongest current commercial baseline unless noted.
4700 | Window Board | 10000 | 0 | 0 | 10000 | 0 | Forecast at strongest current commercial baseline unless noted.
4710 | Door Linings | 18000 | 0 | 0 | 18000 | 0 | Forecast at strongest current commercial baseline unless noted.
4720 | Skirting & Architrave | 28000 | 0 | 0 | 28000 | 0 | Forecast at strongest current commercial baseline unless noted.
4730 | Internal Doors | 42000 | 40000 | 15000 | 42000 | 0 | Forecast at strongest current commercial baseline unless noted.
4740 | Ironmongery | 18000 | 0 | 0 | 18000 | 0 | Forecast at strongest current commercial baseline unless noted.
4760 | Insulation Materials | 68000 | 0 | 29000 | 68000 | 0 | Forecast at strongest current commercial baseline unless noted.
4770 | Fixings | 12000 | 0 | 0 | 12000 | 0 | Forecast at strongest current commercial baseline unless noted.
4790 | Meter Boxes | 9000 | 0 | 0 | 9000 | 0 | Forecast at strongest current commercial baseline unless noted.
4820 | General Material Sundries | 18000 | 0 | 0 | 18000 | 0 | Forecast at strongest current commercial baseline unless noted.
5100 | Demolition / Site Clearance / Remediation: | 80000 | 76000 | 76000 | 80000 | 0 | Forecast at strongest current commercial baseline unless noted.
5120 | Ecology: | 18000 | 0 | 0 | 18000 | 0 | Forecast at strongest current commercial baseline unless noted.
5170 | Attenuation Pond / Swales / Culverts: | 95000 | 0 | 35000 | 95000 | 0 | Forecast at strongest current commercial baseline unless noted.
5200 | Retaining Features & Steps: | 65000 | 0 | 18000 | 65000 | 0 | Forecast at strongest current commercial baseline unless noted.
5240 | Earthworks - Arisings | 55000 | 0 | 34000 | 55000 | 0 | Forecast at strongest current commercial baseline unless noted.
5250 | POS / Abnormal Landscaping: | 25000 | 0 | 0 | 25000 | 0 | Forecast at strongest current commercial baseline unless noted.
5260 | S278 Works: | 75000 | 76500 | 25000 | 80000 | -5000 | Approved £6.5k CE plus minor traffic-management allowance.
5340 | S106 | 160000 | 0 | 80000 | 160000 | 0 | Forecast at strongest current commercial baseline unless noted.
5350 | CIL | 115000 | 0 | 57500 | 115000 | 0 | Forecast at strongest current commercial baseline unless noted.
6110 | Sales Legal Fees | 25000 | 0 | 0 | 25000 | 0 | Forecast at strongest current commercial baseline unless noted.
6120 | Estate Agents | 95000 | 0 | 0 | 95000 | 0 | Forecast at strongest current commercial baseline unless noted.
6140 | Advertising | 42000 | 0 | 10000 | 42000 | 0 | Forecast at strongest current commercial baseline unless noted.
6150 | Signs & Flags | 12000 | 0 | 0 | 12000 | 0 | Forecast at strongest current commercial baseline unless noted.
6160 | Showhouse Furnishing - Showhome 1 | 35000 | 0 | 18000 | 35000 | 0 | Forecast at strongest current commercial baseline unless noted.
6170 | Sales Office Set-up | 18000 | 0 | 0 | 18000 | 0 | Forecast at strongest current commercial baseline unless noted.
6200 | Sales Consumables | 8000 | 0 | 0 | 8000 | 0 | Forecast at strongest current commercial baseline unless noted.
6210 | Sales Running Costs - Sales Office Cleaning | 10000 | 0 | 0 | 10000 | 0 | Forecast at strongest current commercial baseline unless noted.
6220 | Sales Landscaping - Showhome | 12000 | 0 | 0 | 12000 | 0 | Forecast at strongest current commercial baseline unless noted.
6230 | Sales Landscape Maintenance | 10000 | 0 | 0 | 10000 | 0 | Forecast at strongest current commercial baseline unless noted.
6260 | Home Information Packs | 4000 | 0 | 0 | 4000 | 0 | Forecast at strongest current commercial baseline unless noted.
6270 | Welcome Packs | 5000 | 0 | 0 | 5000 | 0 | Forecast at strongest current commercial baseline unless noted.

## Expected CVR
Expected CVR — Independent Control Answer
KPI | Value | [10 empty] | Section | Budget (£) | Expected FFC (£) | Variance (£)
Original Budget | 8065500 | [10 empty] | Land | 1760000 | 1760000 | 0
Committed POs | 2525000 | [10 empty] | Fees | 522000 | 522000 | 0
Approved CE Movement | 53500 | [10 empty] | Prelims | 516500 | 506500 | 10000
Ledger Actual | 3867500 | [10 empty] | R&S | 500000 | 535000 | -35000
Expected FFC | 8115000 | [10 empty] | Plot | 855000 | 855000 | 0
Forecast Variance | -49500 | [10 empty] | Super-Structure | 2948000 | 2967500 | -19500
[12 empty] | Abnormals | 413000 | 418000 | -5000
[12 empty] | Contributions | 275000 | 275000 | 0
[12 empty] | Sales | 276000 | 276000 | 0
Cost Code | Sub-Heading | Element | Budget (£) | PO Commitment (£) | Approved CE (£) | Current Commitment (£) | Ledger Actual (£) | Certified Gross (£) | Expected FFC (£) | Variance (£) | Status / Test Note
1100 | Land | Land Cost | 1650000 | 0 | 0 | 0 | 1650000 | 0 | 1650000 | 0
1110 | Land | VAT on Land Purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1120 | Land | Stamp Duty - Incl VAT if applicable | 85000 | 0 | 0 | 0 | 85000 | 0 | 85000 | 0
1130 | Land | Legal Fees - Solicitor | 25000 | 0 | 0 | 0 | 22000 | 0 | 25000 | 0
1140 | Land | Option Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1150 | Land | Selling Agent Fees - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1160 | Land | Sundy Land Costs - Overage Payments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1170 | Fees | Planning Application & Supporting Fees | 35000 | 0 | 0 | 0 | 35000 | 0 | 35000 | 0
1180 | Fees | Site Investigation | 25000 | 0 | 0 | 0 | 25000 | 0 | 25000 | 0
1190 | Fees | Archaeology | 15000 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0
1200 | Fees | Contamination | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 0
1210 | Fees | Design Fees | 40000 | 0 | 0 | 0 | 28000 | 0 | 40000 | 0
1220 | Fees | Architects - Post Planning | 55000 | 0 | 0 | 0 | 25000 | 0 | 55000 | 0
1230 | Fees | Engineers | 75000 | 0 | 0 | 0 | 42000 | 0 | 75000 | 0
1240 | Fees | Surveys | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 0
1250 | Fees | NHBC Bond Fees | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0
1260 | Fees | Insurance | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | 0
1270 | Fees | Planning Consultants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1280 | Fees | Highways Consultants | 20000 | 0 | 0 | 0 | 8000 | 0 | 20000 | 0
1290 | Fees | Environmental Consultants | 15000 | 0 | 0 | 0 | 6000 | 0 | 15000 | 0
1300 | Fees | M&E Consultants | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0
1310 | Fees | Sewers Adoption (s104): | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | 0
1320 | Fees | Highways Adoption (s18/38): | 22000 | 0 | 0 | 0 | 0 | 0 | 22000 | 0
1330 | Fees | S278 Fees | 12000 | 0 | 0 | 0 | 0 | 0 | 12000 | 0
1340 | Fees | Building Regulation Fees | 22000 | 0 | 0 | 0 | 0 | 0 | 22000 | 0
1350 | Fees | Planning Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1360 | Fees | SAP Calculations | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0
1370 | Fees | Air Tests | 7500 | 0 | 0 | 0 | 0 | 0 | 7500 | 0
1380 | Fees | NHBC - Warranty & Build control | 48000 | 0 | 0 | 0 | 26000 | 0 | 48000 | 0
1400 | Fees | Finance lenders Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1410 | Fees | Other Fees | 12500 | 0 | 0 | 0 | 0 | 0 | 12500 | 0
2100 | Prelims | Site Manager | 95000 | 0 | 0 | 0 | 42000 | 0 | 95000 | 0
2101 | Prelims | Assistant Site Manager | 55000 | 0 | 0 | 0 | 24000 | 0 | 55000 | 0
2110 | Prelims | Direct Staff Bonuses | 12000 | 0 | 0 | 0 | 0 | 0 | 12000 | 0
2120 | Prelims | Direct Staff NIC on Bonuses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2130 | Prelims | NIC on Salary | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | 0
2140 | Prelims | Pension | 9000 | 0 | 0 | 0 | 0 | 0 | 9000 | 0
2150 | Prelims | Forklift Driver - Direct | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2151 | Prelims | Forklift Driver - Agency | 36000 | 0 | 0 | 0 | 12000 | 0 | 36000 | 0
2160 | Prelims | Labourer - Direct | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2161 | Prelims | Labourer - Agency | 30000 | 0 | 0 | 0 | 10000 | 0 | 30000 | 0
2170 | Prelims | Site staff - Holiday Cover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2180 | Prelims | Principle Contractor Set-Up | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 0
2190 | Prelims | Forklift Truck | 34000 | 0 | 0 | 0 | 14000 | 0 | 34000 | 0
2191 | Prelims | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2200 | Prelims | Site Office | 28000 | 0 | 0 | 0 | 10000 | 0 | 28000 | 0
2201 | Prelims | Site Cabins | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | 0
2202 | Prelims | Containers | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0
2210 | Prelims | Oasis Unit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2211 | Prelims | Fuel | 22000 | 0 | 0 | 0 | 9000 | 0 | 22000 | 0
2220 | Prelims | Compound - Groundworks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2230 | Prelims | Site Electric Usage | 18000 | 0 | 0 | 0 | 7000 | 0 | 18000 | 0
2231 | Prelims | Site Water Usage | 7500 | 0 | 0 | 0 | 2500 | 0 | 7500 | 0
2232 | Prelims | TBS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2240 | Prelims | Plot Utility Bills Pre-Handover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2250 | Prelims | Road Cleaning - F Lift Road brush | 8000 | 0 | 0 | 0 | 0 | 0 | 8000 | 0
2260 | Prelims | Road Cleaning - Road sweep | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | 0
2270 | Prelims | Tipping Skips | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2280 | Prelims | Skips | 12000 | 0 | 0 | 0 | 4000 | 0 | 12000 | 0
2290 | Prelims | Pallets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2300 | Prelims | Bulk Items | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2310 | Prelims | PPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2311 | Prelims | Site consumables | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0
2320 | Prelims | Pedestrian Barriers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2321 | Prelims | Heras Fencing | 14000 | 0 | 0 | 0 | 0 | 0 | 14000 | 0
2330 | Prelims | Security - Cameras | 15000 | 0 | 0 | 0 | 5000 | 0 | 15000 | 0
2340 | Prelims | Security - Static guards | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2350 | Prelims | Contingency | 30000 | 0 | 0 | 0 | 0 | 0 | 20000 | 10000 | Only £20k of £30k contingency expected to be used.
3100 | R&S | Groundworker Prelims | 120000 | 115000 | 35000 | 150000 | 112000 | 97000 | 155000 | -35000 | Soft-ground approved CE plus unresolved muck-away risk.
3110 | R&S | Duct Crossings | 35000 | 0 | 0 | 0 | 18000 | 0 | 35000 | 0
3120 | R&S | Footpaths to Base | 55000 | 0 | 0 | 0 | 18000 | 0 | 55000 | 0
3130 | R&S | Saw cut & break out road for kerb install to channel / laybys | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3140 | R&S | White Lining | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3150 | R&S | Street Name Plates - Install | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3160 | R&S | R&S - REMEDIALS: | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 0
3170 | R&S | Electricity Mains - Mains & Connections | 55000 | 0 | 0 | 0 | 22000 | 0 | 55000 | 0
3180 | R&S | Gas Mains | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3190 | R&S | Water Mains - Laying & Connection | 35000 | 0 | 0 | 0 | 14000 | 0 | 35000 | 0
3200 | R&S | Telephone Mains | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | 0
3210 | R&S | Fibre | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | 0
3220 | R&S | Street Lights - Supply & Install Columns | 36000 | 0 | 0 | 0 | 0 | 0 | 36000 | 0
3230 | R&S | Street Lighting Connections | 9000 | 0 | 0 | 0 | 0 | 0 | 9000 | 0
3240 | R&S | Public Open Space & Play Areas | 45000 | 0 | 0 | 0 | 0 | 0 | 45000 | 0
3250 | R&S | Play Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3260 | R&S | Hard Landscaping | 35000 | 0 | 0 | 0 | 0 | 0 | 35000 | 0
3270 | R&S | Roads & Sewers Contingency | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0
3500 | Plot | Service Trenches & Ducts | 95000 | 90000 | 0 | 90000 | 52000 | 0 | 95000 | 0
3510 | Plot | Muck Away | 65000 | 0 | 0 | 0 | 44000 | 0 | 65000 | 0
3520 | Plot | Plot Drainage incl Internal Drainage | 165000 | 155000 | 0 | 155000 | 96000 | 0 | 165000 | 0
3530 | Plot | Paths - Slabs | 42000 | 0 | 0 | 0 | 0 | 0 | 42000 | 0
3540 | Plot | Private Drive Formation | 70000 | 0 | 0 | 0 | 24000 | 0 | 70000 | 0
3541 | Plot | Private Drives Complete | 62000 | 0 | 0 | 0 | 0 | 0 | 62000 | 0
3550 | Plot | Shared Drive Formation | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0
3551 | Plot | Shared Drive Complete | 22000 | 0 | 0 | 0 | 0 | 0 | 22000 | 0
3570 | Plot | Screen Walls - Foundations | 28000 | 0 | 0 | 0 | 0 | 0 | 28000 | 0
3580 | Plot | Screen Walls - Superstructure | 45000 | 0 | 0 | 0 | 0 | 0 | 45000 | 0
3590 | Plot | Fencing | 62000 | 58000 | 0 | 58000 | 15000 | 0 | 62000 | 0
3600 | Plot | Plot Clearance | 24000 | 0 | 0 | 0 | 0 | 0 | 24000 | 0
3610 | Plot | Plot Regrade | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 0
3620 | Plot | Topsoil placement | 32000 | 0 | 0 | 0 | 0 | 0 | 32000 | 0
3630 | Plot | Turfing - Adoptable Verges to Roads | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3640 | Plot | Planting | 48000 | 40000 | 0 | 40000 | 0 | 0 | 48000 | 0
3650 | Plot | Misc. Landscaping | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | 0
3660 | Plot | Pre-Occupation Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3670 | Plot | After Sales Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3680 | Plot | Contingency - Plot Groundworks | 22000 | 0 | 0 | 0 | 0 | 0 | 22000 | 0
4100 | Super-Structure | Pre-Cast Concrete | 35000 | 0 | 0 | 0 | 0 | 0 | 35000 | 0
4110 | Super-Structure | Scaffolding | 82000 | 78000 | 0 | 78000 | 30000 | 24000 | 82000 | 0
4120 | Super-Structure | Brickwork | 245000 | 235000 | 5000 | 240000 | 118000 | 112000 | 255000 | -10000 | Productivity loss pushes final cost above budget/commitment.
4130 | Super-Structure | Carpentry | 180000 | 175000 | 0 | 175000 | 82000 | 77000 | 175000 | 5000 | Control package: forecast at current PO, delivering £5k saving.
4140 | Super-Structure | Contract Crane Hire | 24000 | 0 | 0 | 0 | 0 | 0 | 24000 | 0
4150 | Super-Structure | Cladding | 48000 | 0 | 0 | 0 | 0 | 0 | 48000 | 0
4160 | Super-Structure | Render | 38000 | 0 | 0 | 0 | 0 | 0 | 38000 | 0
4170 | Super-Structure | Steelwork | 22000 | 0 | 0 | 0 | 0 | 0 | 22000 | 0
4180 | Super-Structure | Roofing | 115000 | 110000 | 0 | 110000 | 42000 | 30000 | 118000 | -3000 | Pending valley detail expected in full.
4190 | Super-Structure | PV | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 0
4200 | Super-Structure | Windows and Ext. Doors | 125000 | 122000 | -3000 | 119000 | 46000 | 36000 | 119000 | 6000 | Approved credit expected to flow through to final cost.
4210 | Super-Structure | Garage Doors | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | 0
4220 | Super-Structure | Insulation | 38000 | 0 | 0 | 0 | 0 | 0 | 38000 | 0
4230 | Super-Structure | Plastering & Drylining | 128000 | 125000 | 0 | 125000 | 68000 | 60000 | 125000 | 3000 | Current order forecast; £4k linked recovery is payment-only.
4240 | Super-Structure | Plumbing & Heating | 190000 | 185000 | -6000 | 179000 | 92000 | 87000 | 179000 | 11000 | Approved omission/credit expected to crystallise as saving.
4250 | Super-Structure | Electrical | 145000 | 140000 | 16000 | 156000 | 72000 | 60000 | 156000 | -11000 | Includes £12k customer extras + £4k payable repair origin.
4260 | Super-Structure | Kitchen Fitting | 118000 | 112000 | 0 | 112000 | 30000 | 30000 | 118000 | 0
4270 | Super-Structure | Appliances | 58000 | 55000 | 0 | 55000 | 0 | 0 | 58000 | 0
4280 | Super-Structure | Stone Worktops | 28000 | 0 | 0 | 0 | 0 | 0 | 28000 | 0
4290 | Super-Structure | Wardrobes | 0 | 0 | 0 | 0 | 8500 | 0 | 8500 | -8500 | Deliberate wrong-code ledger posting with no budget.
4300 | Super-Structure | Carpets | 62000 | 0 | 0 | 0 | 0 | 0 | 62000 | 0
4310 | Super-Structure | LVT | 38000 | 0 | 0 | 0 | 0 | 0 | 38000 | 0
4320 | Super-Structure | Vinyl | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 0
4330 | Super-Structure | Mastic & Sealing | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | 0
4340 | Super-Structure | Painting & Decoration | 92000 | 88000 | 0 | 88000 | 38000 | 28000 | 95000 | -3000 | QS forecasts £7k above PO despite normal ledger/cert progress.
4350 | Super-Structure | Ceramic Tiling | 48000 | 46000 | 0 | 46000 | 18000 | 18000 | 48000 | 0
4360 | Super-Structure | Cleaning | 30000 | 28000 | 0 | 28000 | 0 | 0 | 28000 | 2000 | Order expected at £28k; direct recovery affects payment only.
4500 | Super-Structure | Bricks | 165000 | 158000 | 0 | 158000 | 105000 | 0 | 172000 | -7000 | Brick material price/quantity overspend.
4510 | Super-Structure | Brickwork Specials | 12000 | 0 | 0 | 0 | 0 | 0 | 12000 | 0
4520 | Super-Structure | External Cladding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4530 | Super-Structure | Batten | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4540 | Super-Structure | Membrane | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4550 | Super-Structure | Tenmat fire barrier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4560 | Super-Structure | Blocks - Aggrtegate | 54000 | 52000 | 0 | 52000 | 33000 | 0 | 54000 | 0
4570 | Super-Structure | Blocks - Airated | 42000 | 40000 | 0 | 40000 | 28000 | 0 | 42000 | 0
4580 | Super-Structure | Sand Cement & Mortar | 52000 | 50000 | 0 | 50000 | 31000 | 0 | 56000 | -4000 | Mortar usage running above budget.
4590 | Super-Structure | Cast Stone Heads | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 0
4600 | Super-Structure | Cast Stone Cills | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | 0
4610 | Super-Structure | Lintels | 45000 | 0 | 0 | 0 | 23000 | 0 | 45000 | 0
4620 | Super-Structure | Steel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4630 | Super-Structure | Chimneys | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4640 | Super-Structure | Joists | 78000 | 0 | 0 | 0 | 38000 | 0 | 78000 | 0
4650 | Super-Structure | Floor deck | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 0
4660 | Super-Structure | Roof Timbers | 85000 | 82000 | 0 | 82000 | 46000 | 0 | 85000 | 0
4670 | Super-Structure | Soffit & Fascia | 35000 | 0 | 0 | 0 | 0 | 0 | 35000 | 0
4680 | Super-Structure | Staircases | 34000 | 0 | 0 | 0 | 0 | 0 | 34000 | 0
4690 | Super-Structure | Carcassing Timbers | 38000 | 0 | 0 | 0 | 0 | 0 | 38000 | 0
4700 | Super-Structure | Window Board | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0
4710 | Super-Structure | Door Linings | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | 0
4720 | Super-Structure | Skirting & Architrave | 28000 | 0 | 0 | 0 | 0 | 0 | 28000 | 0
4730 | Super-Structure | Internal Doors | 42000 | 40000 | 0 | 40000 | 15000 | 0 | 42000 | 0
4740 | Super-Structure | Ironmongery | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | 0
4750 | Super-Structure | Porches | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4760 | Super-Structure | Insulation Materials | 68000 | 0 | 0 | 0 | 29000 | 0 | 68000 | 0
4770 | Super-Structure | Fixings | 12000 | 0 | 0 | 0 | 0 | 0 | 12000 | 0
4780 | Super-Structure | Loft Traps | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4790 | Super-Structure | Meter Boxes | 9000 | 0 | 0 | 0 | 0 | 0 | 9000 | 0
4800 | Super-Structure | Rooflight | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4810 | Super-Structure | GRP Products | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4820 | Super-Structure | General Material Sundries | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | 0
5100 | Abnormals | Demolition / Site Clearance / Remediation: | 80000 | 76000 | 0 | 76000 | 76000 | 56000 | 80000 | 0
5110 | Abnormals | Archaeology: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5120 | Abnormals | Ecology: | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | 0
5130 | Abnormals | Piling - Specialist: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5140 | Abnormals | Piling - Groundworks: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5150 | Abnormals | Abnormal Foundations: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5160 | Abnormals | Raft Foundation: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5170 | Abnormals | Attenuation Pond / Swales / Culverts: | 95000 | 0 | 0 | 0 | 35000 | 0 | 95000 | 0
5180 | Abnormals | Electric Sub-Station: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5190 | Abnormals | Pump Station & Rising Main: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5200 | Abnormals | Retaining Features & Steps: | 65000 | 0 | 0 | 0 | 18000 | 0 | 65000 | 0
5210 | Abnormals | Abnormal / Non-Plot Fencing & Walls: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5220 | Abnormals | S278 Fees: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5230 | Abnormals | S184 Fees: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5240 | Abnormals | Earthworks - Arisings | 55000 | 0 | 0 | 0 | 34000 | 0 | 55000 | 0
5250 | Abnormals | POS / Abnormal Landscaping: | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0
5260 | Abnormals | S278 Works: | 75000 | 70000 | 6500 | 76500 | 25000 | 0 | 80000 | -5000 | Approved £6.5k CE plus minor traffic-management allowance.
5270 | Abnormals | Offsite Utility Services Maintenance: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5280 | Abnormals | Offsite Utility Service Diversions: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5290 | Abnormals | Render: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5300 | Abnormals | Black Weatherboarding: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5310 | Abnormals | Vertical Tile Hanging: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5320 | Abnormals | Stone Walling (Reconstituted / Prepped): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5340 | Contributions | S106 | 160000 | 0 | 0 | 0 | 80000 | 0 | 160000 | 0
5350 | Contributions | CIL | 115000 | 0 | 0 | 0 | 57500 | 0 | 115000 | 0
6100 | Sales | Private Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6110 | Sales | Sales Legal Fees | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0
6120 | Sales | Estate Agents | 95000 | 0 | 0 | 0 | 0 | 0 | 95000 | 0
6130 | Sales | P/X Assisted Move | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6140 | Sales | Advertising | 42000 | 0 | 0 | 0 | 10000 | 0 | 42000 | 0
6150 | Sales | Signs & Flags | 12000 | 0 | 0 | 0 | 0 | 0 | 12000 | 0
6160 | Sales | Showhouse Furnishing - Showhome 1 | 35000 | 0 | 0 | 0 | 18000 | 0 | 35000 | 0
6170 | Sales | Sales Office Set-up | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | 0
6180 | Sales | Health and Safety Equipment - Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6190 | Sales | Sales Business Rates - Showhome 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6200 | Sales | Sales Consumables | 8000 | 0 | 0 | 0 | 0 | 0 | 8000 | 0
6210 | Sales | Sales Running Costs - Sales Office Cleaning | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0
6220 | Sales | Sales Landscaping - Showhome | 12000 | 0 | 0 | 0 | 0 | 0 | 12000 | 0
6230 | Sales | Sales Landscape Maintenance | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0
6240 | Sales | Sales Parking Areas - Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6250 | Sales | Sales Fencing - Railings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6260 | Sales | Home Information Packs | 4000 | 0 | 0 | 0 | 0 | 0 | 4000 | 0
6270 | Sales | Welcome Packs | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0
6280 | Sales | Utility Bills Pre-Handover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## UAT Scenarios
UAT Scenarios — What BuildLite Must Prove
ID | Area | Scenario | Expected Result | Key Codes / Packages | Severity if Wrong | Status | Notes | Control Source
UAT-01 | Budget | Original budget totals agree to Expected CVR | Exact match to workbook total | All | Critical | Not Run |  | Expected CVR
UAT-02 | Groundworks | Approved £35k CE + £20k pending risk | CCV includes £35k only; pending £20k; FFC £155k on 3100 | 3100 / S-HG001 | Critical | Not Run |  | CE + Forecast
UAT-03 | Brickwork | Productivity loss despite PO below budget | Budget £245k; current commitment £240k; FFC £255k; £10k adverse | 4120 / S-HG005 | Critical | Not Run |  | Expected CVR
UAT-04 | Carpentry | Control package with saving | PO/FFC £175k vs £180k budget = £5k favourable | 4130 / S-HG006 | High | Not Run |  | Expected CVR
UAT-05 | Electrical | Customer upgrade + payable repair origin | CCV £156k; payable events certifiable | 4250 / S-HG011 | Critical | Not Run |  | CE Register
UAT-06 | Drylining recovery | £4k linked recovery against Drylining | Drylining CCV unchanged; Recovery Position driven by deduction history | 4230 / S-HG009 | Critical | Not Run |  | Recovery overlay
UAT-07 | Plumbing credit | Approved £6k credit | CCV £179k; forecast saving £11k vs budget | 4240 / S-HG010 | High | Not Run |  | Expected CVR
UAT-08 | Windows credit | Approved £3k credit | CCV/FFC £119k | 4200 / S-HG008 | Medium | Not Run |  | Expected CVR
UAT-09 | Roofing pending | £8k submitted variation | Pending £8k; CCV £110k until approval; FFC £118k | 4180 / S-HG007 | High | Not Run |  | CE + Forecast
UAT-10 | Direct recovery | £1.5k Cleaning direct recovery | Excluded from CCV; shown in Recovery Position; payment-only | 4360 / S-HG015 | Critical | Not Run |  | Recovery overlay
UAT-11 | Ledger vs certificates | Actual cost differs from certified gross | CVR keeps ledger actual and certified-to-date distinct | Multiple | Critical | Not Run |  | Ledger/Certificates
UAT-12 | Wrong-code posting | £8.5k on unbudgeted Wardrobes code | CVR exposes £8.5k unbudgeted/adverse cost | 4290 | Critical | Not Run |  | Ledger
UAT-13 | Material overspend | Brick material final cost exceeds budget | 4500 FFC £172k vs £165k = £7k adverse | 4500 / M-HG001 | High | Not Run |  | Expected CVR
UAT-14 | Contingency saving | Only £20k of £30k prelim contingency forecast | £10k favourable variance | 2350 | Medium | Not Run |  | Forecast
UAT-15 | Navigation / hydration | Open package/CVR/certs repeatedly | No blank screens, false zeros, stale model or negative remaining contract | All | Critical | Not Run |  | UI
UAT-16 | Plot Import | Valid 24-plot schedule imports | 24 unique plots; house type/config/beds/GIA/phase/tenure/status all populated | Plot Schedule | Critical | Not Run |  | Plot Schedule Control
UAT-17 | Plot Import | Duplicate Plot 12 negative file | Import blocked with duplicate plot-number validation | NEGATIVE TEST 1 | High | Not Run |  | Plot import validation
UAT-18 | Plot Import | Plot 18 missing House Type | Import blocked because House Type is required | NEGATIVE TEST 2 | High | Not Run |  | Plot import validation
UAT-19 | Plot Import | Sq Ft heading mapping test | GIA should not auto-detect from 'Sq Ft'; wizard should require manual mapping | MAPPING TEST | Medium | Not Run |  | Header alias behaviour
UAT-20 | Revenue | Base GDV from ft² × house-type rate | BuildLite base revenue matches control before plot extras | All plots | Critical | Not Run |  | Revenue Strategy Control
UAT-21 | Revenue | Garage premiums entered after import | Garage values increase plot selling prices exactly as control | Selected plots | High | Not Run |  | Plot Schedule Control
UAT-22 | Revenue | Plot-specific premiums/discounts | Open-space/larger-garden premiums and poor-position discounts reconcile to control | Selected plots | High | Not Run |  | Plot Schedule Control
UAT-23 | Revenue | Final GDV reconciliation | Total final plot revenue equals control workbook exactly | All plots | Critical | Not Run |  | Plot Schedule Control

## Matrix Index
Hawthorn Gardens — Payment Matrix Pack
PO Number | Cost Code | Element | Supplier | PO Value (£) | Stage Count | File Name | Test Type | Purpose / Expected Behaviour
S-HG001 | 3100 | Groundworker Prelims | J&M Civils Ltd | 115000 | 4 | S-HG001 - 3100 - Groundworker Prelims.xlsx | VALID | Matrix total exactly equals PO value
S-HG002 | 3500 | Service Trenches & Ducts | J&M Civils Ltd | 90000 | 4 | S-HG002 - 3500 - Service Trenches & Ducts.xlsx | VALID | Matrix total exactly equals PO value
S-HG003 | 3520 | Plot Drainage incl Internal Drainage | J&M Civils Ltd | 155000 | 4 | S-HG003 - 3520 - Plot Drainage incl Internal Drainage.xlsx | VALID | Matrix total exactly equals PO value
S-HG004 | 4110 | Scaffolding | HighReach Scaffolding Ltd | 78000 | 4 | S-HG004 - 4110 - Scaffolding.xlsx | VALID | Matrix total exactly equals PO value
S-HG005 | 4120 | Brickwork | Midlands Brickwork Ltd | 235000 | 5 | S-HG005 - 4120 - Brickwork.xlsx | VALID | Matrix total exactly equals PO value
S-HG006 | 4130 | Carpentry | Oakline Carpentry Ltd | 175000 | 5 | S-HG006 - 4130 - Carpentry.xlsx | VALID | Matrix total exactly equals PO value
S-HG007 | 4180 | Roofing | Peak Roofing Ltd | 110000 | 4 | S-HG007 - 4180 - Roofing.xlsx | VALID | Matrix total exactly equals PO value
S-HG008 | 4200 | Windows and Ext. Doors | Clearview Windows Ltd | 122000 | 4 | S-HG008 - 4200 - Windows and Ext. Doors.xlsx | VALID | Matrix total exactly equals PO value
S-HG009 | 4230 | Plastering & Drylining | SmoothFinish Drylining Ltd | 125000 | 4 | S-HG009 - 4230 - Plastering & Drylining.xlsx | VALID | Matrix total exactly equals PO value
S-HG010 | 4240 | Plumbing & Heating | FlowRight Plumbing Ltd | 185000 | 4 | S-HG010 - 4240 - Plumbing & Heating.xlsx | VALID | Matrix total exactly equals PO value
S-HG011 | 4250 | Electrical | Voltwise Electrical Ltd | 140000 | 4 | S-HG011 - 4250 - Electrical.xlsx | VALID | Matrix total exactly equals PO value
S-HG012 | 4260 | Kitchen Fitting | KitchenCraft Installations Ltd | 112000 | 4 | S-HG012 - 4260 - Kitchen Fitting.xlsx | VALID | Matrix total exactly equals PO value
S-HG013 | 4340 | Painting & Decoration | PerfectFinish Decorating Ltd | 88000 | 4 | S-HG013 - 4340 - Painting & Decoration.xlsx | VALID | Matrix total exactly equals PO value
S-HG014 | 4350 | Ceramic Tiling | TileWorks Midlands Ltd | 46000 | 4 | S-HG014 - 4350 - Ceramic Tiling.xlsx | VALID | Matrix total exactly equals PO value
S-HG015 | 4360 | Cleaning | WipeRight Cleaning Ltd | 28000 | 4 | S-HG015 - 4360 - Cleaning.xlsx | VALID | Matrix total exactly equals PO value
S-HG016 | 3590 | Fencing | Boundary Fencing Ltd | 58000 | 4 | S-HG016 - 3590 - Fencing.xlsx | VALID | Matrix total exactly equals PO value
S-HG017 | 3640 | Planting | Greenleaf Landscapes Ltd | 40000 | 4 | S-HG017 - 3640 - Planting.xlsx | VALID | Matrix total exactly equals PO value
S-HG018 | 5100 | Demolition / Site Clearance / Remediation | CleanEarth Remediation Ltd | 76000 | 4 | S-HG018 - 5100 - Demolition - Site Clearance - Remediation.xlsx | VALID | Matrix total exactly equals PO value
S-HG019 | 5260 | S278 Works | J&M Civils Ltd | 70000 | 4 | S-HG019 - 5260 - S278 Works.xlsx | VALID | Matrix total exactly equals PO value
S-HG005 | 4120 | Brickwork | Midlands Brickwork Ltd | 235000 | 5 | NEGATIVE TEST 1 - S-HG005 Brickwork - Totals Row and Column.xlsx | NEGATIVE TEST | Contains TOTAL row and TOTAL column; tests totals detection/ignore behaviour
S-HG011 | 4250 | Electrical | Voltwise Electrical Ltd | 140000 | 4 | NEGATIVE TEST 2 - S-HG011 Electrical - Missing Plot 24.xlsx | NEGATIVE TEST | Plot 24 omitted; imported total £132,440.00 vs PO £140,000.00

## Matrix Stage Profiles
Matrix Stage Profiles — Upload Design
Cost Code | Element | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | Control
3100 | Groundworker Prelims | Set-up / mobilisation (20%) | Substructure support (30%) | Mid-programme prelims (30%) | Completion / demob (20%) |  | Stage % = 100%
3500 | Service Trenches & Ducts | Service trenches (30%) | Duct installation (30%) | Connections (25%) | Backfill / final (15%) |  | Stage % = 100%
3520 | Plot Drainage incl Internal Drainage | Below slab drainage (30%) | External drainage (30%) | Testing (20%) | Final connections (20%) |  | Stage % = 100%
4110 | Scaffolding | Base Lift (25%) | Second Lift (30%) | Roof Lift (25%) | Strike (20%) |  | Stage % = 100%
4120 | Brickwork | DPC / Splash (12%) | First Lift (28%) | Second Lift (30%) | To Roof (22%) | Snag / Final (8%) | Stage % = 100%
4130 | Carpentry | Joists / Floor (20%) | Roof Carpentry (25%) | First Fix (30%) | Second Fix (20%) | Snag (5%) | Stage % = 100%
4180 | Roofing | Felt / Batten (25%) | Roof Covering (45%) | Ridge / Verges (20%) | Final (10%) |  | Stage % = 100%
4200 | Windows and Ext. Doors | Frames (45%) | Glazing (20%) | External Doors (25%) | Final Adjustments (10%) |  | Stage % = 100%
4230 | Plastering & Drylining | Board / Tack (35%) | Skim (35%) | Ceilings (20%) | Snag (10%) |  | Stage % = 100%
4240 | Plumbing & Heating | First Fix (35%) | Second Fix (35%) | Sanitaryware (20%) | Commissioning (10%) |  | Stage % = 100%
4250 | Electrical | First Fix (35%) | Second Fix (35%) | Accessories (20%) | Test / Certify (10%) |  | Stage % = 100%
4260 | Kitchen Fitting | Units (50%) | Worktops (25%) | Appliances / Final (15%) | Snag (10%) |  | Stage % = 100%
4340 | Painting & Decoration | Mist Coat (20%) | First Coat (30%) | Final Coat (40%) | Snag (10%) |  | Stage % = 100%
4350 | Ceramic Tiling | Bathroom Walls (35%) | Bathroom Floors (25%) | Kitchen / Splashback (25%) | Snag (15%) |  | Stage % = 100%
4360 | Cleaning | Build Clean (25%) | Sparkle Clean (40%) | Pre-Handover Clean (25%) | Final / Snag (10%) |  | Stage % = 100%
3590 | Fencing | Rear Boundaries (35%) | Side Boundaries (30%) | Frontage (25%) | Snag (10%) |  | Stage % = 100%
3640 | Planting | Soil Preparation (25%) | Planting (40%) | Turf / Finish (25%) | Establishment (10%) |  | Stage % = 100%
5100 | Demolition / Site Clearance / Remediation | Clearance (25%) | Excavate / Treat (40%) | Backfill / Make Good (20%) | Validation / Closeout (15%) |  | Stage % = 100%
5260 | S278 Works | Traffic Management (20%) | Kerbs / Civils (30%) | Surfacing (35%) | Lining / Completion (15%) |  | Stage % = 100%

## Plot Schedule Control
Hawthorn Gardens — Plot Schedule & Revenue Control
Plot | House Type | Configuration | Beds | GIA ft² | Phase | Tenure | Status | £/ft² | Base Value (£) | Garage | Garage Premium (£) | Plot Premium/(Discount) (£) | Expected Selling Price (£) | Plot Note | Import / Manual | Revenue Control | Value
1 | The Ash | Semi Detached | 2 | 750 | Phase 1 | Open Market | Not Released | 330 | 247500 | None | 0 | 5000 | 252500 | Corner / larger frontage | Import A-H; set £/ft² / Garage / premiums in BuildLite | Base GDV | 7987000
2 | The Ash | Semi Detached | 2 | 750 | Phase 1 | Open Market | Not Released | 330 | 247500 | None | 0 | 5000 | 252500 | Corner / larger frontage | Import A-H; set £/ft² / Garage / premiums in BuildLite | Garage Premiums | 292000
3 | The Ash | Semi Detached | 2 | 750 | Phase 1 | Open Market | Not Released | 330 | 247500 | Single Garage | 12000 | 0 | 259500 |  | Import A-H; set £/ft² / Garage / premiums in BuildLite | Plot Premiums/(Discounts) | 62500
4 | The Ash | Semi Detached | 2 | 750 | Phase 1 | Open Market | Not Released | 330 | 247500 | Single Garage | 12000 | 0 | 259500 |  | Import A-H; set £/ft² / Garage / premiums in BuildLite | Expected Final GDV | 8341500
5 | The Birch | Semi Detached | 3 | 950 | Phase 1 | Open Market | Not Released | 325 | 308750 | None | 0 | -5000 | 303750 | Close to site entrance | Import A-H; set £/ft² / Garage / premiums in BuildLite | Average £/Unit | 347562.5
6 | The Birch | Semi Detached | 3 | 950 | Phase 1 | Open Market | Not Released | 325 | 308750 | None | 0 | -5000 | 303750 | Close to site entrance | Import A-H; set £/ft² / Garage / premiums in BuildLite
7 | The Birch | Semi Detached | 3 | 950 | Phase 1 | Open Market | Not Released | 325 | 308750 | None | 0 | 0 | 308750 |  | Import A-H; set £/ft² / Garage / premiums in BuildLite
8 | The Birch | Semi Detached | 3 | 950 | Phase 1 | Open Market | Not Released | 325 | 308750 | None | 0 | -7500 | 301250 | Backs onto attenuation feature | Import A-H; set £/ft² / Garage / premiums in BuildLite
9 | The Birch | Semi Detached | 3 | 950 | Phase 1 | Open Market | Not Released | 325 | 308750 | Single Garage | 12000 | 0 | 320750 |  | Import A-H; set £/ft² / Garage / premiums in BuildLite
10 | The Birch | Semi Detached | 3 | 950 | Phase 1 | Open Market | Not Released | 325 | 308750 | Single Garage | 12000 | 0 | 320750 |  | Import A-H; set £/ft² / Garage / premiums in BuildLite
11 | The Birch | Semi Detached | 3 | 950 | Phase 1 | Open Market | Not Released | 325 | 308750 | Single Garage | 12000 | 7500 | 328250 | Open-space outlook | Import A-H; set £/ft² / Garage / premiums in BuildLite
12 | The Birch | Semi Detached | 3 | 950 | Phase 1 | Open Market | Not Released | 325 | 308750 | Single Garage | 12000 | 7500 | 328250 | Open-space outlook | Import A-H; set £/ft² / Garage / premiums in BuildLite
13 | The Cedar | Detached | 3 | 1050 | Phase 2 | Open Market | Not Released | 320 | 336000 | Single Garage | 15000 | 0 | 351000 |  | Import A-H; set £/ft² / Garage / premiums in BuildLite
14 | The Cedar | Detached | 3 | 1050 | Phase 2 | Open Market | Not Released | 320 | 336000 | Single Garage | 15000 | 0 | 351000 |  | Import A-H; set £/ft² / Garage / premiums in BuildLite
15 | The Cedar | Detached | 3 | 1050 | Phase 2 | Open Market | Not Released | 320 | 336000 | Single Garage | 15000 | 0 | 351000 |  | Import A-H; set £/ft² / Garage / premiums in BuildLite
16 | The Cedar | Detached | 3 | 1050 | Phase 2 | Open Market | Not Released | 320 | 336000 | Single Garage | 15000 | 0 | 351000 |  | Import A-H; set £/ft² / Garage / premiums in BuildLite
17 | The Cedar | Detached | 3 | 1050 | Phase 2 | Open Market | Not Released | 320 | 336000 | Single Garage | 15000 | 7500 | 358500 | Open-space outlook | Import A-H; set £/ft² / Garage / premiums in BuildLite
18 | The Cedar | Detached | 3 | 1050 | Phase 2 | Open Market | Not Released | 320 | 336000 | Single Garage | 15000 | 7500 | 358500 | Open-space outlook | Import A-H; set £/ft² / Garage / premiums in BuildLite
19 | The Oak | Detached | 4 | 1350 | Phase 2 | Open Market | Not Released | 310 | 418500 | Single Garage | 15000 | 0 | 433500 |  | Import A-H; set £/ft² / Garage / premiums in BuildLite
20 | The Oak | Detached | 4 | 1350 | Phase 2 | Open Market | Not Released | 310 | 418500 | Single Garage | 15000 | 10000 | 443500 | Larger south-facing garden | Import A-H; set £/ft² / Garage / premiums in BuildLite
21 | The Oak | Detached | 4 | 1350 | Phase 2 | Open Market | Not Released | 310 | 418500 | Double Garage | 25000 | 0 | 443500 |  | Import A-H; set £/ft² / Garage / premiums in BuildLite
22 | The Oak | Detached | 4 | 1350 | Phase 2 | Open Market | Not Released | 310 | 418500 | Double Garage | 25000 | 0 | 443500 |  | Import A-H; set £/ft² / Garage / premiums in BuildLite
23 | The Oak | Detached | 4 | 1350 | Phase 2 | Open Market | Not Released | 310 | 418500 | Double Garage | 25000 | 7500 | 451000 | Open-space outlook | Import A-H; set £/ft² / Garage / premiums in BuildLite
24 | The Oak | Detached | 4 | 1350 | Phase 2 | Open Market | Not Released | 310 | 418500 | Double Garage | 25000 | 22500 | 466000 | Corner plot + best open-space outlook | Import A-H; set £/ft² / Garage / premiums in BuildLite

## Revenue Strategy Control
Revenue Strategy — Known-Answer Control
House Type | Configuration | Beds | GIA ft² | Plots | £/ft² | Base Price (£) | Garage Rule | Location Adjustments | Purpose
The Ash | Semi Detached | 2 | 750 | 4 | 330 | 247500 | Selected plots +£12k single garage | ±£5k | Entry-level control
The Birch | Semi Detached | 3 | 950 | 8 | 325 | 308750 | Selected plots +£12k single garage | -£7.5k to +£7.5k | Core 3-bed
The Cedar | Detached | 3 | 1050 | 6 | 320 | 336000 | All +£15k single garage | +£7.5k on selected | Detached 3-bed
The Oak | Detached | 4 | 1350 | 6 | 310 | 418500 | Single/Double garage +£15k/+£25k | up to +£15k | Premium 4-bed