## Master Register
ID | Programme | Module | Improvement / issue | Requirement or observation | Priority | Implementation Status | JB Homes Deployment Status | Owner-UAT Deployment Status | Human UAT / Acceptance | Needs UAT | Horizon | Source | Item Type | Parent ID | Related / Overlapping IDs | Supporting source references | Supporting test / UAT references | Reconciliation note | Dependency / note | Historical v0.3 deployment note
LED-001 |  | Purchase Ledger | Incremental monthly ledger imports | Append new period costs, deduplicate, reconcile and retain cumulative actuals | P2 | Partially Implemented | Not independently verified | Poplar Road pilot used server-authoritative ledger after configuration correction | Split invoice and supplier-less journal pilot PASS; cumulative import policy remains open | Yes | Pilot improvement | Owner Oct 2026 | Engineering / Product |  | LED-003 | server/services/ledgerRepository.js; server/migrations/070_ledger_optional_supplier.sql; client/src/ledger/ledgerImportService.js | Focused ledger import, fingerprint, migration-070 and Poplar Road pilot evidence | Migration 070 permits genuine blank-supplier journals with source Reference and preserves supplier-present fingerprints. Poplar imported 374 transactions / Â£405,569.54 to PostgreSQL after authority correction; cumulative extract policy remains LED-003. | Sage/Xero integration | Not independently verified; implementation status is repository-based.
LED-002 |  | Purchase Ledger | Ledger exception workflow | Unresolved cost codes, reversals, duplicate warnings and corrections | P2 | Partially Implemented | Not independently verified | Poplar Road governed ledger exceptions resolved for Draft close | Pilot PASS for Cost Code resolution; general correction workflow remains partial | Yes | Pilot improvement | Mature demo UAT | Engineering / Product | LED-001 |  | server/services/ledgerRepository.js — reverseLedgerTransaction(), resolveLedgerTransaction() | server/test/ledgerCostCodeResolution.test.js; server/test/cvrLedgerRoutes.test.js | Two offsetting Cost Code 4000 rows were resolved in governed evidence before close. Reversals and Cost Code resolution remain audited; no general amendment workflow. | LED-001 | Not independently verified; implementation status is repository-based.
REV-001 |  | Revenue | View versus CVR authority | Separate Summary/Sales Register tabs from explicit authoritative source change | P1 | Implemented | Recorded deployed to JB Homes | Not independently verified | Automated or repository evidence only | No | Release | JB Homes UAT | Engineering / Product |  | REV-002 | client/src/components/RevenueWorkspace.jsx; client/src/revenue/revenueSettingsServerMapper.js | client/src/components/RevenueWorkspace.test.jsx — view tabs do not mutate authority | Implemented at a50ede3. Tabs inspect only; explicit confirmed action changes CVR Revenue authority. | a50ede3 | Implemented in Git at a50ede3; recorded deployed to JB Homes. Owner-UAT pending.
REV-002 |  | Revenue | Readable revenue validation | Friendly descriptions rather than technical field-path errors | P2 | Implemented | Recorded deployed to JB Homes | Not independently verified | Automated or repository evidence only | No | Release | JB Homes UAT | Engineering / Product | REV-001 |  | server/services/revenueSettingsValidation.js; client/src/revenue/revenueSettingsServerMapper.js | server/test/summaryRevenueValidation.test.js; client/src/revenue/revenueSettingsServerMapper.test.js | Readable line-numbered validation and legacy label mapping are implemented. | a50ede3 | Implemented in Git at a50ede3; recorded deployed to JB Homes. Owner-UAT pending.
CVR-001 | Wave C - C1 | CVR | Development Budget readiness warning | Overview incorrectly blocks new CVR despite locked periods and eligible P03 | P1 | Implemented | Confirmed deployed in de3331a release | Confirmed deployed in a1a947c release | Product Owner accepted; independent trial continuing | Yes | Pilot UX | JB Homes screenshot | Engineering / Product |  | TEST-001 | client/src/components/CVRRegister.jsx — firstCvrCreationState/readiness messaging; server/services/developmentCommercialReadiness.js; server/services/cvrPeriodRepository.js; client/src/components/DevelopmentOverview.jsx | client/src/components/CVRCreateNextNavigation.test.jsx; server/test/cvrDevelopmentBudgetIntegration.test.js; server/test/developmentCommercialReadiness.test.js; server/test/cvrDevelopmentBudgetIntegration.test.js; server/test/siteStartPeriodFoundation.test.js | Wave C1 at 464b321 corrects the yellow readiness presentation for governed Site Start-backed chains without changing period-creation authority. Confirmed in Main a1a947c and JB de3331a; continuing trial acceptance remains distinct. |  | Not independently verified; implementation status is repository-based.
CVR-002 |  | CVR | Overview KPI blanks | Certificates and forecast overview tiles blank despite underlying evidence | P2 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | JB Homes screenshot | Engineering / Product |  |  | client/src/components/CVRSummaryPage.jsx; client/src/components/CVRPortfolio.jsx; client/src/components/DevelopmentOverview.jsx; client/src/developments/developmentHelpers.js | client/src/components/CVRSummaryPage.kpi.test.jsx; client/src/components/CVRPortfolio.test.jsx; client/src/components/DevelopmentList.test.jsx; client/src/components/DevelopmentWorkspace.test.jsx; client/src/developments/developmentHelpers.test.js | Wave B KPI evidence is implemented. 28 Oct trial requires verification that Actual Cost to Date is prominent on the on-screen Summary, not only PDF/Worksheet. |  | Not independently verified; implementation status is repository-based.
CVR-003 |  | CVR | Budget and EFC terminology | Check Current Budget, EFC and Projected Adjustment clarity | P2 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Oakfield UAT | Engineering / Product | CVR-007 |  | client/src/components/CostCentreDrawer.jsx; server/services/cvrCloseFormulas.js | server/test/cvrCloseFormulas.test.js; client/src/cvr/cvrForecastEngine.test.js | Commercial distinctions are implemented. Remove any lingering Current Budget terminology and verify fixed Site Start benchmark language in the Poplar movement explanation. |  | Not independently verified; implementation status is repository-based.
CVR-004 | BuildLite Commercial Product Polish | CVR | CVR navigation | Reduce confusing page returns and per-code navigation | P2 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Hawthorn UAT | Engineering / Product | UX-001 |  | client/src/components/CVRRegister.jsx; client/src/components/CVRWorkspace.jsx; client/src/components/CvrPeriodSubviewNav.jsx | client/src/components/CVRSummaryPage.interaction.test.jsx | Functional routes exist; predictable return paths need current workflow UAT. |  | Not independently verified; implementation status is repository-based.
CVR-005 |  | CVR | Action-level RBAC | Permission and authenticated actor enforcement for CVR mutations | P0 | Implemented | Recorded deployed to JB Homes | Not independently verified | Automated or repository evidence only | No | Release | Claude security review | Engineering / Product |  |  | server/routes/cvrRoutes.js; server/services/cvrPeriodRepository.js; server/auth/routePermissionManifest.js | server/test/cvrWorkflowOwnership.test.js; server/test/siteStartPeriodFoundation.test.js | Action RBAC, authenticated actors and rollback protection implemented at f959d6a. | f959d6a | Implemented in Git at f959d6a; recorded deployed to JB Homes. Owner-UAT pending.
CVR-006 | BuildLite Commercial Product Polish | CVR | Responsive KPI ribbon | Eight grouped KPIs remain readable at different zoom levels | P3 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | GP5 UAT | Engineering / Product |  |  | client/src/components/CVRSummaryPage.jsx; client/src/styles/po-module.css; client/src/components/CVRPortfolio.jsx; client/src/styles/po-module.css | client/src/components/CVRSummaryPage.kpi.test.jsx; client/src/components/CVRPortfolio.test.jsx; client/src/cvr/cvrPortfolioMargin.test.js | Responsive compact eight-KPI Portfolio implemented through 8eb9e2c, 147b4f9 and cac6a1a. Hosted/human acceptance remains separate. | Previously addressed | Not independently verified; implementation status is repository-based.
CVR-007 |  | CVR | P03 movement explanation | Make commitments, CE exposure, Prelims and Selling Costs movements understandable | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Oak Meadow rehearsal | Engineering / Product |  | CVR-003 | server/services/cvrMovementExplanations.js; client/src/components/CVRTable.jsx | server/test/cvrMovementExplanations.test.js; client/src/components/CVRTable.movement.test.jsx | Movement calculations exist. Poplar shows Â£35,524.86 favourable plus Â£87,799.00 adverse = Â£52,274.14 net; the Â£0.19 difference from Projected Adjustment total requires explanation and director-level UAT. |  | Not independently verified; implementation status is repository-based.
PO-001 |  | Purchase Orders | Multi-cost-code orders | Allocate one PO across several cost codes with correct audit and CVR linkage | P1 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Post-feedback | Owner roadmap | Engineering / Product |  |  | server/routes/poRoutes.js; server/services/pdf.js; server/services/packageMaterialisation.js; server/services/cvrCloseSources.js | server/test/poApprovalPackage.test.js; server/test/cvrCloseEngine.test.js | PO lines can carry Cost Codes, but supported Package/certificate/CVR allocation semantics for a truly split PO are not established. |  | Not independently verified; implementation status is repository-based.
PO-002 | Wave C - C5 | Purchase Orders | PDF branding and approvals | Increase logo size and show electronic approval evidence | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | JB Homes PDF | Engineering / Product |  | OPS-006 | server/services/pdf.js; server/templates/po.hbs; server/services/tenantBranding.js | server/test/poApprovalPackage.test.js; server/test/tenantBranding.test.js | Branding and authenticated approval evidence exist; requested presentation/logo sizing needs visual acceptance. |  | Not independently verified; implementation status is repository-based.
PO-003 |  | Purchase Orders | Tenant-scoped PO numbers | Remove globally keyed PO-number identity collisions | P1 | Outstanding | Not independently verified | Not independently verified | Automated or repository evidence only | No | Scale | Technical manual | Engineering / Product | TEN-001 | SUP-001 | server/migrations/001_baseline.sql; server/migrations/002_tenant_keys.sql | server/test/criticalApplicationContainment.test.js | purchase_orders.po_number remains a global primary key. | TEN-001 | Not independently verified; implementation status is repository-based.
PO-004 | Wave C - C5 | Purchase Orders | Lump-sum trade package simplicity | Keep simple one-line trade orders; breakdown in payment matrix | P2 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Willow UAT | Engineering / Product |  |  | server/routes/poRoutes.js; server/services/packageMaterialisation.js; client/src/components/OrderMatrixEditor.jsx | server/test/poApprovalPackage.test.js; server/test/orderMatrixRoutes.test.js | One-line lump-sum orders and matrix detail are supported; simplicity needs workflow UAT. |  | Not independently verified; implementation status is repository-based.
SUP-001 |  | Suppliers | Tenant-safe supplier identifiers | Remove global supplier-ID collision | P1 | Outstanding | Not independently verified | Not independently verified | Automated or repository evidence only | No | Scale | Technical manual | Engineering / Product | TEN-001 | PO-003 | server/migrations/001_baseline.sql; server/migrations/002_tenant_keys.sql | server/test/criticalApplicationContainment.test.js | suppliers.id remains a global primary key. | TEN-001 | Not independently verified; implementation status is repository-based.
CERT-001 | Wave C - C2 | Certificates | Search and filters | Make certificate/application registers easy to navigate | P1 | Implemented | Confirmed deployed in de3331a release | Confirmed deployed in a1a947c release | JB register functioning; ongoing user UAT | Yes | Pilot UX | Hawthorn UAT | Engineering / Product |  | CERT-005 | client/src/components/CertificateRegister.jsx; server/routes/certificateRoutes.js; server/services/certificateRegisterRepository.js; client/src/components/ApplicationSidebar.jsx | client/src/components/PaymentCertificates.certificateHydration.test.jsx | Wave C2 at 635b1b8 implements the tenant-scoped company-wide Certificate Register with server search, combined filters, pagination and canonical certificate navigation. JB observed 10 records; ongoing human acceptance remains separate. |  | Not independently verified; implementation status is repository-based.
CERT-002 |  | Certificates | Five-stage payment assessment | Application, ordered works, variations, reconciliation, release for approval | P1 | Implemented | Not independently verified | Not independently verified | Automated or repository evidence only | No | Pilot UX | Owner workflow Sep 2026 | Engineering / Product |  |  | client/src/components/PaymentCertificateApplication.jsx; PaymentCertificateValuationGrid.jsx; PaymentCertificateReconcile.jsx; PaymentApprovalRun.jsx | server/test/paymentApplicationRepository.test.js; server/test/paymentCertificateRoutes.test.js; client/src/components/PaymentCertificateReconcile.test.jsx | Application, assessment, variations, reconciliation and approval/release stages are implemented. |  | Not independently verified; implementation status is repository-based.
CERT-003 |  | Certificates | Late notice control | Warn, escalate or govern late Payment Notice issue | P1 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | JB Homes rehearsal | Engineering / Product |  |  | server/services/paymentCertificateTimetable.js; client/src/components/PaymentCertificateNotices.jsx; client/src/components/PaymentApprovalRun.jsx | server/test/paymentCertificateTimetable.test.js; server/test/paymentNoticeRbacLifecycle.test.js | Deadlines and late warnings exist; owner policy must settle warning/escalation versus hard blocking. |  | Not independently verified; implementation status is repository-based.
CERT-004 |  | Certificates | Payment approval batch matrix | One line per certificate, highlight unapproved amounts | P1 | Implemented | Not independently verified | Not independently verified | Automated or repository evidence only | No | Post-feedback | Owner CD workflow | Engineering / Product | ACC-001 |  | client/src/components/PaymentApprovalRun.jsx; server/services/paymentAuthorityRepository.js | client/src/components/PaymentApprovalRun.test.jsx; server/test/paymentAuthorityCombinedApproval.test.js | A real certificate approval queue and combined payment-authority workflow exist. | ACC-001 | Not independently verified; implementation status is repository-based.
CE-001 |  | Commercial Events | Expected liability UX | Clarify treatment and expected-liability controls | P2 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Hawthorn UAT | Engineering / Product |  |  | client/src/components/CommercialEventDrawer.jsx; client/src/commercialEvents/commercialEventExpectedLiability.js | client/src/commercialEvents/commercialEventExpectedLiabilityPanel.test.jsx; server/test/cvrExpectedLiabilityClose.test.js | Expected-liability treatment is implemented; clarity remains human UAT. |  | Not independently verified; implementation status is repository-based.
MAT-001 | BuildLite Commercial Product Polish | Order Matrices | Matrix header alignment | Improve numeric and column-heading alignment | P3 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Hawthorn UAT | Engineering / Product |  |  | client/src/components/OrderMatrixEditor.jsx; client/src/components/OrderMatrixDrawerSection.jsx; client/src/styles/po-module.css | client/src/components/OrderMatrixPlaceholderPreview.test.jsx; server/test/orderMatrixRoutes.test.js | Functional matrix UI exists; alignment is visual UAT. |  | Not independently verified; implementation status is repository-based.
PRE-001 | BuildLite Commercial Product Polish | Prelims | Programme date dependency | Explain unresolved time-related lines when dates missing | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Oak Meadow rehearsal | Engineering / Product | ADM-001 |  | server/services/prelimsForecastEngine.js; client/src/components/PrelimsTimeSpanFields.jsx | server/test/prelimsForecastEngine.test.js; client/src/components/DevelopmentPrelimsSetupWorksheet.test.jsx | Programme dates and unresolved TIME lines are supported; explanation quality needs UAT. |  | Not independently verified; implementation status is repository-based.
PRE-002 | Wave C - C5 | Prelims | Template adoption UX | Make setup, inheritance and adoption actions obvious | P2 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Oakfield UAT | Engineering / Product | ADM-001 | SELL-001 | client/src/components/DevelopmentPrelimsWorkspace.jsx; DevelopmentPrelimsAdoptionReview.jsx | server/test/prelimsSetupRoutes.test.js; server/test/prelimsAdoptionApplyRoutes.test.js | Templates, inheritance and adoption exist; discoverability requires UAT. |  | Not independently verified; implementation status is repository-based.
SELL-001 | Wave C - C5 | Selling Costs | Detailed template UX | Clarify add-line location, mappings and adopted state | P2 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Oakfield UAT | Engineering / Product | ADM-001 | PRE-002 | client/src/components/DevelopmentDetailedSellingCosts.jsx; client/src/components/admin/AdminSellingCostsTemplatesPage.jsx | server/test/sellingCostsDetailedProposal.test.js; client/src/components/DevelopmentDetailedSellingCosts.test.jsx | Detailed templates and adoption state exist; add-line and mapping usability need UAT. |  | Not independently verified; implementation status is repository-based.
ADM-001 |  | Administration | Company readiness flow | Reduce repeated setup, improve mapping multi-select and button states | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Willow UAT | Engineering / Product |  | PRE-001; PRE-002; SELL-001 | client/src/components/admin/AdminCostCodeHierarchySetup.jsx; AdminCostCodeBulkClassification.jsx; server/routes/tenantAdministrationRoutes.js | client/src/components/admin/AdminCostCodeHierarchySetup.test.jsx; server/test/tenantMembershipAdministration.test.js | Persisted company setup and bulk mapping exist; end-to-end readiness flow still spans several screens. |  | Not independently verified; implementation status is repository-based.
UX-001 | BuildLite Commercial Product Polish | Navigation | Navigation and return paths | Make Home and post-save destinations predictable | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Historical UAT | Engineering / Product |  | CVR-004; UX-002 | client/src/developments/developmentWorkspaceTabNavigation.js; client/src/admin/adminNavigation.js | client/src/developments/developmentWorkspaceTabNavigation.test.js; client/src/admin/adminNavigation.test.js | The production sidebar and canonical navigation materially improve the global frame; end-to-end workflow return paths still require human UAT. |  | Not independently verified; implementation status is repository-based.
UX-002 | Wave C - C3 | Navigation | Post-action button states | Disable adopted/done actions once completed | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Willow/Oakfield UAT | Engineering / Product | UX-001 |  | Prelims/Selling Costs adoption components; certificate lifecycle components; RevenueWorkspace.jsx | respective component tests | Many completed actions disable or disappear, but this is not demonstrated as an application-wide invariant. |  | Not independently verified; implementation status is repository-based.
UX-003 |  | Navigation | Animated Home hero | Subtle financial-symbol animation with reduced-motion support | P2 | Implemented | Not independently verified | Not independently verified | Automated or repository evidence only | No | Later | Branding idea | Engineering / Product |  |  | client/src/components/BuildLiteHome.jsx; client/src/App.css |  | Financial Data Flow V2 is implemented in the production Home hero with reduced-motion support at 639f645. |  | Not independently verified; implementation status is repository-based.
ACC-001 |  | Accounts Integration | Sage/Xero integration | Commercial-to-accounts handoff, export, posted/paid reconciliation | P1 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Post-feedback | Owner roadmap | Engineering / Product |  | ACC-002; CERT-004 | client/src/components/PaymentApprovalRun.jsx; PaymentReleaseWorklist.jsx; server/services/paymentReleaseRepository.js | server/test/paymentReleaseFoundation.test.js | Governed handoff exists; no live Sage/Xero API or posted/paid reconciliation. | CERT-004 | Not independently verified; implementation status is repository-based.
ACC-002 |  | Accounts Integration | Payment Release export | Controlled CSV/Excel first, APIs later | P1 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Post-feedback | Demo capability gap | Engineering / Product | ACC-001 |  | client/src/components/PaymentReleaseWorklist.jsx; server/routes/paymentReleaseRoutes.js | server/test/paymentReleaseFoundation.test.js | Release worklist exists; controlled CSV/Excel payment schedule export was not found. | ACC-001 | Not independently verified; implementation status is repository-based.
CASH-001 |  | Cash Flow | Development cash flow model | Time-phase costs, sales, commitments and working capital | P2 | Future Development | Not independently verified | Not independently verified | Automated or repository evidence only | No | Post-feedback | Owner roadmap | Engineering / Product |  | CASH-002 |  |  | No development time-phased cash-flow/working-capital model found. |  | Not independently verified; implementation status is repository-based.
CASH-002 |  | Cash Flow | Portfolio cash flow | Aggregate development cash forecasts | P3 | Future Development | Not independently verified | Not independently verified | Automated or repository evidence only | No | Scale | Owner roadmap | Engineering / Product | CASH-001 |  |  |  | No portfolio cash-flow aggregation; depends on CASH-001. | CASH-001 | Not independently verified; implementation status is repository-based.
AI-001 |  | Assistant | Authoritative commercial assistant | Tenant-safe answers on payments, orders, CVRs and variations | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Post-feedback | Owner roadmap | Engineering / Product |  | AI-002 | client/src/commercialAssistant/recommendationEngine.js; CommercialAssistantDrawer.jsx | client/src/commercialAssistant/commercialAssistant.test.js | Rule-based recommendations exist; not a server-authoritative tenant-safe question-answering assistant. |  | Not independently verified; implementation status is repository-based.
AI-002 |  | Assistant | Guided actions | Explain workflows and propose auditable actions with approval | P3 | Future Development | Not independently verified | Not independently verified | Automated or repository evidence only | No | Scale | Owner roadmap | Engineering / Product | AI-001 |  | client/src/commercialAssistant/commercialAssistantNavigation.js |  | Current assistant navigates/explains but does not propose governed executable actions. | AI-001 | Not independently verified; implementation status is repository-based.
TEN-001 |  | Architecture | Shared tenancy and unified deployment | One release for all customers with robust isolation and tenant-safe IDs | P1 | Partially Implemented | Not independently verified | Not independently verified | Automated or repository evidence only | No | Scale | Architecture discussion | Engineering / Product |  | PO-003; SUP-001 | server/auth/authMiddleware.js; server/auth/requestContext.js; server/services/activeClient.js; migrations/031,059,063 | server/test/rbacIdentityFoundation.test.js; server/test/tenantMembershipAdministration.test.js | Clerk tenancy and RBAC exist; global identifiers prevent unrestricted shared tenancy. | PO-003; SUP-001 | Not independently verified; implementation status is repository-based.
OPS-001 |  | Operations | Migration runner safeguards | Database identity guard, lock, checksum and preview | P1 | Outstanding | Not independently verified | Not independently verified | Automated or repository evidence only | No | Hardening | Technical review | Engineering / Product |  | OPS-007; OPS-008; OPS-009 | server/scripts/migrate.js; docs/operations/BUILDLITE_TECHNICAL_OPERATIONS_MANUAL.md §7.2/L6 | server/test/hostedReadiness.test.js | Runner lacks intrinsic database guard, advisory lock, checksums and dry-run. |  | Not independently verified; implementation status is repository-based.
OPS-002 |  | Operations | Recovery runbook | Tested restore, checksums, destination guard and UTC snapshot hashes | P1 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete | No | Hardening | JB Homes incident | Engineering / Product |  | OPS-009 | docs/operations/BUILDLITE_TECHNICAL_OPERATIONS_MANUAL.md §§7.4–7.7 | Recorded Owner-UAT and JB Homes backup, archive validation and isolated restore procedures | Recovery runbook and secure PowerShell procedures are implemented; individual recovery exercises remain operational evidence. |  | Not independently verified; implementation status is repository-based.
OPS-003 |  | Operations | Hosted safety configuration | Verify production NODE_ENV, no test auth, CORS and authority flags | P0 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Immediate | Technical review | Engineering / Product |  | OPS-008 | server/utils/productionConfig.js; server/app.js; docs/HOSTED_PILOT_RUNBOOK.md | server/test/hostedReadiness.test.js | P0 open safety finding: Main CVR server authority was enabled while ledger server authority was absent, causing browser-local actuals and server CVR divergence. Add deployment validation and fail-visible/closed behaviour; do not rely on manual flag knowledge. | Effective authority-variable validation across matched frontend/API deployment is required. | Not independently verified; implementation status is repository-based.
OPS-004 |  | Operations | Owner-UAT migration 068 upgrade | Verify ledger, back up, migrate 068 and deploy latest API and Revenue frontend | P1 | Implemented | Not independently verified | Known pending migration/release parity | Operational verification recorded complete | No | Near term release | 18 Oct rollback | Engineering / Product |  | OPS-007 | server/migrations/068_site_start_budget_submission_boundary.sql; server/migrations/068_site_start_budget_submission_boundary.sql; docs/operations/BUILDLITE_TECHNICAL_OPERATIONS_MANUAL.md | server/test/siteStartPeriodFoundation.test.js; Product Owner evidence: Owner-UAT ledger frontier 068 and function verification passed | Owner-UAT migration 068 is complete. Later release parity remains OPS-007. | Currently 4382970/067 | Owner-UAT recorded at API 4382970 / database frontier 067; JB Homes is on a frontier-068-compatible release.
OPS-005 |  | Operations | CI and deployment tracking | Automated tests, tags, release matrix, staging and rollback | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Scale | Technical review | Engineering / Product |  | OPS-007 | package.json; server/package.json; server/scripts/rehearse-blank-pilot-database.js | server/test/hostedReadiness.test.js | Release controls exist but several migration/audit scripts failed due to psql parsing, constraint canonicalisation or environment loading. Create a maintained locally end-to-end-tested guarded procedure without weakening safeguards. |  | Not independently verified; implementation status is repository-based.
DOC-001 |  | Documentation | Reconcile legacy docs | Correct README, Constitution, DATABASE and CURRENT_STATE | P2 | Outstanding | Not independently verified | Not independently verified | Automated or repository evidence only | No | Documentation | Manual v1.1 | Engineering / Product |  |  | docs/operations/BUILDLITE_TECHNICAL_OPERATIONS_MANUAL.md §1.3; README.md; docs/PRODUCT_CONSTITUTION.md; docs/DATABASE.md |  | Current operations manual explicitly identifies stale legacy documentation. |  | Not independently verified; implementation status is repository-based.
REP-001 |  | Reporting | Portfolio CVR dashboard | Director-level development movements and margin visibility | P1 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Post-feedback | Owner roadmap | Engineering / Product |  |  | client/src/components/CVRPortfolio.jsx | client/src/components/CVRPortfolio.test.jsx | CVR Portfolio plus the tenant-scoped Home dashboard provide executive visibility; full cross-development movement/exception reporting remains incomplete. |  | Not independently verified; implementation status is repository-based.
TEND-001 |  | Tendering | Tender management | Issue trade enquiries, compare returns, award and create PO | P3 | Future Development | Not independently verified | Not independently verified | Automated or repository evidence only | No | Scale | Owner roadmap | Engineering / Product |  |  |  |  | No tender enquiry/return comparison/award module found. |  | Not independently verified; implementation status is repository-based.
PORT-001 |  | Supplier Portal | Supplier collaboration | Applications, variations and documents with permission controls | P3 | Future Development | Not independently verified | Not independently verified | Automated or repository evidence only | No | Scale | Owner roadmap | Engineering / Product |  |  |  |  | No external supplier collaboration portal found. |  | Not independently verified; implementation status is repository-based.
FB-001 |  | Customer Feedback | John Burke demo feedback | Capture independent Finance Director experience | P1 | Outstanding | Not independently verified | Not independently verified | Required / not recorded complete | Yes | External validation | JB Homes invite | Customer Discovery |  | PO-005; PO-006; ADM-002; UX-016 |  |  | Independent JB trial is active. PO204 persistence/attribution remains unproved. Membership audit found activation only and no deactivation event; cause unresolved. Optional per-user light theme requested. Do not infer causes without evidence. |  | Not independently verified; implementation status is repository-based.
FB-002 |  | Customer Feedback | Levison discovery | Capture MD, QS and accounts workflows and pilot fit | P1 | Partially Implemented | Not independently verified | Poplar Road DEV-002 retrospective onboarding delivered in Main trial | Draft P01 reporting milestone delivered to Matt; commercial interpretation pending | Yes | External validation | Owner plan | Customer Discovery |  | ONB-001; DEV-001 |  |  | Poplar Road Draft P01 reconciled at EFC Â£767,712.02 and Actual Â£405,569.54; PDF and Excel sent to Matt. Not Locked/approved and not proof of loss. Earlier recreate proposal is reassessed; no reset without explicit authority. | Retain Â£648.70 Sage source/import difference and Â£0.19 movement-attribution difference as unresolved evidence. | Not independently verified; implementation status is repository-based.
FB-003 |  | Customer Feedback | Cotswold Oak response | Capture needs, objections and trial opportunity | P2 | Outstanding | Not independently verified | Not independently verified | Required / not recorded complete | Yes | External validation | Owner plan | Customer Discovery |  |  |  |  | External customer-discovery action requiring a customer response. |  | Not independently verified; implementation status is repository-based.
LED-003 |  | Purchase Ledger | Cumulative accounting-extract import policy | Decide and support the safe treatment of monthly cumulative files containing previously imported and new transactions. | P1 | Outstanding | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot improvement | Repository reconciliation | Engineering / Product | LED-001 | LED-002 | server/services/ledgerRepository.js — whole-batch duplicate gate | server/test/cvrLedgerRoutes.test.js — duplicate whole-batch rollback | Product Owner must decide delta-only versus cumulative-file contract. | LED-001 | Not deployed / not independently verified.
TEST-001 |  | Test Assurance | Development Budget stale integration fixtures | Reconcile the five historically reported stale Development Budget fixtures with current Site Start and monthly CVR authority. | P1 | Implemented | Not independently verified | Not independently verified | Automated or repository evidence only | No | Release assurance | Repository reconciliation | Engineering / Product |  | CVR-001 | server/services/cvrSiteStartBudgetSource.js; server/services/cvrDevelopmentBudgetSnapshot.js; server/test/cvrDevelopmentBudgetIntegration.test.js; server/test/siteStartPeriodFoundation.test.js | server/test/cvrDevelopmentBudgetIntegration.test.js; server/test/cvrDevelopmentBudgetBaseline.test.js; 71c103f real-path Site Start continuation and tampered-linkage regressions | The stale Development Budget integration-fixture gap is corrected at 71c103f. |  | Not deployed / not independently verified.
OPS-006 |  | Operations | Hosted commercial-document PDF acceptance | Verify certificate, Payment Notice and Pay Less PDF rendering in a hosted environment using legitimate existing evidence. | P0 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot acceptance | Prior release deferral | Engineering / Product |  | PO-002 | server/services/commercialDocumentRenderer.js; server/templates/commercial-documents/ | server/test/paymentNoticeRbacLifecycle.test.js; local Chromium rendering evidence | Do not create artificial financial evidence solely for this test. |  | Not deployed / not independently verified.
UAT-001 |  | UAT | Hawthorn Gardens current-mechanics recovery | Recover the protected Hawthorn Gardens known-answer pack against current Site Start, CVR, CE/VO, certificate and ledger mechanics without remapping its client-owned chart. | P1 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot assurance | CURRENT_STATE / Product Constitution | Engineering / Product |  | CVR-003; CERT-002 | CURRENT_STATE.md — Hawthorn protected UAT; docs/test-data/Hawthorn Gardens UAT/ | docs/test-data/Hawthorn Gardens UAT/recovery/KNOWN_ANSWER_RECONCILIATION.md | Protected UAT evidence exists but is not imported on current mechanics. |  | Not deployed / not independently verified.
OPS-007 |  | Operations | Environment release-pair parity | Record and verify frontend build, API commit and database migration frontier together for every hosted environment. | P0 | Partially Implemented | Resolved mismatch; matched de3331a | Matched a1a947c; de3331a unverified | Automated or repository evidence only | No | Immediate | Repository reconciliation | Engineering / Product |  | OPS-004; OPS-005 | docs/operations/BUILDLITE_TECHNICAL_OPERATIONS_MANUAL.md §§4,8,12 | Separate JB Homes and Owner-UAT migration/deployment preflights | JB frontend advanced ahead of API 71c103f and caused Certificate Register 404; matching both at de3331a resolved the incident. Manual controls exist, but repeatable provider-side release-pair verification remains partially implemented. |  | Not deployed / not independently verified.
OPS-008 |  | Operations | Developer reset containment | Remove or further contain the all-tenant developer reset risk beyond reliance on NODE_ENV configuration. | P1 | Outstanding | Not independently verified | Not independently verified | Automated or repository evidence only | No | Hardening | Technical operations review | Engineering / Product |  | OPS-003 | server/app.js; server/routes/developerRoutes.js; server/scripts/reset-dev-data.js | server/test/criticalApplicationContainment.test.js | Production excludes the route, but a misconfigured non-production hosted service could expose destructive reset behaviour. |  | Not deployed / not independently verified.
OPS-009 |  | Operations | Verified recovery drill evidence | Complete and record a dated isolated restore with archive checksum, ledger comparison, row counts and immutable financial fingerprints. | P0 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Hardening | Repository reconciliation | Engineering / Product | OPS-002 |  | docs/operations/BUILDLITE_TECHNICAL_OPERATIONS_MANUAL.md §§7.4–7.7 |  | A documented procedure is not proof of recoverability. |  | Not deployed / not independently verified.
CERT-005 | Wave C - C2 | Certificates | Certificate register acceptance criteria | Define and verify minimum filters for development, supplier, Package, lifecycle state, period and payment status. | P1 | Implemented | Confirmed deployed in de3331a release | Confirmed deployed in a1a947c release | Isolated browser acceptance passed; hosted trial continuing | Yes | Pilot UX | Repository reconciliation | Engineering / Product | CERT-001 |  | client/src/components/PaymentCertificates.jsx; PaymentCertificateWorkspace.jsx | client/src/components/PaymentCertificates.certificateHydration.test.jsx | Wave C2 interaction, route-authority, guarded database and isolated production-component browser acceptance completed. Hosted customer acceptance remains open. |  | Not deployed / not independently verified.
UX-004 | BuildLite Commercial Product Polish | UX Consistency | Complete missing shared CSS rules | Add the missing button, table-scroll, modal, status-badge, Admin feedback and radius-token rules without changing workflow behaviour. | P0 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Claude UX consistency audit | Engineering / Product | UX-001 | UX-002; MAT-001; PRE-002; SELL-001 | client/src/styles/po-module.css; client/src/styles/brand.css; client/src/styles/brand.css; client/src/styles/po-module.css | Focused rendered tests plus visual UAT; client/src/components/SupplierSelect.modalDismissal.test.jsx | Wave A (239273a) implements missing shared modal, button, disabled-state and status primitives. |  | Not deployed / not independently verified.
UX-005 | Wave C - C4 | UX Consistency | Neutralise starter styles and standardise payment headers | Remove Vite starter heading/link/theme leakage and use the established page header and button treatments on Payment Approval and Release. | P0 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Claude UX consistency audit | Engineering / Product | UX-001 | CERT-004; ACC-001 | client/src/index.css; client/src/components/PaymentApprovalRun.jsx; PaymentReleaseWorklist.jsx; client/src/styles/brand.css; client/src/styles/po-module.css | PaymentApprovalRun.test.jsx; PaymentReleaseWorklist.test.jsx; visual UAT; Wave A visual-foundation evidence at 239273a | Wave A neutralised several legacy/light surfaces; the cross-module sweep remains Wave C C4. |  | Not deployed / not independently verified.
UX-006 | Wave C - C4 | UX Consistency | Dark-theme surface corrections | Replace light-theme backgrounds and hard-coded light text colours on Prelims, Selling Costs and related dark screens with existing brand tokens. | P0 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Claude UX consistency audit | Engineering / Product | UX-004 | PRE-002; SELL-001 | client/src/styles/po-module.css; client/src/styles/brand.css; client/src/styles/brand.css; client/src/styles/po-module.css | DevelopmentPrelimsWorkspace tests; Selling Costs component tests; visual UAT; Wave A visual-foundation evidence at 239273a | Dark-theme corrections are materially implemented but not proven across every module; remaining work is C4. |  | Not deployed / not independently verified.
UX-007 | Wave C - C3 | Navigation | Reliable unsaved-changes protection | Make the shared guard evaluate isDirty, avoid false prompts, and protect critical edited forms and drawers from silent loss. | P0 | Outstanding | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot safety | Claude UX consistency audit | Engineering / Product | UX-001 | UX-002; UX-014 | client/src/navigation/UnsavedChangesProvider.jsx; AdminCostCodeBulkClassification.jsx | navigation/UnsavedChangesContext.test.jsx plus form/drawer tests | Audit quick win 4 identifies a confirmed functional defect; broader drawer coverage is higher risk. |  | Not deployed / not independently verified.
UX-008 | Wave C - C4 | UX Consistency | Consistent financial display formatting | Standardise en-GB money, negative sign placement, null/zero presentation and shared helpers without altering stored values or calculations. | P1 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Claude UX consistency audit | Engineering / Product |  | CVR-003; UX-010 | client/src/components/poDrawerHelpers.js; client/src/cvr/cvrHelpers.js; client/src/ledger/ledgerHelpers.js; payments/paymentCertificateProgress.js; client/src/styles/po-module.css; client/src/components/CVRPortfolio.jsx; client/src/components/CVRSummaryPage.jsx | Existing money-format and known-answer presentation tests; Hawthorn visual UAT; CVR Portfolio/Summary and Wave B presentation tests | Financial presentation is consistent in Home, CVR and Development screens; application-wide completion remains C4. |  | Not deployed / not independently verified.
UX-009 | Wave C - C1 | UX Consistency | Correct status colour semantics | Correct blocker, review, awaiting-approval, in-accounts and PO status tones while preserving domain status values. | P0 | Implemented | Confirmed deployed in de3331a release | Confirmed deployed in a1a947c release | Product Owner accepted; independent trial continuing | Yes | Pilot UX | Claude UX consistency audit | Engineering / Product | UX-004 | ADM-001; CERT-004; ACC-001 | DevelopmentOverview.jsx; AdminSuppliersPage.jsx; PaymentApprovalRun.jsx; PaymentReleaseWorklist.jsx; POList.jsx; client/src/styles/brand.css; client/src/styles/po-module.css; client/src/components/DevelopmentOverview.jsx | Focused component tests and visual UAT; client/src/components/DevelopmentCommercialReadiness.test.jsx; client/src/components/CVRPortfolio.test.jsx | Wave C1 completed the known Commercial Readiness colour/wording defect at 464b321. Other module-specific visual acceptance remains separately tracked. |  | Not deployed / not independently verified.
UX-010 | Wave C - C4 | UX Consistency | Numeric table alignment | Add and apply a shared tabular numeric-cell class to financial tables currently rendering money left-aligned. | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Claude UX consistency audit | Engineering / Product | UX-004 | UX-008; MAT-001 | client/src/styles/po-module.css; Approval, Release, Revenue, PlotMaster and Ledger components; client/src/styles/po-module.css; client/src/components/CVRPortfolio.jsx; client/src/components/CVRSummaryPage.jsx | Focused rendered table tests; zoom UAT; CVR presentation tests | CVR financial tables use tabular/right-aligned figures; remaining module coverage is C4. |  | Not deployed / not independently verified.
UX-011 | Wave C - C3 | CVR | Inline CVR action feedback | Replace native CVR alerts with accessible inline feedback, correct Reject styling and use one Create Next Period label. | P0 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Claude UX consistency audit | Engineering / Product | CVR-004 | UX-001; UX-002 | client/src/components/CVRWorkspace.jsx; CVRSummaryPage.jsx; CVRPortfolio.jsx; client/src/components/CVRSummaryPage.jsx; client/src/styles/po-module.css | CVR lifecycle/navigation component suites; client/src/components/CVRSummaryPage.interaction.test.jsx | Inline CVR feedback remains partial. Forecast Onboarding currently needs clearer rendering of server blockers, including unresolved ledger counts and source evidence, rather than a generic readiness error. |  | Not deployed / not independently verified.
UX-012 | Wave C - C4 | UX Consistency | Human-readable dates | Replace raw ISO dates in Purchase Orders and Purchase Ledger with the established BuildLite date formatter. | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Claude UX consistency audit | Engineering / Product |  | PO-002; LED-002 | client/src/components/POList.jsx; PurchaseLedger.jsx; poDrawerHelpers.js; server/services/cvrReportRenderer.js; client/src/styles/po-module.css | Focused PO/Ledger rendering tests; server/test/cvrReportRenderer.test.js | Human-readable dates exist in selected reports/views; a cross-module pass remains C4. |  | Not deployed / not independently verified.
UX-013 | BuildLite Commercial Product Polish | UX Consistency | Single page heading and permission-aware actions | Remove duplicate page h1 elements and hide New Development when the authenticated principal lacks permission. | P0 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Pilot UX | Claude UX consistency audit | Engineering / Product | UX-001 | CERT-001; ADM-001 | PaymentCertificateWorkspace.jsx; PurchaseLedger.jsx; DevelopmentList.jsx; client/src/components/DevelopmentList.jsx; client/src/components/DevelopmentWorkspace.jsx; client/src/components/ApplicationSidebar.jsx | Focused rendered heading and permission tests; client/src/components/DevelopmentList.test.jsx; client/src/components/ApplicationSidebar.test.jsx | Wave B and the sidebar improve heading/action hierarchy; application-wide completion remains partial. |  | Not deployed / not independently verified.
UX-014 | BuildLite Commercial Product Polish | UX Architecture | Shared component and interaction standard | Consolidate status badges, confirmation dialogs, drawers, tables, filters, feedback, empty states and focus behaviour into reviewed shared components. | P2 | Future Development | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Post-feedback UX | Claude UX consistency audit | Engineering / Product | UX-001 | UX-004; UX-007; UX-009; UX-010 |  | Cross-module visual, accessibility and commercial-workflow UAT | Higher-risk work: phase it after quick wins; avoid a global CSS rewrite. |  | Not deployed / not independently verified.
UX-015 | BuildLite Commercial Product Polish | Navigation | Navigation architecture and potential left-hand navigation | Evaluate a persistent left-hand navigation and coherent route/frame model while preserving permissions, deep links and commercial context. | P2 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Post-feedback UX | Claude UX consistency audit | Engineering / Product | UX-001 | CVR-004; UX-014 | client/src/App.jsx; client/src/navigation/NavigationContext.jsx; useRegisterNavigationFrame.js | Navigation regression suite plus Product Owner prototype UAT | The collapsible desktop and tablet-overlay sidebar is implemented at 639f645; hosted human acceptance remains separate. |  | Not deployed / not independently verified.
BRAND-001 | BuildLite Commercial Product Polish | Branding | Financial Data Flow Home background | Introduce a restrained dark-green financial data-flow motif in the Home welcome area only, preserving readability, navigation and reduced-motion behaviour. | P2 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Prototype | Claude UX consistency audit / Product Owner concept | Engineering / Product |  | UX-003; BRAND-002 | client/src/components/BuildLiteHome.jsx; client/src/styles/po-module.css | BuildLiteHome.test.jsx; reduced-motion and visual UAT | Financial Data Flow V2 is implemented in production Home at 639f645. |  | Not deployed / not independently verified.
BRAND-002 | BuildLite Commercial Product Polish | Branding | Abstract skyline BuildLite logo | Explore an abstract skyline/financial-flow BuildLite mark without replacing the current logo until separately approved. | P2 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Later branding | Claude UX consistency audit / Product Owner concept | Engineering / Product |  | BRAND-001 |  | Brand concept review and multi-size accessibility checks | Approved Skyline symbol/horizontal assets and production header integration are implemented at 639f645. |  | Not deployed / not independently verified.
HOME-001 | BuildLite Commercial Product Polish | Home Dashboard | Authoritative Home dashboard and hosted acceptance | Provide tenant-scoped Commercial Overview KPIs, permission-filtered Attention Required and authoritative Recent Activity; verify deployment and human acceptance separately. | P1 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Release / acceptance | October 2026 competitor reconciliation | Engineering / Product |  | REP-001; UX-015 | server/services/homeDashboardService.js; server/routes/homeDashboardRoutes.js; client/src/components/BuildLiteHome.jsx | server/test/homeDashboardService.test.js; server/test/homeDashboardRoutes.test.js; client/src/components/BuildLiteHome.test.jsx | Implemented at 639f645. Dashboard uses authenticated tenant identity, restricted/unavailable states, bounded attention and audit activity. | Hosted acceptance and performance verification | Not independently verified; implementation status is repository-based.
ONB-001 |  | Onboarding | Unified Excel onboarding | Unify existing Budget, Cost Code, Plot, Sales Register, Order Matrix and Ledger import experiences with reusable mappings, previews, clear validation and restartable setup. | P1 | Partially Implemented | Land Appraisal v2 confirmed in de3331a | Land Appraisal, Plot Master and Forecast Onboarding used in Main trial | Poplar Forecast Onboarding pilot PASS; common importer programme remains partial | Yes | Competitive essential | October 2026 competitor reconciliation | Engineering / Product | ADM-001 | LED-001; PO-001 | CVRBudgetImportWizard.jsx; SetupCostCodeImportWizard.jsx; PlotScheduleImportWizard.jsx; SalesRegisterImportWizard.jsx; PurchaseLedgerImportWizard.jsx | Existing focused importer tests | Forecast Onboarding handles worksheet selection, raw Excel values, exclusions, source fingerprint, governed floors and atomic adoption. A standard Cost Code / Target EFC template and consistent cross-importer sheet/header UX remain open. | Reuse existing import authorities; customer file discovery helps but does not gate general UX work | Not independently verified; implementation status is repository-based.
HTI-001 |  | House-type Intelligence | House-type cost intelligence | Build reusable house-type cost libraries, plot/package rate comparison, historic trade rates and budget-versus-actual insight using existing plot, Package and Cost Code authorities. | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Differentiation | October 2026 competitor reconciliation | Engineering / Product |  | PO-001; REV-001; TEND-001 | client/src/components/HouseTypeRevenueTable.jsx; client/src/components/OrderMatrixEditor.jsx | HouseTypeRevenueTable.test.jsx; orderMatrixRoutes.test.js | House-type revenue and plot structures exist; governed cost/rate intelligence is not implemented. | Stable multi-cost-code and Package identity semantics | Not independently verified; implementation status is repository-based.
RET-001 |  | Certificates | Retention release management | Track outstanding retention, due/release dates, governed release authority and Accounts handoff without changing approved certificate valuation evidence. | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete | Yes | Differentiation | October 2026 competitor reconciliation | Engineering / Product | CERT-002 | ACC-001; ACC-002 | payment certificate calculations/repositories; PaymentReleaseWorklist.jsx | paymentCertificateFinancials.test.js; paymentReleaseFoundation.test.js | Retention deductions exist; an operational release ledger and lifecycle were not found. | Certificate authority and Accounts export contract | Not independently verified; implementation status is repository-based.
CVR-008 | BuildLite Commercial Product Polish | CVR | Monthly CVR Summary PDF | Provide a professionally branded, A4 landscape, print-ready PDF for each development monthly CVR. It must identify the development, reporting period and lifecycle status; present the existing authoritative Forecast Revenue, EFC, Gross Profit, Margin, Cost to Complete, budget, period movements and commercial variances; include the Commercial Head Summary, commercial exceptions and commentary; show prepared, submitted and approved attribution where available; use page numbering and repeated table headers; clearly mark Draft and Submitted reports as provisional; use immutable governed snapshot evidence for Locked CVRs; and provide a Download PDF action on CVR Summary. Values must be exact existing BuildLite values, never invented or independently recalculated. | P0 | Implemented | Recorded deployed to JB Homes | Poplar Road hosted PDF downloaded; exact live application SHA not separately captured | Design and real-data reconciliation accepted; Poplar Draft report used in pilot | Yes | Next functional development after Wave B Development Workspace closeout | Product Owner / Commercial Director experience - 20 October 2026 | Engineering / Product |  | REP-001; CVR-004; CVR-007; OPS-006; BRAND-002 | client/src/components/CVRSummaryPage.jsx; client/src/cvr/cvrSummaryHelpers.js; server/services/commercialDocumentRenderer.js; server/services/commercialDocumentRepository.js; server/services/pdf.js; server/services/cvrReportService.js; server/services/cvrReportRenderer.js; server/templates/cvr-summary-report-v1.hbs; server/routes/cvrRoutes.js; client/src/components/CVRSummaryPage.jsx | client/src/components/CVRSummaryPage.kpi.test.jsx; client/src/components/CVRSummaryPage.interaction.test.jsx; server/test/commercialDocumentFoundation.test.js; server/test/cvrReportService.test.js; server/test/cvrReportRenderer.test.js; server/test/cvrReportRoutes.test.js; client/src/components/CVRSummaryPage.interaction.test.jsx; Oak Meadow P02 real-data reconciliation | Implemented and used for Poplar Road Draft reporting. Commentary printed literal Markdown asterisks; formatting/sanitisation remains a bounded UX correction. Draft output is provisional, not approved evidence. | Dependencies: approved Wave B closeout; authoritative CVR Summary presentation data; locked snapshot selection; company/development branding; authenticated download and report authority. Risks: independent recalculation or mutable data could disagree with governed CVR evidence; long commercial-head tables need deterministic pagination. Acceptance: A4 landscape branded PDF downloads from CVR Summary; all displayed totals match the on-screen authoritative model and locked snapshot evidence exactly; Draft/Submitted are visibly provisional; Locked is tied to immutable evidence; repeated headers, page numbers, commentary and available attribution render correctly. | Implemented at d9de870 and recorded deployed to JB Homes. Owner-UAT deployment and hosted human acceptance remain separate.
CVR-009 | BuildLite Commercial Product Polish | CVR | CVR Worksheet Excel export | Provide a downloadable .xlsx export of the current CVR Worksheet containing complete cost-code-level financial detail, the existing worksheet columns and exact financial values, numeric Excel cells with appropriate financial formatting, cost codes preserved as identifiers, retained totals and commercial hierarchy, and the reporting period, development identity and lifecycle status. Locked periods must export governed historical evidence and Draft periods must be identified as provisional. Export must not mutate authoritative CVR data and there is no requirement to import an edited workbook back into BuildLite. | P1 | Implemented | Not independently verified | Hosted Poplar workbook downloaded; exact live application SHA not separately captured | Poplar Road pilot PASS; real print readability remains human review | Yes | Immediately after Monthly CVR Summary PDF | Product Owner / Commercial Director experience - 20 October 2026 | Engineering / Product | CVR-008 | CVR-004; REP-001 | client/src/cvr/cvrWorksheetExport.js; client/src/components/CVRWorkspace.jsx; server/services/cvrReportService.js; server/routes/cvrRoutes.js | client/src/cvr/cvrWorksheetExport.test.js; server/test/cvrReportService.test.js; server/test/cvrReportRoutes.test.js; Poplar DEV-002 known-answer reconciliation | Implemented at 02d9856. A3 landscape, one page wide/multiple tall, frozen/repeated headers, filters, numeric values and repeating Draft/Submitted/Locked authority. Excel exact-pence validation is isolated from the Summary PDF path. | Draft uses governed provisional close; Locked uses immutable snapshot; no import/mutation path. | Implemented and pushed 28 October 2026; hosted Poplar workbook observed, exact deployment SHA unverified.
PO-005 |  | Purchase Orders | PO provenance, archive and attribution | Expose company-wide PO discovery, archived visibility, authenticated creator/time and distinguish creation, submission and later changes. | P1 | Outstanding | Investigation outstanding | Investigation outstanding | Required / not recorded complete | Yes | Pilot investigation | JB Homes PO204 | Engineering / Product |  | FB-001; PO-003 | Purchase Order register, archive and history services | Future focused route/UI and audit regressions | PO204 has not been proved saved. Existing persisted records carry provenance, but current user-facing discovery is insufficient. | Read-only tenant evidence requires separate authorisation
PO-006 |  | Purchase Orders | Governed PO void, tombstone and numbering | Prevent deleted Drafts from erasing transaction history or enabling ambiguous number reuse; design transaction-safe tenant numbering and void evidence. | P0 | Outstanding | Not deployed | Not deployed | Product Owner decision required | No | Commercial governance | JB Homes PO204 | Engineering / Product | PO-003 | PO-005 | Existing PO creation/deletion and number allocation services | Design and migration evidence required | Current Draft deletion may remove history and MAX+1 allocation may reuse a number. No change is authorised in this documentation sync. | Requires separately approved authority/schema design
ADM-002 |  | Administration | Membership state and audit clarity | Distinguish Clerk identity, invitation and tenant membership states; show recorded actor, reason and time for activation/deactivation. | P1 | Outstanding | Audit discrepancy observed | Not independently verified | Required / not recorded complete | Yes | Pilot UX | John Burke membership audit | Engineering / Product |  | FB-001 | Administration Users and tenant membership authority audit | Guarded JB read-only audit 23 Oct 2026 | Audit recorded invitation acceptance/activation only, no deactivation/reactivation event; the Inactive UI state remains unexplained. | Do not infer inactivity or deployment cause
UX-016 | BuildLite Commercial Product Polish | UX Consistency | Optional per-user light/dark theme | Provide an accessible per-user Dark/Light preference while retaining BuildLite charcoal/emerald identity and commercial readability. | P1 | Future Development | Not deployed | Not deployed | Discovery required | Yes | Pilot UX | John Burke feedback | Engineering / Product | UX-004 | UX-006; BRAND-001; BRAND-002 | brand.css, po-module.css and remaining hard-coded colour inventory | Future contrast, persistence, chart, table and 200% zoom acceptance | Dark remains the current production identity. Optional light mode is requested but not designed or implemented. | Preference persistence and contrast authority decision
DEV-001 |  | Developments | Governed development retirement and supersession | Retire or supersede an incorrectly established development without deleting immutable evidence or falsely marking it Complete. | P1 | Outstanding | Not deployed | Not deployed | Product Owner decision required | Yes | Pilot governance | Levison Rose recovery | Engineering / Product |  | FB-002; ONB-001 | Development lifecycle and evidence dependencies | Future authority and dependency regressions | General governed retirement/supersession remains outstanding. The earlier immediate Levison reset proposal is reassessed after successful DEV-002 Draft onboarding; do not delete or recreate without explicit authority. | Requires authority design; no direct SQL deletion
CERT-006 |  | Certificates | Certificate financial column clarity | Make VAT, recoveries, retention, Net Payment and payment-release semantics explicit without changing stored certificate calculations. | P2 | Needs Verification | JB trial observation | Not independently verified | Required / not recorded complete | Yes | Pilot UX | JB Certificate Register trial | Engineering / Product | CERT-001 | CERT-004; CERT-005 | Certificate Register and governed certificate financial fields | Known-answer financial presentation review | Net Payment may include VAT or recoveries not evident from Gross/Retention alone. Verify semantics before any presentation change; Locked/Approved is not Paid. | No financial calculation change
OPS-010 |  | Operations | Obsolete hosted services audit | Inventory unused Render/Netlify services, domains, billing, dependencies and rollback value before any controlled retirement. | P2 | Outstanding | Not started | Not started | Operator evidence required | No | Operations | 24 Oct continuity | Operations |  | OPS-005; OPS-007 | Provider inventory and Technical Operations Manual | Future read-only provider audit | No hosted service is authorised for deletion. Audit first and preserve rollback evidence. | Provider access and Product Owner approval
FB-004 |  | Customer Feedback | Valhalla Welford Road trial closeout | Complete the independent Valhalla trial after safe 75-plot correction, Revenue entry/reconciliation and concise NIA compatibility guidance. | P1 | Partially Implemented | Not applicable | Safe Plot Master confirmed in a1a947c | Required / trial continuing | Yes | External validation | Valhalla Welford Road trial | Customer Discovery |  | ONB-001; HTI-001; REV-001 | Safe Plot Master bulk update and Revenue workspaces | Product Owner 75/75 match, 65 changes and ftÂ² checks | Plot identities and ftÂ² reconcile after the 75/75 update. Next: preserve the existing development, reconcile selling values/Revenue, then exercise Package-to-CVR end-to-end UAT with realistic approval roles. | Do not weaken GIA/NIA authority
CVR-010 |  | CVR | Draft CVR Forecast Onboarding import | Import Cost Code / Target EFC evidence into a Draft monthly CVR through governed preview, forecast floors, explicit exclusions, source fingerprint, reasoned QS confirmation and atomic Projected Adjustment application. Preserve omitted codes, historic facts, adjustment history and immutable snapshots. | P1 | Implemented | Not independently verified | Poplar Road pilot used hosted feature; exact live application SHA not separately captured | Poplar Road pilot PASS with governed-floor reconciliation | Yes | Pilot onboarding | Levison Poplar Road trial â€” 28 October 2026 | Engineering / Product |  | CVR-003; CVR-007; ONB-001; UX-011 | client/src/components/CVRForecastImportWizard.jsx; client/src/cvr/forecastOnboardingImport.js; server/services/cvrForecastOnboardingService.js; server/routes/cvrRoutes.js | client/src/components/CVRForecastImportWizard.test.jsx; client/src/cvr/forecastOnboardingImport.test.js; server/test/cvrForecastOnboarding.test.js; Poplar 95-row pilot | Implemented at ca361a9 plus e10045d. Poplar adopted EFC Â£767,712.02 after governed floors and active-code membership reconciliation. Original target, floor uplift and audit are retained. | Open UX: standard two-column template, clearer floor reconciliation and server blocker presentation. | Implemented and pushed; hosted pilot use recorded, exact deployment SHA unverified.
CVR-011 |  | CVR | Current-month Draft with month-end close gate | Permit a monthly CVR Draft for the current calendar month while prohibiting future-month creation and preventing Submit or Approve & Lock until the reporting month has ended. Preserve Site Start sequencing, P numbering, skipped months and server authority. | P0 | Implemented | Not independently verified | Poplar Road October P01 created during October trial | Product Owner pilot acceptance; month-end close restriction retained | No | Release / pilot workflow | Levison Poplar Road trial â€” 28 October 2026 | Engineering / Product |  | CVR-005; CVR-004 | server/services/cvrPeriodRepository.js; client/src/cvr/cvrReportingMonth.js; client/src/components/CvrReportingMonthDialog.jsx | server/test/cvrDevelopmentBudgetIntegration.test.js; server/test/siteStartPeriodFoundation.test.js; client/src/cvr/cvrReportingMonth.test.js | Implemented at f28cdad. October P01 Draft could be created before month end; submission and lock remained prohibited until November. | No future-month CVR; immutable snapshots and reporting-period authority unchanged. | Implemented, pushed and exercised by Poplar Road pilot.

## Overview
BuildLite Master Improvement Register v0.8
86 requirements: all 84 v0.7 IDs/descriptions/priorities preserved plus two distinct 28 October CVR capabilities. Evidence states remain separate.
Measure | Count / value | Meaning
Total items | 86 | 76-item v0.6 baseline and eight v0.7 additions preserved; two new IDs added
Implemented | 24 | Implementation status; deployment and acceptance separate
Partially Implemented | 29 | Implementation status
Outstanding | 14 | Implementation status
Needs Verification | 12 | Implementation or evidence requires verification
Future Development | 7 | Strategic future capability
P0 priority | 15 | Original priorities preserved
P1 priority | 33 | Original priorities preserved
P2 priority | 32 | Original priorities preserved
P3 priority | 6 | Original priorities preserved
Wave C1 / C2 | Implemented and deployed | Main a1a947c; JB de3331a; ongoing human UAT retained
Wave C3 | PAUSED | Discovery prompt not sent; no implementation authorised

## Roadmap
BuildLite Roadmap v0.8
Levison Poplar onboarding/reporting delivered; Valhalla end-to-end trial is next. Wave C3 remains PAUSED. Pilot authority and governed evidence take precedence.
Horizon | Action | Business benefit | Benchmark | Register IDs | Dependencies | Complexity | Product Owner decision
Delivered | Wave C1 - Commercial Readiness clarity | Remove misleading yellow Needs Attention when a Site Start-backed chain is genuinely ready. | Pilot clarity | CVR-001; UX-009 | 71c103f authority remains unchanged | Low | Implemented 464b321; deployed Main/JB; ongoing trial acceptance
Delivered | Wave C2 - Certificate Register | Search, filters, actionable status presentation and acceptance. | Independent QS operation | CERT-001; CERT-005 | Existing certificate evidence and permissions | Medium | Implemented 635b1b8; deployed Main/JB; ongoing user UAT
PAUSED | Action safety | Unsaved changes plus loading, disabled, success and error states. | Data-loss prevention | UX-007; UX-002; UX-011 | Existing edit-state and navigation guards | Medium | Discovery prompt not sent; resume only with explicit Product Owner authority
Wave C4 | Visual consistency | Financial formatting, dates, numeric alignment and dark-theme cleanup. | Premium presentation | UX-005; UX-006; UX-008; UX-010; UX-012 | Wave A tokens | Low?Medium | Module-by-module boundary
Wave C5 | Workflow presentation | Prelims, Selling Costs, lump-sum Package, PO and commercial-document presentation. | First-time operation | PRE-002; SELL-001; PO-004; PO-002 | Existing governed workflows | Medium | No workflow redesign
Delivered | Monthly CVR Summary PDF | Professional monthly Commercial Director and management-team review, circulation and record keeping from governed CVR evidence. | Professional branded commercial reporting without spreadsheet reproduction. | CVR-008 | Implemented at d9de870; migration 069 supplies future Locked GIA evidence | Medium | Implemented and recorded deployed; hosted human acceptance remains separate
Delivered / pilot pass | CVR Worksheet Excel export | Export complete cost-code-level CVR detail for structured review and circulation without changing BuildLite authority. | Excel-compatible QS workflow while retaining BuildLite as the system of record. | CVR-009 | 02d9856; governed Worksheet rows; immutable Locked snapshots; provisional close evidence | Medium | Implemented and used for Poplar Draft; exact live SHA and print readability remain separate evidence
P0 | Hosted safety, release parity, recovery evidence and commercial PDF acceptance | Operational confidence with real financial evidence | Established vendors | OPS-003; OPS-006/007/009 | Owner dashboard evidence; legitimate document | Medium | Confirm acceptance window
P1 | Controlled Accounts schedule export and reconciliation | Completes commercial-to-Accounts chain | Planyard; DuoApp; Eque2 | ACC-001; ACC-002 | Export identity and duplicate policy | Medium | Export format/system
P1 partial / pilot proven | Unified Excel onboarding and importer standardisation | Faster move from Excel and lower setup effort | Planyard | ONB-001; ADM-001; FB-002; CVR-010; DEV-001 | de3331a Land Appraisal v2; remaining importer gaps | Medium–High | Forecast Onboarding pilot passed; common importer UX and standard template remain open
P1 | Cumulative ledger policy | Reliable monthly actual-cost loading | Accounting-connected tools | LED-001; LED-003 | Import contract decision | Medium | Delta-only vs cumulative
P1 | Multi-cost-code PO authority | Fits real procurement without duplicate orders | Planyard; ERP | PO-001 | Package/certificate allocation semantics | High | One Package vs multiple authorities
P1 | Portfolio movement reporting and certificate filters | Director visibility and everyday speed | Planyard; Payapps | REP-001; HOME-001; CERT-001/005 | Locked CVRs | Low–Medium | Minimum filter set
P2 | BuildLite Commercial Product Polish programme | Premium, consistent and intuitive product quality | DuoApp; Buildxact usability | UX-004–UX-014 plus mapped module items | Approved Home/sidebar standard | Medium | Sequence by customer impact
P2 | House-type intelligence and retention release | Housebuilder differentiation and complete payment evidence | DuoApp; BuildQS/Payapps | HTI-001; RET-001 | Stable procurement and Accounts contract | Medium–High | First intelligence use case
P2 | Development cash flow and read-only Assistant | Finance Director insight and evidence explanation | Planyard; BuildPredict | CASH-001; AI-001 | Reliable timings and server evidence | High | Scope after essentials
P3 | Direct accounting APIs, tendering, supplier portal, portfolio cash flow | Strategic expansion after foundations | Market-wide | ACC-001; TEND-001; PORT-001; CASH-002 | Prior P1/P2 foundations | High–Very High | Customer validation
P0 pilot | JB PO204 and PO governance | Establish actual evidence and make provenance/numbering auditable | Independent trial | FB-001; PO-005; PO-006 | Read-only evidence then separately approved design | Medium-High | PO204 remains outstanding
Delivered milestone / reassess reset | Levison Poplar Road retrospective onboarding | Governed Draft P01, Sage actuals and management reports delivered without rewriting history | Pilot recovery | FB-002; CVR-009; CVR-010; CVR-011; ONB-001; DEV-001 | Preserve Draft/provisional status and historical appraisal incident | Medium | Do not reset successful DEV-002 without explicit authority
P1 trial | Valhalla Revenue reconciliation and end-to-end UAT | Complete real owner-led workflow after safe Plot correction | Independent trial | FB-004; REV-001; HTI-001 | Selling values and governed Revenue | Low-Medium | 75/75 matched; preserve development; Revenue and workflow UAT next
P1 discovery | Per-user light/dark theme | Accessible user choice without losing BuildLite identity | User preference | UX-016 | Token/hard-coded colour and persistence audit | Medium | Discovery only; C3 remains paused

## Commercial Product Polish
BuildLite Commercial Product Polish
Premium professional financial software: visually impressive, consistent and accessible without excessive animation or reduced usability.
Workstream | Module | Scope | Priority | Mapped IDs | Acceptance | Dependencies / evidence | Complexity / state | Notes
Wave A - completed implementation | Cross-application | Visual tokens, shared CSS, button/status foundations and dark-surface corrections. | P0/P2 | UX-004; UX-005; UX-006; UX-008; UX-009; UX-010 | Implementation complete; remaining partial children retain UAT | 239273a | Completed implementation | Not every child UX item is complete
Wave B - completed implementation | Developments | Development List, identity, navigation rail, KPI states, readiness and Packages. | P1/P2 | CVR-001; CVR-002; ADM-001; UX-013 | Implementation complete; yellow readiness presentation remains C1 | 15b0845; 71c103f | Completed implementation | Commercial authority unchanged
Wave C1 - completed implementation | Development Overview | Remove misleading yellow Needs Attention for genuinely ready Site Start-backed chains. | Original priorities retained | CVR-001; UX-009 | Approved presentation; continuing trial acceptance | 464b321; Main a1a947c; JB de3331a | Implemented and deployed | No authority changes
Wave C2 - completed implementation | Certificates | Search, filters, actionable statuses and acceptance. | Original priorities retained | CERT-001; CERT-005 | Isolated browser acceptance passed; hosted UAT continuing | 635b1b8; Main a1a947c; JB de3331a | Implemented and deployed | Human acceptance required
Wave C3 - Action safety (PAUSED) | Cross-application | Unsaved changes, loading, disabled, success and error states. | Original priorities retained | UX-007; UX-002; UX-011 | No silent loss or duplicate action; honest feedback | Existing edit/navigation guards | PAUSED | Discovery prompt not sent; explicit authority required
Wave C4 - Visual consistency | Cross-application | Financial formatting, dates, numeric alignment and dark-theme cleanup. | Original priorities retained | UX-005; UX-006; UX-008; UX-010; UX-012 | Module checklist at laptop width and 200% zoom | Wave A tokens | Low-Medium | No global CSS rewrite
Wave C5 - Workflow presentation | Commercial workflows | Prelims, Selling Costs, Package, PO and document presentation. | Original priorities retained | PRE-002; SELL-001; PO-004; PO-002 | Independent operation without workflow changes | Existing governed workflows | Medium | Relevant certificate/document UX included
CVR Portfolio, Summary and Worksheet | CVR | KPI ribbons, movements, navigation and action feedback. | P0/P2 | CVR-003; CVR-004; CVR-006; CVR-007; CVR-009; CVR-010; CVR-011; UX-011; REP-001 | Known-answer financial and visual UAT | 8eb9e2c; 147b4f9; cac6a1a | Implemented/partial | No formula changes
Monthly CVR Summary PDF | CVR Summary | A4 landscape governed monthly report with immutable Locked evidence. | P0 | CVR-008 | Real-data reconciliation and hosted download acceptance | 6cb5879; d9de870 | Implemented and deployed | Hosted human acceptance remains distinct
CVR Worksheet Excel export â€” implemented | CVR Worksheet | Download-only .xlsx with governed hierarchy, values and period authority. | P1 | CVR-009 | Poplar known-answer reconciliation; A3 print/readability review | 02d9856; governed report payload and ExcelJS | Implemented / pilot pass | Exact live deployment SHA and human print readability remain distinct
Payment Approval | Payments | Consistent headers, statuses and financial tables. | P2 | CERT-004; UX-005; UX-008; UX-009; UX-010 | Director workflow UAT | Existing authority | Low-Medium | Authority unchanged
Administration and onboarding | Administration | Readiness, mapping, templates and permission-aware actions. | P1/P2 | ADM-001; ONB-001; UX-002; UX-013 | First-company setup rehearsal | Existing importers | Medium | Client Cost Codes remain client-owned
Responsive and accessible shell | Application shell | Sidebar, worksheets, focus, zoom, reduced motion and financial readability. | P0/P2 | UX-007; UX-014; UX-015; BRAND-001; BRAND-002 | Keyboard, 200% zoom, tablet/mobile and reduced-motion checks | 639f645 | Implemented/ongoing | Production shell implemented
Optional light/dark theme | Application shell | Per-user accessible theme preference retaining charcoal/emerald identity. | P1 | UX-016 | Contrast, tables, charts, focus, zoom and persistence | Wave A tokens and hard-coded colour audit | Future discovery | No implementation authorised

## Needs UAT
Needs Human UAT / Acceptance
Implementation evidence is not deployment or human acceptance.
ID | Module | Item | Priority | Implementation | JB Homes | Owner-UAT | Acceptance
LED-001 | Purchase Ledger | Incremental monthly ledger imports | P2 | Partially Implemented | Not independently verified | Poplar Road pilot used server-authoritative ledger after configuration correction | Split invoice and supplier-less journal pilot PASS; cumulative import policy remains open
LED-002 | Purchase Ledger | Ledger exception workflow | P2 | Partially Implemented | Not independently verified | Poplar Road governed ledger exceptions resolved for Draft close | Pilot PASS for Cost Code resolution; general correction workflow remains partial
CVR-001 | CVR | Development Budget readiness warning | P1 | Implemented | Confirmed deployed in de3331a release | Confirmed deployed in a1a947c release | Product Owner accepted; independent trial continuing
CVR-002 | CVR | Overview KPI blanks | P2 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete
CVR-003 | CVR | Budget and EFC terminology | P2 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete
CVR-004 | CVR | CVR navigation | P2 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete
CVR-006 | CVR | Responsive KPI ribbon | P3 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete
CVR-007 | CVR | P03 movement explanation | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
PO-001 | Purchase Orders | Multi-cost-code orders | P1 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
PO-002 | Purchase Orders | PDF branding and approvals | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
PO-004 | Purchase Orders | Lump-sum trade package simplicity | P2 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete
CERT-001 | Certificates | Search and filters | P1 | Implemented | Confirmed deployed in de3331a release | Confirmed deployed in a1a947c release | JB register functioning; ongoing user UAT
CERT-003 | Certificates | Late notice control | P1 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
CE-001 | Commercial Events | Expected liability UX | P2 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete
MAT-001 | Order Matrices | Matrix header alignment | P3 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete
PRE-001 | Prelims | Programme date dependency | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
PRE-002 | Prelims | Template adoption UX | P2 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete
SELL-001 | Selling Costs | Detailed template UX | P2 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete
ADM-001 | Administration | Company readiness flow | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
UX-001 | Navigation | Navigation and return paths | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
UX-002 | Navigation | Post-action button states | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
ACC-001 | Accounts Integration | Sage/Xero integration | P1 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
ACC-002 | Accounts Integration | Payment Release export | P1 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
AI-001 | Assistant | Authoritative commercial assistant | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
OPS-003 | Operations | Hosted safety configuration | P0 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete
OPS-005 | Operations | CI and deployment tracking | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
REP-001 | Reporting | Portfolio CVR dashboard | P1 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
FB-001 | Customer Feedback | John Burke demo feedback | P1 | Outstanding | Not independently verified | Not independently verified | Required / not recorded complete
FB-002 | Customer Feedback | Levison discovery | P1 | Partially Implemented | Not independently verified | Poplar Road DEV-002 retrospective onboarding delivered in Main trial | Draft P01 reporting milestone delivered to Matt; commercial interpretation pending
FB-003 | Customer Feedback | Cotswold Oak response | P2 | Outstanding | Not independently verified | Not independently verified | Required / not recorded complete
LED-003 | Purchase Ledger | Cumulative accounting-extract import policy | P1 | Outstanding | Not independently verified | Not independently verified | Required / not recorded complete
OPS-006 | Operations | Hosted commercial-document PDF acceptance | P0 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete
UAT-001 | UAT | Hawthorn Gardens current-mechanics recovery | P1 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete
OPS-009 | Operations | Verified recovery drill evidence | P0 | Needs Verification | Not independently verified | Not independently verified | Required / not recorded complete
CERT-005 | Certificates | Certificate register acceptance criteria | P1 | Implemented | Confirmed deployed in de3331a release | Confirmed deployed in a1a947c release | Isolated browser acceptance passed; hosted trial continuing
UX-004 | UX Consistency | Complete missing shared CSS rules | P0 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete
UX-005 | UX Consistency | Neutralise starter styles and standardise payment headers | P0 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
UX-006 | UX Consistency | Dark-theme surface corrections | P0 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
UX-007 | Navigation | Reliable unsaved-changes protection | P0 | Outstanding | Not independently verified | Not independently verified | Required / not recorded complete
UX-008 | UX Consistency | Consistent financial display formatting | P1 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
UX-009 | UX Consistency | Correct status colour semantics | P0 | Implemented | Confirmed deployed in de3331a release | Confirmed deployed in a1a947c release | Product Owner accepted; independent trial continuing
UX-010 | UX Consistency | Numeric table alignment | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
UX-011 | CVR | Inline CVR action feedback | P0 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
UX-012 | UX Consistency | Human-readable dates | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
UX-013 | UX Consistency | Single page heading and permission-aware actions | P0 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
UX-014 | UX Architecture | Shared component and interaction standard | P2 | Future Development | Not independently verified | Not independently verified | Required / not recorded complete
UX-015 | Navigation | Navigation architecture and potential left-hand navigation | P2 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete
BRAND-001 | Branding | Financial Data Flow Home background | P2 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete
BRAND-002 | Branding | Abstract skyline BuildLite logo | P2 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete
HOME-001 | Home Dashboard | Authoritative Home dashboard and hosted acceptance | P1 | Implemented | Not independently verified | Not independently verified | Required / not recorded complete
ONB-001 | Onboarding | Unified Excel onboarding | P1 | Partially Implemented | Land Appraisal v2 confirmed in de3331a | Land Appraisal, Plot Master and Forecast Onboarding used in Main trial | Poplar Forecast Onboarding pilot PASS; common importer programme remains partial
HTI-001 | House-type Intelligence | House-type cost intelligence | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
RET-001 | Certificates | Retention release management | P2 | Partially Implemented | Not independently verified | Not independently verified | Required / not recorded complete
CVR-008 | CVR | Monthly CVR Summary PDF | P0 | Implemented | Recorded deployed to JB Homes | Poplar Road hosted PDF downloaded; exact live application SHA not separately captured | Design and real-data reconciliation accepted; Poplar Draft report used in pilot
CVR-009 | CVR | CVR Worksheet Excel export | P1 | Implemented | Not independently verified | Hosted Poplar workbook downloaded; exact live application SHA not separately captured | Poplar Road pilot PASS; real print readability remains human review
PO-005 | Purchase Orders | PO provenance, archive and attribution | P1 | Outstanding | Investigation outstanding | Investigation outstanding | Required / not recorded complete
ADM-002 | Administration | Membership state and audit clarity | P1 | Outstanding | Audit discrepancy observed | Not independently verified | Required / not recorded complete
UX-016 | UX Consistency | Optional per-user light/dark theme | P1 | Future Development | Not deployed | Not deployed | Discovery required
DEV-001 | Developments | Governed development retirement and supersession | P1 | Outstanding | Not deployed | Not deployed | Product Owner decision required
CERT-006 | Certificates | Certificate financial column clarity | P2 | Needs Verification | JB trial observation | Not independently verified | Required / not recorded complete
FB-004 | Customer Feedback | Valhalla Welford Road trial closeout | P1 | Partially Implemented | Not applicable | Safe Plot Master confirmed in a1a947c | Required / trial continuing
CVR-010 | CVR | Draft CVR Forecast Onboarding import | P1 | Implemented | Not independently verified | Poplar Road pilot used hosted feature; exact live application SHA not separately captured | Poplar Road pilot PASS with governed-floor reconciliation

## Read Me - Change Log
Read Me / Change Log - Version 0.8
Version 0.8 preserves all 84 v0.7 requirements and adds two distinct CVR capabilities from the 28 October evidence.
Topic | Detail | Governance
Baseline | Source: BuildLite_Master_Improvement_Register_v0_7.xlsx | v0.6 retained unchanged
Reconciliation | 86 requirements reconciled at 02d9856 and documented 28 October pilot evidence | 24 Implemented; 29 Partially Implemented; 14 Outstanding; 12 Needs Verification; 7 Future Development
Evidence separation | Implementation, deployment, independent verification and human UAT remain separate | Committed or deployed does not mean accepted
Wave A | Visual foundations completed at 239273a | Partial child items retain UAT
Wave B/C1/C2 | Wave B, C1 and C2 implementation completed; C1/C2 confirmed in Main a1a947c and JB de3331a | Human trial acceptance remains separately recorded
CVR-008 | Monthly CVR Summary PDF implemented and used for Poplar Draft reporting; Markdown commentary snag retained | Design approval and real-data reconciliation do not replace hosted acceptance
CVR-009 | CVR Worksheet Excel export marked Implemented / pilot pass at 02d9856 | A3 governed export; exact live SHA and print readability remain separate acceptance evidence
Wave C | C1/C2 completed; C3 PAUSED; C4/C5 queued | C3 discovery prompt not sent
v0.5 unsupported-ID discrepancy | v0.5 Change Log referred to TEN-002, DEP-004, OPS-013 and OPS-014, but none exists in the 76-item Master Register. The historical claim is disclosed; no IDs were created or deleted. | Product Owner approval required before creating any such requirements
Trial coordination | Levison Poplar onboarding milestone delivered in Main; Valhalla is next; JB investigations continue | Critical financial, authority or workflow defects take priority; confirmed findings enter through controlled updates
Descriptions and priorities | All 84 v0.7 IDs/descriptions/priorities preserved; CVR-010 and CVR-011 added for distinct capabilities | No silent redefinition
Workbook scope | Workbook-only update | No application, database, migration, commit, push or deployment action
24 Oct continuity | Added PO-005/006, ADM-002, UX-016, DEV-001, CERT-006, OPS-010 and FB-004. | New IDs only for genuinely distinct requirements; 76-item baseline retained
Deployment evidence | Git pushed 02d9856; Main frontier 070 recorded; exact current Render/Netlify SHAs not separately captured | Push and deployment remain distinct
Pilot evidence | PO204 and membership cause remain open; Poplar Draft delivered; Valhalla Revenue/end-to-end UAT next | No unsupported cause or completion claim
Importer programme | Forecast Onboarding pilot recorded under CVR-010; standard template/common importer UX remains ONB-001 | Module-specific authority retained
28 Oct additions | Added CVR-010 Forecast Onboarding and CVR-011 current-month Draft/month-end close gate | New IDs only for distinct implemented capabilities; no duplicate requirements
Levison milestone | Draft P01 EFC Â£767,712.02 / Actual Â£405,569.54; PDF and Excel sent to Matt | Provisional, not approved or proof of loss; earlier reset proposal reassessed
Authority incident | Missing ledger server-authority flag caused browser/server divergence before governed reimport | OPS-003 remains open P0 safety requirement
Unresolved evidence | Â£648.70 Sage source/import difference; Â£0.19 movement attribution difference; live tier SHAs unverified | No automatic financial correction authorised
Wave C | Wave C3 remains PAUSED; C4/C5 queued | No discovery or implementation authorised